## Task_Table1 (hidden)
Initative | Process | Phase | Process level | Process group | Percent complete | IT process Consultant | Responsible | Care taker | Start | End | Duration | Approval date | Actual phase | Planned phase | Associated process on L1
Corporate IT body | Manage IT strategy | Total | L1 | MP | 7% |  |  |  | 2026-01-07 | 2026-06-30 | 125 |  |  | 1 | Manage IT strategy
Corporate IT body | Manage IT strategy | Elaboration | L1 | MP | 15% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  | Elaboration in progress | Scheduled | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT strategy
Corporate IT body | Manage IT governance framework | Total | L1 | MP | 0% |  |  |  | 2026-01-07 | 2026-06-30 | 125 |  |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Elaboration | L1 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  |  | Scheduled | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Total | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Elaboration | L2 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-01-07 | 2026-01-17 | 8 |  |  | Scheduled | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Manage enterprise architecture | Total | L1 | MP | 0% |  |  |  | 2026-01-07 | 2026-06-22 | 119 |  |  |  | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Elaboration | L1 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 2026-01-07 | 2026-03-16 | 49 |  |  | Scheduled | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-22 | 49 |  |  | Scheduled | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LUS | L1 | MP | 0% |  |  |  | 2026-04-30 | 2026-04-30 | 1 |  |  | Scheduled | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Total | L2 | MP | 0% |  |  |  | 2026-04-30 | 2026-04-30 | 1 |  |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Elaboration | L2 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) |  |  | 0 |  |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LIS | L2 | MP | 0% |  |  |  |  | 2026-04-30 | 32959 |  |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage enterprise architecture
ITSM | Manage IT portfolio | Total | L1 | MP | 0% |  |  |  | 2025-11-10 | 2026-05-15 | 135 |  |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Elaboration | L1 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Rantou Anna (LIS) |  | 2025-08-08 | 2026-01-31 | 126 |  | Delayed | Elaboration in progress | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LUS | L1 | MP | 0% |  |  |  | 2025-12-22 | 2026-01-03 | 10 |  |  | Scheduled | Manage IT portfolio
IT project management | Manage IT project portfolio | Total | L2 | MP | 0% |  |  |  | 2025-11-10 | 2025-12-23 | 32 |  |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Elaboration | L2 | MP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-10 | 2025-12-23 | 32 |  | Delayed | Elaboration in progress | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Total | L2 | MP | 0% |  |  |  | 2026-01-05 | 2026-06-30 | 127 |  |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Elaboration | L2 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Rantou Anna (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-05 | 2026-03-30 | 61 |  |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-06 | 2026-06-30 | 62 |  |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
IT planning and steering | Manage and control IT financials | Total | L1 | MP | 0% |  |  |  | 2025-10-15 | 2026-09-30 | 251 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Elaboration | L1 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Total | L2 | MP | 0% |  |  |  | 2026-01-07 | 2026-06-29 | 124 |  |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-23 | 54 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-06 | 2026-06-29 | 61 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Total | L2 | MP | 0% |  |  |  | 2025-10-15 | 2026-03-23 | 114 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2026-01-07 | 2026-03-23 | 54 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Total | L3 | MP | 0% | [9 empty] | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Total | L2 | MP | 0% |  |  |  | 2026-01-12 | 2026-06-22 | 116 |  |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2026-01-12 | 2026-03-31 | 57 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-07 | 2026-06-22 | 55 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation COT |  | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Total | L2 | MP | 0% |  |  |  | 2026-01-12 | 2026-09-30 | 188 |  |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2026-01-12 | 2026-03-31 | 57 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation COT | L2 | MP | 0% |  |  |  | 2026-02-02 | 2026-09-30 | 173 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Iplement cost allocation to stakeholders / companies | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Iplement cost allocation to stakeholders / companies | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Iplement cost allocation to stakeholders / companies | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Iplement cost allocation to stakeholders / companies | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Iplement cost allocation to stakeholders / companies | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
Corporate IT body | Manage IT stakeholder relationships | Total | L1 | MP | 0% |  |  |  | 2026-04-01 | 2026-12-23 | 191 |  |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Elaboration | L1 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 |  |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT stakeholder relationships
ITSM | Manage IT processes and continuous improvement | Total | L1 | MP | 0% |  |  |  | 2025-10-01 | 2026-06-30 | 195 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Elaboration | L1 | MP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip (LIS) | Rollinger Alexander (LIS) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Total | L2 | MP | 0% |  |  |  |  | 2025-10-16 | 32819 | Thu 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Total | L2 | MP | 0% |  |  |  | 2025-10-01 | 2026-01-30 | 88 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Elaboration | L2 | MP | 0% | Hoermann Patrick (LLI) | Hiller Moritz (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-01-30 | 88 |  | Delayed | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Total | L3 | MP | 0% |  |  |  |  | 2025-10-16 | 32819 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Hiller Moritz (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Total | L3 | MP | 0% |  |  |  |  | 2025-10-16 | 32819 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Hiller Moritz (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Total | L2 | MP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Elaboration | L2 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Total | L3 | MP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Total | L3 | MP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Total | L3 | MP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Total | L3 | MP | 0% | [5 empty] | 0 | Fri 19.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Total | L3 | MP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Total | L3 | MP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
Central area (Jan Müskens) | Manage IT risks and compliance | Total | L1 | MP | 0% |  |  |  | 2025-10-16 | 2026-05-31 | 162 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Elaboration | L1 | MP | 0% | Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-02-28 | 97 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation COT | L2 | MP | 0% |  |  |  | 2026-01-01 | 2026-02-28 | 42 |  |  | Scheduled | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2026-01-31 | 77 |  | Delayed | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-02-02 | 2026-04-30 | 64 |  |  | Scheduled | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-05-31 | 162 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2026-03-31 | 119 |  | Delayed | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation COT | L2 | MP | 0% |  |  |  | 2026-04-01 | 2026-05-31 | 43 |  |  | Scheduled | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-03-31 | 119 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2026-02-15 | 87 |  | Delayed | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation COT | L2 | MP | 0% |  |  |  | 2026-02-16 | 2026-03-31 | 32 |  |  | Scheduled | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 1 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Total | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Corporate IT body | Plan IT service | Total | L1 | CP | 0% |  |  |  | 2025-08-01 | 2026-04-30 | 195 |  |  |  | Plan IT service
Corporate IT body | Plan IT service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-10-16 | 2025-10-31 | 12 | Wed 10.12.25 | Delayed | Elaboration Done | Plan IT service
Corporate IT body | Plan IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Plan IT service | Implementation COT | L1 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 |  | Delayed | Implementation COT | Plan IT service
Corporate IT body | Plan IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Total | L2 | CP | 0% | [5 empty] | 0 | Tue 19.08.25 |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Total | L2 | CP | 0% |  |  |  | 2025-08-01 | 2026-04-30 | 195 | Wed 10.12.25 |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Total | L3 | CP | 0% |  |  |  | 2025-08-01 | 2026-04-30 | 195 |  |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Elaboration | L3 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-10-15 | 54 |  | Delayed | Elaboration Done | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation COT | L3 | CP | 0% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  | Delayed | Implementation COT | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Total | L2 | CP | 0% | [5 empty] | 0 | Tue 19.08.25 |  |  | Plan IT service
Corporate IT body | Approve IT demand | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
ITSM | Build IT Service | Total | L1 | CP | 0% |  |  |  | 2025-04-01 | 2026-08-31 | 370 |  |  |  | Build IT Service
ITSM | Build IT Service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) |  |  | 0 |  |  |  | Build IT Service
ITSM | Build IT Service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Build IT Service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Build IT Service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Design IT service | Total | L2 | CP | 0% |  |  |  | 2025-10-01 | 2026-08-14 | 228 |  |  |  | Build IT Service
ITSM | Design IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) | 2026-02-16 | 2026-05-15 | 65 |  |  | Scheduled | Build IT Service
ITSM | Design IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-05-18 | 2026-08-14 | 65 |  |  | Scheduled | Build IT Service
ITSM | Design IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Design IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Define solution target architecture | Total | L3 | CP | 0% |  |  |  | 2026-01-14 | 2026-06-30 | 120 |  |  |  | Build IT Service
Architecture management | Define solution target architecture | Elaboration | L3 | CP | 0% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) | 2026-01-15 | 2026-03-31 | 54 |  |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation LIS | L3 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation COT | L3 | CP | 0% |  |  |  |  | 2026-06-30 | 33002 |  |  |  | Build IT Service
Architecture management | Define solution target architecture | Implementation LUS | L3 | CP | 0% |  |  |  | 2026-01-14 | 2026-01-14 | 1 |  |  | Scheduled | Build IT Service
Architecture management | Perform software selection | Total | L3 | CP | 0% |  |  |  | 2025-10-01 | 2026-04-30 | 152 | Tue 14.10.25 |  |  | Build IT Service
Architecture management | Perform software selection | Elaboration | L3 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 60 |  | Delayed | Elaboration in progress | Build IT Service
Architecture management | Perform software selection | Implementation LIS | L3 | CP | 0% |  |  |  | 2026-02-16 | 2026-04-30 | 54 |  |  | Scheduled | Build IT Service
Architecture management | Perform software selection | Implementation COT | L3 | CP | 0% |  |  |  | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Implementation COT | Build IT Service
Architecture management | Perform software selection | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Total | L4 | CP | 0% | [5 empty] | 0 | Tue 14.10.25 |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Total | L4 | CP | 0% | [5 empty] | 0 | Tue 14.10.25 |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Total | L4 | CP | 0% | [5 empty] | 0 | Tue 14.10.25 |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Total | L4 | CP | 0% | [5 empty] | 0 | Tue 14.10.25 |  |  | Build IT Service
Architecture management | Validate strategic fit | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Total | L4 | CP | 0% | [5 empty] | 0 | Tue 14.10.25 |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Develop and customise IT service | Total | L2 | CP | 0% |  |  |  | 2025-05-26 | 2026-05-15 | 255 |  |  |  | Build IT Service
ITSM | Develop and customise IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) |  | 2026-02-16 | 2026-05-15 | 65 |  |  | Scheduled | Build IT Service
ITSM | Develop and customise IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-05-26 | 2025-08-15 | 60 |  | Delayed | Implementation LIS Done | Build IT Service
ITSM | Develop and customise IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Develop and customise IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Deploy IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 |  |  |  | Build IT Service
ITSM | Deploy IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 |  |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Deploy IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
| Test and validate IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 |  |  |  | Build IT Service
ITSM | Test and validate IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 |  |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Test and validate IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Total | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) |  |  | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manage IT service change | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-30 | 122 |  |  |  | Build IT Service
ITSM | Manag IT service change | Elaboration | L2 | CP | 0% | Frank Maren (LIS); Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Sint Rachel (LBH) | Koiner Alexander (LWN) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Build IT Service
ITSM | Manag IT service change | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Build IT Service
ITSM | Manag IT service change | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manag IT service change | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manage IT service release | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-30 | 122 |  |  |  | Build IT Service
ITSM | Manage IT service release | Elaboration | L2 | CP | 0% | Frank Maren (LIS); Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Sint Rachel (LBH) | Koiner Alexander (LWN) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Build IT Service
ITSM | Manage IT service release | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Build IT Service
ITSM | Manage IT service release | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manage IT service release | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Deliver IT service | Total | L1 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-15 | 111 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Elaboration | L1 | CP | 0% | Hoermann Patrick (LLI) | Mechegia Eloise (LIS) | Bergmann Aniko (LIS-LIN) |  |  | 0 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Manage IT service provision request | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-15 | 111 |  |  |  | Deliver IT service
ITSM | Manage IT service provision request | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Mechegia Eloise (LIS) | Bergmann Aniko (LIS-LIN) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Deliver IT service
ITSM | Manage IT service provision request | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Deliver IT service
ITSM | Manage IT service provision request | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Manage IT service provision request | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Handle IT service order | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-15 | 111 |  |  |  | Deliver IT service
ITSM | Handle IT service order | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Mechegia Eloise (LIS) | Bergmann Aniko (LIS-LIN) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Deliver IT service
ITSM | Handle IT service order | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Deliver IT service
ITSM | Handle IT service order | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Handle IT service order | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Run IT service | Total | L1 | CP | 0% |  |  |  | 2025-10-15 | 2026-06-30 | 185 |  |  |  | Run IT service
ITSM | Run IT service | Elaboration | L1 | CP | 0% | Schroeder Michael (LIS) |  |  |  |  | 0 |  |  |  | Run IT service
ITSM | Run IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Run IT service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Run IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Ensure IT service continuity | Total | L2 | CP | 0% |  |  |  | 2025-10-15 | 2026-06-30 | 185 |  |  |  | Run IT service
ITSM | Ensure IT service continuity | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Held Matthias | Sint Rachel (LBH) | 2026-01-15 | 2026-03-16 | 43 |  |  | Scheduled | Run IT service
ITSM | Ensure IT service continuity | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Run IT service
ITSM | Ensure IT service continuity | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Total | L2 | CP | 0% |  |  |  | 2025-10-15 | 2026-03-30 | 119 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kueschner Phillip (LIS) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Run IT service
ITSM | Montior and report IT service performance | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Operate and maintain IT service | Total | L2 | CP | 0% |  |  |  | 2025-10-15 | 2026-06-30 | 185 |  |  |  | Run IT service
ITSM | Operate and maintain IT service | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Run IT service
ITSM | Operate and maintain IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Run IT service
ITSM | Operate and maintain IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Operate and maintain IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Provide IT service support | Total | L2 | CP | 0% |  |  |  | 2025-10-15 | 2026-06-15 | 174 |  |  |  | Run IT service
ITSM | Provide IT service support | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Rantou Anna (LIS) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  |  | Scheduled | Run IT service
ITSM | Provide IT service support | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Run IT service
ITSM | Provide IT service support | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Provide IT service support | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
Information security | Ensure Information security | Total | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Total | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Elaboration | L2 | SP | 0% | Hoermann Patrick (LLI) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
IT project management | Manage IT project | Total | L1 | SP | 0% |  |  |  | 2025-07-14 | 2026-06-29 | 251 | Thu 18.09.25 |  |  | Manage IT project
IT project management | Manage IT project | Elaboration | L1 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-09-30 | 57 |  | Delayed | Elaboration Done | Manage IT project
IT project management | Manage IT project | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-29 | 64 |  |  | Scheduled | Manage IT project
IT project management | Manage IT project | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Initiate IT project | Total | L2 | SP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT project
IT project management | Initiate IT project | Elaboration | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Manage IT project
IT project management | Initiate IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Initiate IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Initiate IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Plan IT project | Total | L2 | SP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT project
IT project management | Plan IT project | Elaboration | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Manage IT project
IT project management | Plan IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Plan IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Plan IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Steer & execute IT project | Total | L2 | SP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT project
IT project management | Steer & execute IT project | Elaboration | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Manage IT project
IT project management | Steer & execute IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Steer & execute IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Steer & execute IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Close IT project | Total | L2 | SP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT project
IT project management | Close IT project | Elaboration | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Manage IT project
IT project management | Close IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Close IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Close IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project change request | Total | L2 | SP | 0% | [5 empty] | 0 | Thu 18.09.25 |  |  | Manage IT project
IT project management | Manage IT project change request | Elaboration | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Assign personnel resources to IT project | Total | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Elaboration | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
ITSM | Manage IT sourcing and procurement | Total | L1 | SP | 0% |  |  |  | 2026-04-20 | 2026-09-30 | 118 |  |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Elaboration | L1 | SP | 0% | Moser Mario (LIS-LAH);Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Monnier Murielle (LEC) | 2026-04-20 | 2026-06-30 | 52 |  |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-13 | 2026-09-30 | 58 |  |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT sourcing and procurement
HR initiatives for IT | Provide and develop IT workforce | Total | L1 | SP | 0% |  |  |  | 2025-10-16 | 2027-06-15 | 434 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Elaboration | L1 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Total | L2 | SP | 0% |  |  |  | 2025-10-16 | 2026-12-31 | 316 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation COT | L2 | SP | 0% |  |  |  | 2026-01-01 | 2026-12-31 | 261 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Total | L2 | SP | 0% |  |  |  | 2026-01-07 | 2026-06-15 | 114 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kiesewetter Ivana (LIS) | Rollinger Alexander (LIS) | 2026-01-07 | 2026-03-16 | 49 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Total | L2 | SP | 0% |  |  |  | 2026-01-07 | 2026-06-15 | 114 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kiesewetter Ivana (LIS) | Rollinger Alexander (LIS) | 2026-01-07 | 2026-03-16 | 49 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Total | L2 | SP | 0% |  |  |  | 2025-10-16 | 2026-02-02 | 78 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kramer Annika (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2025-11-30 | 32 |  | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Implementation COT | L2 | SP | 0% |  |  |  | 2025-12-01 | 2026-02-02 | 46 |  | Delayed | Implementation COT | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Total | L2 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kramer Annika (LIS) | Mielenz Thomas (LMT) | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Implementation COT | L2 | SP | 0% |  |  |  | 2026-07-01 | 2026-09-30 | 66 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Total | L2 | SP | 0% |  |  |  | 2025-10-16 | 2026-12-31 | 316 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2026-04-30 | 141 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation COT | L2 | SP | 0% |  |  |  | 2026-05-04 | 2026-12-31 | 174 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Total | L2 | SP | 0% |  |  |  | 2026-01-01 | 2026-11-30 | 238 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Implementation COT | L2 | SP | 0% |  |  |  | 2026-01-01 | 2026-11-30 | 238 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Total | L2 | SP | 0% |  |  |  | 2026-01-15 | 2026-12-23 | 245 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-05-04 | 78 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Implementation COT | L2 | SP | 0% |  |  |  | 2026-02-02 | 2026-11-30 | 216 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Total | L2 | SP | 0% |  |  |  | 2026-04-01 | 2027-06-15 | 315 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2027-06-15 | 315 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation COT | L2 | SP | 0% |  |  |  | 2026-05-04 | 2026-12-31 | 174 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Total | L2 | SP | 0% |  |  |  | 2026-01-15 | 2026-03-31 | 54 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-03-31 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Total | L2 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kramer Annika (LIS) | Mielenz Thomas (LMT) | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Implementation COT | L2 | SP | 0% |  |  |  | 2026-05-18 | 2026-09-30 | 98 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
ITSM | Ensure performance and conformance of IT services | Total | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Elaboration | L1 | SP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure performance and conformance of IT services
ITSM | Manage IT knowledge | Total | L1 | SP | 0% |  |  |  | 2026-01-15 | 2026-06-30 | 119 |  |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Elaboration | L1 | SP | 0% | Schroeder Michael (LIS) | Rantou Anna (LIS) | Sint Rachel (LBH) | 2026-01-15 | 2026-03-31 | 54 |  |  | Scheduled | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT knowledge
ITSM | Leverage IT innovtion | Total | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Leverage IT innovtion
ITSM | Leverage IT innovtion | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS) | Frick Markus (LIS) | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Leverage IT innovtion
ITSM | Leverage IT innovtion | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Leverage IT innovtion
ITSM | Leverage IT innovtion | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Leverage IT innovtion
ITSM | Leverage IT innovtion | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Leverage IT innovtion
Formulas:
Duration = NETWORKDAYS([Start],[End])

## Tabelle1 (hidden)
Datum | Elaboration | Implementation LIS | Implementation LUS | Implementation COT
2025-08-01 | 1 | 2 | 0 | 1
2025-08-02 | 2 | 2 | 0 | 1
2025-08-03 | 2 | 2 | 0 | 1
2025-08-04 | 2 | 2 | 0 | 1
2025-08-05 | 2 | 2 | 0 | 1
2025-08-06 | 2 | 2 | 0 | 1
2025-08-07 | 2 | 2 | 0 | 1
2025-08-08 | 2 | 2 | 0 | 1
2025-08-09 | 3 | 2 | 0 | 1
2025-08-10 | 3 | 2 | 0 | 1
2025-08-11 | 3 | 2 | 0 | 1
2025-08-12 | 3 | 2 | 0 | 1
2025-08-13 | 3 | 2 | 0 | 1
2025-08-14 | 3 | 2 | 0 | 1
2025-08-15 | 3 | 1 | 0 | 1
2025-08-16 | 3 | 1 | 0 | 1
2025-08-17 | 3 | 1 | 0 | 1
2025-08-18 | 3 | 1 | 0 | 1
2025-08-19 | 3 | 1 | 0 | 1
2025-08-20 | 3 | 1 | 0 | 1
2025-08-21 | 3 | 1 | 0 | 1
2025-08-22 | 3 | 1 | 0 | 1
2025-08-23 | 3 | 1 | 0 | 1
2025-08-24 | 3 | 1 | 0 | 1
2025-08-25 | 3 | 1 | 0 | 1
2025-08-26 | 3 | 1 | 0 | 1
2025-08-27 | 3 | 1 | 0 | 1
2025-08-28 | 3 | 1 | 0 | 1
2025-08-29 | 3 | 1 | 0 | 1
2025-08-30 | 3 | 1 | 0 | 1
2025-08-31 | 3 | 1 | 0 | 1
2025-09-01 | 3 | 1 | 0 | 1
2025-09-02 | 3 | 1 | 0 | 1
2025-09-03 | 3 | 1 | 0 | 1
2025-09-04 | 3 | 1 | 0 | 1
2025-09-05 | 3 | 1 | 0 | 1
2025-09-06 | 3 | 1 | 0 | 1
2025-09-07 | 3 | 1 | 0 | 1
2025-09-08 | 3 | 1 | 0 | 1
2025-09-09 | 3 | 1 | 0 | 1
2025-09-10 | 3 | 1 | 0 | 1
2025-09-11 | 3 | 1 | 0 | 1
2025-09-12 | 3 | 1 | 0 | 1
2025-09-13 | 3 | 1 | 0 | 1
2025-09-14 | 3 | 1 | 0 | 1
2025-09-15 | 3 | 1 | 0 | 1
2025-09-16 | 3 | 1 | 0 | 1
2025-09-17 | 3 | 1 | 0 | 1
2025-09-18 | 3 | 1 | 0 | 1
2025-09-19 | 3 | 1 | 0 | 1
2025-09-20 | 3 | 1 | 0 | 1
2025-09-21 | 3 | 1 | 0 | 1
2025-09-22 | 3 | 1 | 0 | 1
2025-09-23 | 3 | 1 | 0 | 1
2025-09-24 | 3 | 1 | 0 | 1
2025-09-25 | 3 | 1 | 0 | 1
2025-09-26 | 3 | 1 | 0 | 1
2025-09-27 | 3 | 1 | 0 | 1
2025-09-28 | 3 | 1 | 0 | 1
2025-09-29 | 3 | 1 | 0 | 1
2025-09-30 | 2 | 1 | 0 | 1
2025-10-01 | 2 | 1 | 0 | 1
2025-10-02 | 4 | 1 | 0 | 1
2025-10-03 | 4 | 1 | 0 | 1
2025-10-04 | 4 | 1 | 0 | 1
2025-10-05 | 4 | 1 | 0 | 1
2025-10-06 | 4 | 1 | 0 | 1
2025-10-07 | 4 | 1 | 0 | 1
2025-10-08 | 4 | 1 | 0 | 1
2025-10-09 | 4 | 1 | 0 | 1
2025-10-10 | 4 | 1 | 0 | 1
2025-10-11 | 4 | 1 | 0 | 1
2025-10-12 | 4 | 1 | 0 | 1
2025-10-13 | 4 | 1 | 0 | 1
2025-10-14 | 4 | 1 | 0 | 1
2025-10-15 | 3 | 1 | 0 | 1
2025-10-16 | 3 | 1 | 0 | 1
2025-10-17 | 11 | 1 | 0 | 3
2025-10-18 | 11 | 1 | 0 | 3
2025-10-19 | 11 | 1 | 0 | 3
2025-10-20 | 11 | 1 | 0 | 3
2025-10-21 | 11 | 1 | 0 | 3
2025-10-22 | 11 | 1 | 0 | 3
2025-10-23 | 11 | 1 | 0 | 3
2025-10-24 | 11 | 1 | 0 | 3
2025-10-25 | 11 | 1 | 0 | 3
2025-10-26 | 11 | 1 | 0 | 3
2025-10-27 | 11 | 1 | 0 | 3
2025-10-28 | 11 | 1 | 0 | 3
2025-10-29 | 11 | 1 | 0 | 3
2025-10-30 | 11 | 1 | 0 | 3
2025-10-31 | 10 | 1 | 0 | 3
2025-11-01 | 10 | 1 | 0 | 3
2025-11-02 | 10 | 1 | 0 | 3
2025-11-03 | 10 | 1 | 0 | 3
2025-11-04 | 10 | 1 | 0 | 4
2025-11-05 | 10 | 1 | 0 | 4
2025-11-06 | 10 | 1 | 0 | 4
2025-11-07 | 10 | 1 | 0 | 4
2025-11-08 | 10 | 1 | 0 | 4
2025-11-09 | 10 | 1 | 0 | 4
2025-11-10 | 10 | 1 | 0 | 4
2025-11-11 | 11 | 1 | 0 | 4
2025-11-12 | 11 | 1 | 0 | 4
2025-11-13 | 11 | 1 | 0 | 4
2025-11-14 | 11 | 1 | 0 | 4
2025-11-15 | 11 | 1 | 0 | 4
2025-11-16 | 11 | 1 | 0 | 4
2025-11-17 | 11 | 1 | 0 | 4
2025-11-18 | 11 | 1 | 0 | 4
2025-11-19 | 11 | 1 | 0 | 4
2025-11-20 | 11 | 1 | 0 | 4
2025-11-21 | 11 | 1 | 0 | 4
2025-11-22 | 11 | 1 | 0 | 4
2025-11-23 | 11 | 1 | 0 | 4
2025-11-24 | 11 | 1 | 0 | 4
2025-11-25 | 11 | 1 | 0 | 4
2025-11-26 | 11 | 1 | 0 | 4
2025-11-27 | 11 | 1 | 0 | 4
2025-11-28 | 11 | 1 | 0 | 4
2025-11-29 | 11 | 1 | 0 | 4
2025-11-30 | 10 | 1 | 0 | 4
2025-12-01 | 10 | 1 | 0 | 4
2025-12-02 | 10 | 1 | 0 | 5
2025-12-03 | 10 | 1 | 0 | 5
2025-12-04 | 10 | 1 | 0 | 5
2025-12-05 | 10 | 1 | 0 | 5
2025-12-06 | 10 | 1 | 0 | 5
2025-12-07 | 10 | 1 | 0 | 5
2025-12-08 | 10 | 1 | 0 | 5
2025-12-09 | 10 | 1 | 0 | 5
2025-12-10 | 10 | 1 | 0 | 5
2025-12-11 | 10 | 1 | 0 | 5
2025-12-12 | 10 | 1 | 0 | 5
2025-12-13 | 10 | 1 | 0 | 5
2025-12-14 | 10 | 1 | 0 | 5
2025-12-15 | 10 | 1 | 0 | 5
2025-12-16 | 10 | 1 | 0 | 5
2025-12-17 | 10 | 1 | 0 | 5
2025-12-18 | 10 | 1 | 0 | 5
2025-12-19 | 10 | 1 | 0 | 5
2025-12-20 | 10 | 1 | 0 | 5
2025-12-21 | 10 | 1 | 0 | 5
2025-12-22 | 10 | 1 | 0 | 5
2025-12-23 | 8 | 1 | 1 | 5
2025-12-24 | 8 | 1 | 1 | 5
2025-12-25 | 8 | 1 | 1 | 5
2025-12-26 | 8 | 1 | 1 | 5
2025-12-27 | 8 | 1 | 1 | 5
2025-12-28 | 8 | 1 | 1 | 5
2025-12-29 | 8 | 1 | 1 | 5
2025-12-30 | 8 | 1 | 1 | 5
2025-12-31 | 6 | 1 | 1 | 4
2026-01-01 | 6 | 1 | 1 | 4
2026-01-02 | 6 | 1 | 1 | 7
2026-01-03 | 6 | 1 | 0 | 7
2026-01-04 | 6 | 1 | 0 | 7
2026-01-05 | 6 | 1 | 0 | 7
2026-01-06 | 7 | 1 | 0 | 7
2026-01-07 | 7 | 1 | 0 | 7
2026-01-08 | 15 | 2 | 0 | 7
2026-01-09 | 15 | 2 | 0 | 7
2026-01-10 | 15 | 2 | 0 | 7
2026-01-11 | 15 | 2 | 0 | 7
2026-01-12 | 15 | 2 | 0 | 7
2026-01-13 | 25 | 2 | 0 | 7
2026-01-14 | 25 | 2 | 0 | 7
2026-01-15 | 25 | 2 | 0 | 7
2026-01-16 | 30 | 2 | 0 | 7
2026-01-17 | 30 | 1 | 0 | 7
2026-01-18 | 30 | 1 | 0 | 7
2026-01-19 | 30 | 1 | 0 | 7
2026-01-20 | 30 | 1 | 0 | 7
2026-01-21 | 30 | 1 | 0 | 7
2026-01-22 | 30 | 1 | 0 | 7
2026-01-23 | 30 | 1 | 0 | 7
2026-01-24 | 30 | 1 | 0 | 7
2026-01-25 | 30 | 1 | 0 | 7
2026-01-26 | 30 | 1 | 0 | 7
2026-01-27 | 30 | 1 | 0 | 7
2026-01-28 | 30 | 1 | 0 | 7
2026-01-29 | 30 | 1 | 0 | 7
2026-01-30 | 29 | 1 | 0 | 7
2026-01-31 | 27 | 1 | 0 | 7
2026-02-01 | 27 | 1 | 0 | 7
2026-02-02 | 27 | 1 | 0 | 6
2026-02-03 | 27 | 2 | 0 | 8
2026-02-04 | 27 | 2 | 0 | 8
2026-02-05 | 27 | 2 | 0 | 8
2026-02-06 | 27 | 2 | 0 | 8
2026-02-07 | 27 | 2 | 0 | 8
2026-02-08 | 27 | 2 | 0 | 8
2026-02-09 | 27 | 2 | 0 | 8
2026-02-10 | 27 | 2 | 0 | 8
2026-02-11 | 27 | 2 | 0 | 8
2026-02-12 | 27 | 2 | 0 | 8
2026-02-13 | 27 | 2 | 0 | 8
2026-02-14 | 27 | 2 | 0 | 8
2026-02-15 | 26 | 2 | 0 | 8
2026-02-16 | 26 | 2 | 0 | 8
2026-02-17 | 28 | 3 | 0 | 9
2026-02-18 | 28 | 3 | 0 | 9
2026-02-19 | 28 | 3 | 0 | 9
2026-02-20 | 28 | 3 | 0 | 9
2026-02-21 | 28 | 3 | 0 | 9
2026-02-22 | 28 | 3 | 0 | 9
2026-02-23 | 28 | 3 | 0 | 9
2026-02-24 | 28 | 3 | 0 | 9
2026-02-25 | 28 | 3 | 0 | 9
2026-02-26 | 28 | 3 | 0 | 9
2026-02-27 | 28 | 3 | 0 | 9
2026-02-28 | 28 | 3 | 0 | 8
2026-03-01 | 28 | 3 | 0 | 8
2026-03-02 | 28 | 3 | 0 | 8
2026-03-03 | 28 | 3 | 0 | 8
2026-03-04 | 28 | 3 | 0 | 8
2026-03-05 | 28 | 3 | 0 | 8
2026-03-06 | 28 | 3 | 0 | 8
2026-03-07 | 28 | 3 | 0 | 8
2026-03-08 | 28 | 3 | 0 | 8
2026-03-09 | 28 | 3 | 0 | 8
2026-03-10 | 28 | 3 | 0 | 8
2026-03-11 | 28 | 3 | 0 | 8
2026-03-12 | 28 | 3 | 0 | 8
2026-03-13 | 28 | 3 | 0 | 8
2026-03-14 | 28 | 3 | 0 | 8
2026-03-15 | 28 | 3 | 0 | 8
2026-03-16 | 21 | 3 | 0 | 8
2026-03-17 | 21 | 3 | 0 | 8
2026-03-18 | 21 | 3 | 0 | 8
2026-03-19 | 21 | 3 | 0 | 8
2026-03-20 | 21 | 3 | 0 | 8
2026-03-21 | 21 | 3 | 0 | 8
2026-03-22 | 21 | 3 | 0 | 8
2026-03-23 | 19 | 3 | 0 | 8
2026-03-24 | 19 | 3 | 0 | 8
2026-03-25 | 19 | 3 | 0 | 8
2026-03-26 | 19 | 3 | 0 | 8
2026-03-27 | 19 | 3 | 0 | 8
2026-03-28 | 19 | 3 | 0 | 8
2026-03-29 | 19 | 3 | 0 | 8
2026-03-30 | 10 | 3 | 0 | 8
2026-03-31 | 4 | 3 | 0 | 6
2026-04-01 | 4 | 3 | 0 | 6
2026-04-02 | 6 | 10 | 0 | 10
2026-04-03 | 6 | 10 | 0 | 10
2026-04-04 | 6 | 10 | 0 | 10
2026-04-05 | 6 | 10 | 0 | 10
2026-04-06 | 6 | 10 | 0 | 10
2026-04-07 | 6 | 12 | 0 | 10
2026-04-08 | 6 | 13 | 0 | 10
2026-04-09 | 6 | 13 | 0 | 10
2026-04-10 | 6 | 13 | 0 | 10
2026-04-11 | 6 | 13 | 0 | 10
2026-04-12 | 6 | 13 | 0 | 10
2026-04-13 | 6 | 13 | 0 | 10
2026-04-14 | 6 | 13 | 0 | 10
2026-04-15 | 6 | 13 | 0 | 10
2026-04-16 | 12 | 24 | 0 | 10
2026-04-17 | 12 | 24 | 0 | 10
2026-04-18 | 12 | 24 | 0 | 10
2026-04-19 | 12 | 24 | 0 | 10
2026-04-20 | 12 | 24 | 0 | 10
2026-04-21 | 13 | 24 | 0 | 10
2026-04-22 | 13 | 24 | 0 | 10
2026-04-23 | 13 | 24 | 0 | 10
2026-04-24 | 13 | 24 | 0 | 10
2026-04-25 | 13 | 24 | 0 | 10
2026-04-26 | 13 | 24 | 0 | 10
2026-04-27 | 13 | 24 | 0 | 10
2026-04-28 | 13 | 24 | 0 | 10
2026-04-29 | 13 | 24 | 0 | 10
2026-04-30 | 12 | 21 | 0 | 9
2026-05-01 | 12 | 21 | 0 | 9
2026-05-02 | 12 | 21 | 0 | 9
2026-05-03 | 12 | 21 | 0 | 9
2026-05-04 | 11 | 21 | 0 | 9
2026-05-05 | 11 | 21 | 0 | 11
2026-05-06 | 11 | 21 | 0 | 11
2026-05-07 | 11 | 21 | 0 | 11
2026-05-08 | 11 | 21 | 0 | 11
2026-05-09 | 11 | 21 | 0 | 11
2026-05-10 | 11 | 21 | 0 | 11
2026-05-11 | 11 | 21 | 0 | 11
2026-05-12 | 11 | 21 | 0 | 11
2026-05-13 | 11 | 21 | 0 | 11
2026-05-14 | 11 | 21 | 0 | 11
2026-05-15 | 9 | 21 | 0 | 11
2026-05-16 | 9 | 21 | 0 | 11
2026-05-17 | 9 | 21 | 0 | 11
2026-05-18 | 9 | 21 | 0 | 11
2026-05-19 | 9 | 22 | 0 | 12
2026-05-20 | 9 | 22 | 0 | 12
2026-05-21 | 9 | 22 | 0 | 12
2026-05-22 | 9 | 22 | 0 | 12
2026-05-23 | 9 | 22 | 0 | 12
2026-05-24 | 9 | 22 | 0 | 12
2026-05-25 | 9 | 22 | 0 | 12
2026-05-26 | 9 | 22 | 0 | 12
2026-05-27 | 9 | 22 | 0 | 12
2026-05-28 | 9 | 22 | 0 | 12
2026-05-29 | 9 | 22 | 0 | 12
2026-05-30 | 9 | 22 | 0 | 12
2026-05-31 | 9 | 22 | 0 | 11
2026-06-01 | 9 | 22 | 0 | 11
2026-06-02 | 9 | 22 | 0 | 11
2026-06-03 | 9 | 22 | 0 | 11
2026-06-04 | 9 | 22 | 0 | 11
2026-06-05 | 9 | 22 | 0 | 11
2026-06-06 | 9 | 22 | 0 | 11
2026-06-07 | 9 | 22 | 0 | 11
2026-06-08 | 9 | 22 | 0 | 11
2026-06-09 | 9 | 22 | 0 | 11
2026-06-10 | 9 | 22 | 0 | 11
2026-06-11 | 9 | 22 | 0 | 11
2026-06-12 | 9 | 22 | 0 | 11
2026-06-13 | 9 | 22 | 0 | 11
2026-06-14 | 9 | 22 | 0 | 11
2026-06-15 | 5 | 14 | 0 | 9
2026-06-16 | 5 | 14 | 0 | 9
2026-06-17 | 5 | 14 | 0 | 9
2026-06-18 | 5 | 14 | 0 | 9
2026-06-19 | 5 | 14 | 0 | 9
2026-06-20 | 5 | 14 | 0 | 9
2026-06-21 | 5 | 14 | 0 | 9
2026-06-22 | 5 | 12 | 0 | 9
2026-06-23 | 5 | 12 | 0 | 9
2026-06-24 | 5 | 12 | 0 | 9
2026-06-25 | 5 | 12 | 0 | 9
2026-06-26 | 5 | 12 | 0 | 9
2026-06-27 | 5 | 12 | 0 | 9
2026-06-28 | 5 | 12 | 0 | 9
2026-06-29 | 5 | 10 | 0 | 9
2026-06-30 | 1 | 1 | 0 | 8
2026-07-01 | 1 | 1 | 0 | 7
2026-07-02 | 1 | 1 | 0 | 8
2026-07-03 | 1 | 1 | 0 | 8
2026-07-04 | 1 | 1 | 0 | 8
2026-07-05 | 1 | 1 | 0 | 8
2026-07-06 | 1 | 1 | 0 | 8
2026-07-07 | 1 | 1 | 0 | 8
2026-07-08 | 1 | 1 | 0 | 8
2026-07-09 | 1 | 1 | 0 | 8
2026-07-10 | 1 | 1 | 0 | 8
2026-07-11 | 1 | 1 | 0 | 8
2026-07-12 | 1 | 1 | 0 | 8
2026-07-13 | 1 | 1 | 0 | 8
2026-07-14 | 1 | 2 | 0 | 8
2026-07-15 | 1 | 2 | 0 | 8
2026-07-16 | 1 | 8 | 0 | 8
2026-07-17 | 1 | 8 | 0 | 8
2026-07-18 | 1 | 8 | 0 | 8
2026-07-19 | 1 | 8 | 0 | 8
2026-07-20 | 1 | 8 | 0 | 8
2026-07-21 | 1 | 8 | 0 | 8
2026-07-22 | 1 | 8 | 0 | 8
2026-07-23 | 1 | 8 | 0 | 8
2026-07-24 | 1 | 8 | 0 | 8
2026-07-25 | 1 | 8 | 0 | 8
2026-07-26 | 1 | 8 | 0 | 8
2026-07-27 | 1 | 8 | 0 | 8
2026-07-28 | 1 | 8 | 0 | 8
2026-07-29 | 1 | 8 | 0 | 8
2026-07-30 | 1 | 8 | 0 | 8
2026-07-31 | 1 | 8 | 0 | 8
2026-08-01 | 1 | 8 | 0 | 8
2026-08-02 | 1 | 8 | 0 | 8
2026-08-03 | 1 | 8 | 0 | 8
2026-08-04 | 1 | 8 | 0 | 8
2026-08-05 | 1 | 8 | 0 | 8
2026-08-06 | 1 | 8 | 0 | 8
2026-08-07 | 1 | 8 | 0 | 8
2026-08-08 | 1 | 8 | 0 | 8
2026-08-09 | 1 | 8 | 0 | 8
2026-08-10 | 1 | 8 | 0 | 8
2026-08-11 | 1 | 8 | 0 | 8
2026-08-12 | 1 | 8 | 0 | 8
2026-08-13 | 1 | 8 | 0 | 8
2026-08-14 | 1 | 7 | 0 | 8
2026-08-15 | 1 | 7 | 0 | 8
2026-08-16 | 1 | 7 | 0 | 8
2026-08-17 | 1 | 7 | 0 | 8
2026-08-18 | 1 | 7 | 0 | 8
2026-08-19 | 1 | 7 | 0 | 8
2026-08-20 | 1 | 7 | 0 | 8
2026-08-21 | 1 | 7 | 0 | 8
2026-08-22 | 1 | 7 | 0 | 8
2026-08-23 | 1 | 7 | 0 | 8
2026-08-24 | 1 | 7 | 0 | 8
2026-08-25 | 1 | 7 | 0 | 8
2026-08-26 | 1 | 7 | 0 | 8
2026-08-27 | 1 | 7 | 0 | 8
2026-08-28 | 1 | 7 | 0 | 8
2026-08-29 | 1 | 7 | 0 | 8
2026-08-30 | 1 | 7 | 0 | 8
2026-08-31 | 1 | 5 | 0 | 8
2026-09-01 | 1 | 5 | 0 | 8
2026-09-02 | 1 | 5 | 0 | 8
2026-09-03 | 1 | 5 | 0 | 8
2026-09-04 | 1 | 5 | 0 | 8
2026-09-05 | 1 | 5 | 0 | 8
2026-09-06 | 1 | 5 | 0 | 8
2026-09-07 | 1 | 5 | 0 | 8
2026-09-08 | 1 | 5 | 0 | 8
2026-09-09 | 1 | 5 | 0 | 8
2026-09-10 | 1 | 5 | 0 | 8
2026-09-11 | 1 | 5 | 0 | 8
2026-09-12 | 1 | 5 | 0 | 8
2026-09-13 | 1 | 5 | 0 | 8
2026-09-14 | 1 | 5 | 0 | 8
2026-09-15 | 1 | 5 | 0 | 8
2026-09-16 | 1 | 5 | 0 | 8
2026-09-17 | 1 | 5 | 0 | 8
2026-09-18 | 1 | 5 | 0 | 8
2026-09-19 | 1 | 5 | 0 | 8
2026-09-20 | 1 | 5 | 0 | 8
2026-09-21 | 1 | 5 | 0 | 8
2026-09-22 | 1 | 5 | 0 | 8
2026-09-23 | 1 | 5 | 0 | 8
2026-09-24 | 1 | 5 | 0 | 8
2026-09-25 | 1 | 5 | 0 | 8
2026-09-26 | 1 | 5 | 0 | 8
2026-09-27 | 1 | 5 | 0 | 8
2026-09-28 | 1 | 5 | 0 | 8
2026-09-29 | 1 | 5 | 0 | 8
2026-09-30 | 1 | 0 | 0 | 5
2026-10-01 | 1 | 0 | 0 | 5
2026-10-02 | 1 | 0 | 0 | 5
2026-10-03 | 1 | 0 | 0 | 5
2026-10-04 | 1 | 0 | 0 | 5
2026-10-05 | 1 | 0 | 0 | 5
2026-10-06 | 1 | 0 | 0 | 5
2026-10-07 | 1 | 0 | 0 | 5
2026-10-08 | 1 | 0 | 0 | 5
2026-10-09 | 1 | 0 | 0 | 5
2026-10-10 | 1 | 0 | 0 | 5
2026-10-11 | 1 | 0 | 0 | 5
2026-10-12 | 1 | 0 | 0 | 5
2026-10-13 | 1 | 0 | 0 | 5
2026-10-14 | 1 | 0 | 0 | 5
2026-10-15 | 1 | 0 | 0 | 5
2026-10-16 | 1 | 3 | 0 | 5
2026-10-17 | 1 | 3 | 0 | 5
2026-10-18 | 1 | 3 | 0 | 5
2026-10-19 | 1 | 3 | 0 | 5
2026-10-20 | 1 | 3 | 0 | 5
2026-10-21 | 1 | 3 | 0 | 5
2026-10-22 | 1 | 3 | 0 | 5
2026-10-23 | 1 | 3 | 0 | 5
2026-10-24 | 1 | 3 | 0 | 5
2026-10-25 | 1 | 3 | 0 | 5
2026-10-26 | 1 | 3 | 0 | 5
2026-10-27 | 1 | 3 | 0 | 5
2026-10-28 | 1 | 3 | 0 | 5
2026-10-29 | 1 | 3 | 0 | 5
2026-10-30 | 1 | 3 | 0 | 5
2026-10-31 | 1 | 3 | 0 | 5
2026-11-01 | 1 | 3 | 0 | 5
2026-11-02 | 1 | 3 | 0 | 5
2026-11-03 | 1 | 3 | 0 | 5
2026-11-04 | 1 | 3 | 0 | 5
2026-11-05 | 1 | 3 | 0 | 5
2026-11-06 | 1 | 3 | 0 | 5
2026-11-07 | 1 | 3 | 0 | 5
2026-11-08 | 1 | 3 | 0 | 5
2026-11-09 | 1 | 3 | 0 | 5
2026-11-10 | 1 | 3 | 0 | 5
2026-11-11 | 1 | 3 | 0 | 5
2026-11-12 | 1 | 3 | 0 | 5
2026-11-13 | 1 | 3 | 0 | 5
2026-11-14 | 1 | 3 | 0 | 5
2026-11-15 | 1 | 3 | 0 | 5
2026-11-16 | 1 | 3 | 0 | 5
2026-11-17 | 1 | 3 | 0 | 5
2026-11-18 | 1 | 3 | 0 | 5
2026-11-19 | 1 | 3 | 0 | 5
2026-11-20 | 1 | 3 | 0 | 5
2026-11-21 | 1 | 3 | 0 | 5
2026-11-22 | 1 | 3 | 0 | 5
2026-11-23 | 1 | 3 | 0 | 5
2026-11-24 | 1 | 3 | 0 | 5
2026-11-25 | 1 | 3 | 0 | 5
2026-11-26 | 1 | 3 | 0 | 5
2026-11-27 | 1 | 3 | 0 | 5
2026-11-28 | 1 | 3 | 0 | 5
2026-11-29 | 1 | 3 | 0 | 5
2026-11-30 | 1 | 3 | 0 | 3
2026-12-01 | 1 | 3 | 0 | 3
2026-12-02 | 1 | 3 | 0 | 3
2026-12-03 | 1 | 3 | 0 | 3
2026-12-04 | 1 | 3 | 0 | 3
2026-12-05 | 1 | 3 | 0 | 3
2026-12-06 | 1 | 3 | 0 | 3
2026-12-07 | 1 | 3 | 0 | 3
2026-12-08 | 1 | 3 | 0 | 3
2026-12-09 | 1 | 3 | 0 | 3
2026-12-10 | 1 | 3 | 0 | 3
2026-12-11 | 1 | 3 | 0 | 3
2026-12-12 | 1 | 3 | 0 | 3
2026-12-13 | 1 | 3 | 0 | 3
2026-12-14 | 1 | 3 | 0 | 3
2026-12-15 | 1 | 3 | 0 | 3
2026-12-16 | 1 | 3 | 0 | 3
2026-12-17 | 1 | 3 | 0 | 3
2026-12-18 | 1 | 3 | 0 | 3
2026-12-19 | 1 | 3 | 0 | 3
2026-12-20 | 1 | 3 | 0 | 3
2026-12-21 | 1 | 3 | 0 | 3
2026-12-22 | 1 | 3 | 0 | 3
2026-12-23 | 1 | 0 | 0 | 3
2026-12-24 | 1 | 0 | 0 | 3
2026-12-25 | 1 | 0 | 0 | 3
2026-12-26 | 1 | 0 | 0 | 3
2026-12-27 | 1 | 0 | 0 | 3
2026-12-28 | 1 | 0 | 0 | 3
2026-12-29 | 1 | 0 | 0 | 3
2026-12-30 | 1 | 0 | 0 | 3
2026-12-31 | 1 | 0 | 0 | 0
2027-01-01 | 1 | 0 | 0 | 0

## Task_Table_02_26 (hidden)
Initiative | Process | Phase | Process level | Process Group | % Work Complete | IT Process Consultant | Responsible | IT Process Manager |  |  | Duration2 | Process approval date | Actual Phase | Planned phase | Associated Process on L1
Corporate IT body | Manage IT strategy | Total | L1 | MP | 15% |  |  |  | 2026-01-07 | 2026-06-30 | 125 | 2025-10-23 |  |  | Manage IT strategy
Corporate IT body | Manage IT strategy | Elaboration | L1 | MP | 15% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  | Elaboration in progress | Elaboration in progress | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT strategy
Corporate IT body | Manage IT governance framework | Total | L1 | MP | 0% |  |  |  | 2026-01-07 | 2026-06-30 | 125 |  |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Elaboration | L1 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  | Delayed | Elaboration in progress | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Total | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Elaboration | L2 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | [5 empty] | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-01-07 | 2026-01-17 | 8 |  | Delayed | Implementation LIS Done | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation COT | L2 | MP | 0% |  |  |  | 2026-01-07 | [5 empty] | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT governance framework
Corporate IT body | Manage enterprise architecture | Total | L1 | MP | 0% |  |  |  | 2025-10-16 | 2026-07-02 | 186 |  |  |  | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Elaboration | L1 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 2026-02-09 | 2026-04-24 | 55 |  | Delayed | Elaboration in progress | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-24 | 2026-07-02 | 50 |  |  | Scheduled | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation COT | L1 | MP | 0% |  |  |  | 2026-02-09 | 2026-02-09 | 1 |  | Delayed | Implementation COT Done | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LUS | L1 | MP | 0% |  |  |  | 2026-04-30 | 2026-04-30 | 1 |  |  | Scheduled | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Elaboration | L2 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 2025-10-16 | 2025-10-16 | 1 |  | Delayed | Elaboration Done | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LIS | L2 | MP | 0% |  |  |  |  | 2026-04-30 |  |  |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation COT | L2 | MP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 1 |  | Delayed | Implementation COT Done | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LUS | L2 | MP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 1 |  | Delayed | Implementation LUS Done | Manage enterprise architecture
ITSM | Manage IT portfolio | Total | L1 | MP | 11% |  |  |  | 2025-11-10 | 2026-05-15 | 135 |  |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Elaboration | L1 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | ? |  | 2025-11-11 | 2026-01-29 | 58 |  | Delayed | Elaboration Done | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation COT | L1 | MP | 0% |  |  |  | 2025-11-10 | [5 empty] | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Total | L2 | MP | 100% |  |  |  | 2025-10-09 | 2025-12-10 | 45 |  |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Elaboration | L2 | MP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-10 | 2025-12-10 | 23 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 2025-10-09 | [5 empty] | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Total | L2 | MP | 0% |  |  |  | 2026-02-23 | 2026-06-30 | 92 |  |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Elaboration | L2 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | ? | Reiner Heiko (HAU-ITSA) | 2026-02-23 | 2026-04-06 | 31 |  |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-06 | 2026-06-30 | 62 |  |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT portfolio
IT planning and steering | Manage and control IT financials | Total | L1 | MP | 0% |  |  | Moser Mario (LIS-LAH) | 2025-10-15 | 2026-09-30 | 251 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Elaboration | L1 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Total | L2 | MP | 0% |  |  |  | 2026-01-07 | 2026-06-29 | 124 |  |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-23 | 54 |  | Delayed | Elaboration in progress | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-06 | 2026-06-29 | 61 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  | 18 | Manage and control IT financials
IT planning and steering | Review budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Total | L2 | MP | 0% |  |  |  | 2025-10-15 | 2026-03-23 | 114 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2026-01-07 | 2026-03-23 | 54 |  | Delayed | Elaboration in progress | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Total | L2 | MP | 0% |  |  |  | 2026-01-12 | 2026-06-22 | 116 |  |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2026-01-12 | 2026-03-31 | 57 |  | Delayed | Elaboration in progress | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-07 | 2026-06-22 | 55 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation COT |  | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget (forecast) | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Total | L2 | MP | 0% |  |  |  | 2026-01-12 | 2026-09-30 | 188 |  |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Elaboration | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2026-01-12 | 2026-03-31 | 57 |  | Delayed | Elaboration in progress | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation COT | L2 | MP | 0% |  |  |  | 2026-02-02 | 2026-09-30 | 173 |  | Delayed | Implementation COT | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders / companies | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders / companies | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders / companies | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders / companies | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders / companies | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Total | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Elaboration | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) |  |  | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage and control IT financials
Corporate IT body | Manage IT stakeholder relationships | Total | L1 | MP | 0% |  |  |  | 2026-04-01 | 2026-12-23 | 191 |  |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Elaboration | L1 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 |  |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT stakeholder relationships
ITSM | Manage IT processes and continuous improvement | Total | L1 | MP | 0% |  |  |  | 2025-10-01 | 2026-06-30 | 195 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Elaboration | L1 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-03-30 | 56 |  | Delayed | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Total | L2 | MP | 0% | [6 empty] | 2025-09-18 |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Total | L2 | MP | 0% |  |  |  | 2025-10-01 | 2026-01-30 | 88 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Elaboration | L2 | MP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-01-30 | 88 |  | Delayed | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Total | L3 | MP | 0% | [9 empty] | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Total | L3 | MP | 0% | [9 empty] | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Total | L2 | MP | 0% | [5 empty] | 0 | 2025-09-18 |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Elaboration | L2 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Total | L3 | MP | 0% | [5 empty] | 0 | 2025-09-18 |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Total | L3 | MP | 0% | [5 empty] | 0 | 2025-09-18 |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Total | L3 | MP | 0% | [5 empty] | 0 | 2025-09-18 |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Total | L3 | MP | 0% | [5 empty] | 0 | 2025-09-19 |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Total | L3 | MP | 0% | [5 empty] | 0 | 2025-09-18 |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Total | L3 | MP | 0% | [5 empty] | 0 | 2025-09-18 |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Elaboration | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT processes and continuous improvement
Central area (Jan Müskens) | Manage IT risks and compliance | Total | L1 | MP | 0% |  |  |  | 2025-10-01 | 2026-05-31 | 173 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Elaboration | L1 | MP | 0% | Rollinger Alexander (LIS);Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-02-28 | 97 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Elaboration Done | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation COT | L2 | MP | 0% |  |  |  | 2026-01-01 | 2026-02-28 | 42 |  | Delayed | Implementation COT | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2026-01-31 | 77 |  | Delayed | Elaboration Done | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-02-02 | 2026-04-30 | 64 |  | Delayed | Implementation LIS | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-05-31 | 162 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2026-03-31 | 119 |  | Delayed | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation COT | L2 | MP | 0% |  |  |  | 2026-04-01 | 2026-05-31 | 43 |  |  | Scheduled | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-03-31 | 119 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-16 | 2026-02-15 | 87 |  | Delayed | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation COT | L2 | MP | 0% |  |  |  | 2026-02-16 | 2026-03-31 | 32 |  |  | Scheduled | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Total | L2 | MP | 0% |  |  |  | 2025-10-01 | 2025-10-01 | 1 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Total | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | (DC/DCC/MSC IT-compliance | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  |  | Manage IT risks and compliance
Corporate IT body | Plan IT service | Total | L1 | CP | 0% |  |  |  | 2025-08-01 | 2026-04-30 | 195 |  |  |  | Plan IT service
Corporate IT body | Plan IT service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-10-16 | 2025-10-31 | 12 | 2025-12-10 | Delayed | Elaboration Done | Plan IT service
Corporate IT body | Plan IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Plan IT service | Implementation COT | L1 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 |  | Delayed | Implementation COT | Plan IT service
Corporate IT body | Plan IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Total | L2 | CP | 0% | [5 empty] | 0 | 2025-08-19 |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Total | L2 | CP | 0% |  |  |  | 2025-08-01 | 2026-04-30 | 195 | 2025-12-10 |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Total | L3 | CP | 0% |  |  |  | 2025-08-01 | 2026-04-30 | 195 |  |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Elaboration | L3 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-10-15 | 54 |  | Delayed | Elaboration Done | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation COT | L3 | CP | 0% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  | Delayed | Implementation COT | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Total | L2 | CP | 0% | [5 empty] | 0 | 2025-08-19 |  |  | Plan IT service
Corporate IT body | Approve IT demand | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
Corporate IT body | Approve IT demand | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Plan IT service
ITSM | Build IT Service | Total | L1 | CP | 0% |  |  |  | 2025-04-01 | 2026-08-31 | 370 |  |  |  | Build IT Service
ITSM | Build IT Service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) |  |  | 0 |  |  |  | Build IT Service
ITSM | Build IT Service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Build IT Service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Build IT Service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Design IT service | Total | L2 | CP | 0% |  |  |  | 2025-10-01 | 2026-08-14 | 228 |  |  |  | Build IT Service
ITSM | Design IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) | 2026-02-16 | 2026-05-15 | 65 |  |  | Scheduled | Build IT Service
ITSM | Design IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-05-18 | 2026-08-14 | 65 |  |  | Scheduled | Build IT Service
ITSM | Design IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Design IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Define solution target architecture | Total | L3 | CP | 0% |  |  |  | 2026-01-14 | 2026-06-22 | 114 |  |  |  | Build IT Service
Architecture management | Define solution target architecture | Elaboration | L3 | CP | 0% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) | 2026-02-05 | 2026-04-21 | 54 |  | Delayed | Elaboration in progress | Build IT Service
Architecture management | Define solution target architecture | Implementation LIS | L3 | CP | 0% |  |  |  | 2026-04-22 | 2026-06-22 | 44 |  |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation COT | L3 | CP | 0% |  |  |  | 2026-04-22 | 2026-04-22 | 1 |  |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation LUS | L3 | CP | 0% |  |  |  | 2026-01-14 | 2026-01-14 | 1 |  | Delayed | Implementation LUS Done | Build IT Service
Architecture management | Perform software selection | Total | L3 | CP | 0% |  |  |  | 2025-10-01 | 2026-04-30 | 152 | 2025-10-14 |  |  | Build IT Service
Architecture management | Perform software selection | Elaboration | L3 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 60 |  | Delayed | Elaboration Done | Build IT Service
Architecture management | Perform software selection | Implementation LIS | L3 | CP | 0% |  |  |  | 2026-02-16 | 2026-04-30 | 54 |  |  | Scheduled | Build IT Service
Architecture management | Perform software selection | Implementation COT | L3 | CP | 0% |  |  |  | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Implementation COT Done | Build IT Service
Architecture management | Perform software selection | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Total | L4 | CP | 0% | [5 empty] | 0 | 2025-10-14 |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Record and plan functional requirements | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Total | L4 | CP | 0% | [5 empty] | 0 | 2025-10-14 |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Conduct market analysis & compile long/short list | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Total | L4 | CP | 0% | [5 empty] | 0 | 2025-10-14 |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Perform vendor use case pitch & usability test | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Total | L4 | CP | 0% | [5 empty] | 0 | 2025-10-14 |  |  | Build IT Service
Architecture management | Validate strategic fit | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Validate strategic fit | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Total | L4 | CP | 0% | [5 empty] | 0 | 2025-10-14 |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Elaboration | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
Architecture management | Recommendation & EA approval | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Develop and customise IT service | Total | L2 | CP | 0% |  |  |  | 2025-05-26 | 2026-05-15 | 255 |  |  |  | Build IT Service
ITSM | Develop and customise IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) |  | 2026-02-16 | 2026-05-15 | 65 |  |  | Scheduled | Build IT Service
ITSM | Develop and customise IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-05-26 | 2025-08-15 | 60 |  | Delayed | Implementation LIS Done | Build IT Service
ITSM | Develop and customise IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Develop and customise IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Deploy IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 |  |  |  | Build IT Service
ITSM | Deploy IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 |  |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Deploy IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
| Test and validate IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 |  |  |  | Build IT Service
ITSM | Test and validate IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 |  |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Test and validate IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Total | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Koiner Alexander (LWN) |  |  | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manage IT service change | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-30 | 122 |  |  |  | Build IT Service
ITSM | Manag IT service change | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Koiner Alexander (LWN) | 2026-01-12 | 2026-03-30 | 56 |  | Delayed | Elaboration in progress | Build IT Service
ITSM | Manag IT service change | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Build IT Service
ITSM | Manag IT service change | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manag IT service change | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manage IT service release | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-30 | 122 |  |  |  | Build IT Service
ITSM | Manage IT service release | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Koiner Alexander (LWN) | 2026-01-12 | 2026-03-30 | 56 |  | Delayed | Elaboration in progress | Build IT Service
ITSM | Manage IT service release | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Build IT Service
ITSM | Manage IT service release | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Manage IT service release | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Build IT Service
ITSM | Deliver IT service | Total | L1 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-15 | 111 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Elaboration | L1 | CP | 0% | Hoermann Patrick (LLI) | Mechegia Eloise (LIS) | Bergmann Aniko (LIS-LIN) |  |  | 0 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Manage IT service provision request | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-15 | 111 |  |  |  | Deliver IT service
ITSM | Manage IT service provision request | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Mechegia Eloise (LIS) | Bergmann Aniko (LIS-LIN) | 2026-01-12 | 2026-03-30 | 56 |  | Delayed | Elaboration in progress | Deliver IT service
ITSM | Manage IT service provision request | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Deliver IT service
ITSM | Manage IT service provision request | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Manage IT service provision request | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Handle IT service order | Total | L2 | CP | 0% |  |  |  | 2026-01-12 | 2026-06-15 | 111 |  |  |  | Deliver IT service
ITSM | Handle IT service order | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Mechegia Eloise (LIS) | Bergmann Aniko (LIS-LIN) | 2026-01-12 | 2026-03-30 | 56 |  | Delayed | Elaboration in progress | Deliver IT service
ITSM | Handle IT service order | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Deliver IT service
ITSM | Handle IT service order | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Handle IT service order | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Deliver IT service
ITSM | Run IT service | Total | L1 | CP | 12% |  |  |  | 2025-10-15 | 2026-06-30 | 185 |  |  |  | Run IT service
ITSM | Run IT service | Elaboration | L1 | CP | 0% | Schroeder Michael (LIS) |  |  |  |  | 0 |  |  |  | Run IT service
ITSM | Run IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Run IT service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Run IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Ensure IT service continuity | Total | L2 | CP | 0% |  |  |  | 2025-10-15 | 2026-06-30 | 185 |  |  |  | Run IT service
ITSM | Ensure IT service continuity | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Held Matthias | Sint Rachel (LBH) | 2026-01-15 | 2026-03-16 | 43 |  | Delayed | Elaboration in progress | Run IT service
ITSM | Ensure IT service continuity | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Run IT service
ITSM | Ensure IT service continuity | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Total | L2 | CP | 0% |  |  |  | 2025-10-15 | 2026-03-30 | 119 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kueschner Phillip (LIS) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  | Delayed | Elaboration in progress | Run IT service
ITSM | Montior and report IT service performance | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias |  |  |  | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Monitor user experience | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Operate and maintain IT service | Total | L2 | CP | 5% |  |  |  | 2025-10-15 | 2026-06-30 | 185 |  |  |  | Run IT service
ITSM | Operate and maintain IT service | Elaboration | L2 | CP | 5% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  | Elaboration in progress | Elaboration in progress | Run IT service
ITSM | Operate and maintain IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Run IT service
ITSM | Operate and maintain IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Operate and maintain IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Total | L3 | CP | 5% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Elaboration | L3 | CP | 5% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) |  | 2026-01-14 | 2026-03-30 | 54 |  | Elaboration in progress | Elaboration in progress | Run IT service
ITSM | Maintain CMDB | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain CMDB | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Provide IT service support | Total | L2 | CP | 27% |  |  |  | 2025-10-15 | 2026-06-15 | 174 |  |  |  | Run IT service
ITSM | Provide IT service support | Elaboration | L2 | CP | 10% | Schroeder Michael (LIS) | Kürschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  | Elaboration in progress | Elaboration in progress | Run IT service
ITSM | Provide IT service support | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Run IT service
ITSM | Provide IT service support | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Provide IT service support | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Total | L3 | CP | 50% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Elaboration | L3 | CP | 50% | Schroeder Michael (LIS) | Kürschner Philipp (LIS) |  | 2026-01-13 | 2026-02-25 | 32 |  | Elaboration in progress | Elaboration in progress | Run IT service
ITSM | Handle IT Incident | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT Incident | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Total | L3 | CP | 50% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Elaboration | L3 | CP | 50% | Schroeder Michael (LIS) | Kürschner Philipp (LIS) |  | 2026-01-13 | 2026-02-25 | 32 |  | Elaboration in progress | Elaboration in progress | Run IT service
ITSM | Handle IT problem | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT problem | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Total | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Elaboration | L3 | CP | 0% | Frank Maren (LIS) | Kürschner Philipp (LIS) |  | 2026-02-02 | 2026-02-25 | 18 |  | Delayed | Elaboration in progress | Run IT service
ITSM | Handle IT service request | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Handle IT service request | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Total | L3 | CP | 0% |  | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) |  |  |  | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  |  | Run IT service
Information security | Ensure Information security | Total | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) |  |  | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Total | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Elaboration | L2 | SP | 0% | Hoermann Patrick (LLI) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure Information security
IT project management | Manage IT project | Total | L1 | SP | 100% |  |  |  | 2025-07-14 | 2025-12-10 | 108 | 2025-09-18 |  |  | Manage IT project
IT project management | Manage IT project | Elaboration | L1 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Manage IT project | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Initiate IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project
IT project management | Initiate IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Initiate IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Initiate IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Initiate IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Plan IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project
IT project management | Plan IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Plan IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Plan IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Plan IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Steer & execute IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project
IT project management | Steer & execute IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Steer & execute IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Steer & execute IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Steer & execute IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Close IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project
IT project management | Close IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Close IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Close IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Close IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project change request | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project
IT project management | Manage IT project change request | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Manage IT project change request | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Assign personnel resources to IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 |  |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT project
ITSM | Manage IT sourcing and procurement | Total | L1 | SP | 0% |  |  |  | 2026-04-20 | 2026-09-30 | 118 |  |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Elaboration | L1 | SP | 0% | Moser Mario (LIS-LAH);Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Frick Markus (LIS) | Monnier Murielle (LEC) | 2026-04-20 | 2026-06-30 | 52 |  |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-13 | 2026-09-30 | 58 |  |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT sourcing and procurement
HR initiatives for IT | Provide and develop IT workforce | Total | L1 | SP | 0% |  |  |  | 2025-10-16 | 2027-06-15 | 434 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Elaboration | L1 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Rollinger Alexander (LIS) |  |  | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Total | L2 | SP | 0% |  |  |  | 2025-10-16 | 2026-12-31 | 316 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation COT | L2 | SP | 0% |  |  |  | 2026-01-01 | 2026-12-31 | 261 |  | Delayed | Implementation COT | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Total | L2 | SP | 0% |  |  |  | 2026-01-07 | 2026-06-15 | 114 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kiesewetter Ivana (LIS) | Rollinger Alexander (LIS) | 2026-01-07 | 2026-03-16 | 49 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Recruit IT workforce | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Total | L2 | SP | 0% |  |  |  | 2026-01-07 | 2026-06-15 | 114 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kiesewetter Ivana (LIS) | Rollinger Alexander (LIS) | 2026-01-07 | 2026-03-16 | 49 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Total | L2 | SP | 0% |  |  |  | 2025-10-16 | 2026-02-02 | 78 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kramer Annika (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2025-11-30 | 32 |  | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Implementation COT | L2 | SP | 0% |  |  |  | 2025-12-01 | 2026-02-02 | 46 |  | Delayed | Implementation COT Done | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Total | L2 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kramer Annika (LIS) | Mielenz Thomas (LMT) | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Implementation COT | L2 | SP | 0% |  |  |  | 2026-07-01 | 2026-09-30 | 66 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Monitoring IT employee retention | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Total | L2 | SP | 0% |  |  |  | 2025-10-16 | 2026-12-31 | 316 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2026-04-30 | 141 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation COT | L2 | SP | 0% |  |  |  | 2026-05-04 | 2026-12-31 | 174 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Total | L2 | SP | 0% |  |  |  | 2026-01-01 | 2026-11-30 | 238 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Implementation COT | L2 | SP | 0% |  |  |  | 2026-01-01 | 2026-11-30 | 238 |  | Delayed | Implementation COT | Provide and develop IT workforce
HR initiatives for IT | Evaluate IT career path | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Total | L2 | SP | 0% |  |  |  | 2026-01-15 | 2026-12-23 | 245 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-05-04 | 78 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Implementation COT | L2 | SP | 0% |  |  |  | 2026-02-02 | 2026-11-30 | 216 |  | Delayed | Implementation COT | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Total | L2 | SP | 0% |  |  |  | 2026-04-01 | 2027-06-15 | 315 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2027-06-15 | 315 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation COT | L2 | SP | 0% |  |  |  | 2026-05-04 | 2026-12-31 | 174 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Total | L2 | SP | 0% |  |  |  | 2026-01-15 | 2026-03-31 | 54 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-03-31 | 54 |  | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Total | L2 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Elaboration | L2 | SP | 0% | Moser Mario (LIS-LAH) | Kramer Annika (LIS) | Mielenz Thomas (LMT) | 2026-04-15 | 2026-06-15 | 44 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Implementation COT | L2 | SP | 0% |  |  |  | 2026-05-18 | 2026-09-30 | 98 |  |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT employee benefits | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  |  | Provide and develop IT workforce
ITSM | Ensure performance and conformance of IT services | Total | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Elaboration | L1 | SP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Ensure performance and conformance of IT services
ITSM | Manage IT knowledge | Total | L1 | SP | 50% |  |  |  | 2026-01-20 | 2026-06-30 | 116 |  |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Elaboration | L1 | SP | 50% | Schroeder Michael (LIS) | Kürschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-20 | 2026-02-25 | 27 |  | Elaboration in progress | Elaboration in progress | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Manage IT knowledge
ITSM | Leverage IT innovtion | Total | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-09-30 | 121 |  |  |  | Leverage IT innovtion
ITSM | Leverage IT innovtion | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS) | Frick Markus (LIS) | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 |  |  | Scheduled | Leverage IT innovtion
ITSM | Leverage IT innovtion | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-15 | 2026-09-30 | 56 |  |  | Scheduled | Leverage IT innovtion
ITSM | Leverage IT innovtion | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Leverage IT innovtion
ITSM | Leverage IT innovtion | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  |  | Leverage IT innovtion
[5 empty] | 0% | [5 empty] | 0 dys

## Date_table_02_26 (hidden)
Datum | Elaboration | Implementation LIS | Implementation LUS | Implementation COT
2025-08-01 | 0 | 2 | 0 | 0
2025-08-02 | 1 | 2 | 0 | 0
2025-08-03 | 1 | 2 | 0 | 0
2025-08-04 | 1 | 2 | 0 | 0
2025-08-05 | 1 | 2 | 0 | 0
2025-08-06 | 1 | 2 | 0 | 0
2025-08-07 | 1 | 2 | 0 | 0
2025-08-08 | 1 | 2 | 0 | 0
2025-08-09 | 1 | 2 | 0 | 0
2025-08-10 | 1 | 2 | 0 | 0
2025-08-11 | 1 | 2 | 0 | 0
2025-08-12 | 1 | 2 | 0 | 0
2025-08-13 | 1 | 2 | 0 | 0
2025-08-14 | 1 | 2 | 0 | 0
2025-08-15 | 1 | 1 | 0 | 0
2025-08-16 | 1 | 1 | 0 | 0
2025-08-17 | 1 | 1 | 0 | 0
2025-08-18 | 1 | 1 | 0 | 0
2025-08-19 | 1 | 1 | 0 | 0
2025-08-20 | 1 | 1 | 0 | 0
2025-08-21 | 1 | 1 | 0 | 0
2025-08-22 | 1 | 1 | 0 | 0
2025-08-23 | 1 | 1 | 0 | 0
2025-08-24 | 1 | 1 | 0 | 0
2025-08-25 | 1 | 1 | 0 | 0
2025-08-26 | 1 | 1 | 0 | 0
2025-08-27 | 1 | 1 | 0 | 0
2025-08-28 | 1 | 1 | 0 | 0
2025-08-29 | 1 | 1 | 0 | 0
2025-08-30 | 1 | 1 | 0 | 0
2025-08-31 | 1 | 1 | 0 | 0
2025-09-01 | 1 | 1 | 0 | 0
2025-09-02 | 1 | 1 | 0 | 0
2025-09-03 | 1 | 1 | 0 | 0
2025-09-04 | 1 | 1 | 0 | 0
2025-09-05 | 1 | 1 | 0 | 0
2025-09-06 | 1 | 1 | 0 | 0
2025-09-07 | 1 | 1 | 0 | 0
2025-09-08 | 1 | 1 | 0 | 0
2025-09-09 | 1 | 1 | 0 | 0
2025-09-10 | 1 | 1 | 0 | 0
2025-09-11 | 1 | 1 | 0 | 0
2025-09-12 | 1 | 1 | 0 | 0
2025-09-13 | 1 | 1 | 0 | 0
2025-09-14 | 1 | 1 | 0 | 0
2025-09-15 | 1 | 1 | 0 | 0
2025-09-16 | 1 | 1 | 0 | 0
2025-09-17 | 1 | 1 | 0 | 0
2025-09-18 | 1 | 1 | 0 | 0
2025-09-19 | 1 | 1 | 0 | 0
2025-09-20 | 1 | 1 | 0 | 0
2025-09-21 | 1 | 1 | 0 | 0
2025-09-22 | 1 | 1 | 0 | 0
2025-09-23 | 1 | 1 | 0 | 0
2025-09-24 | 1 | 1 | 0 | 0
2025-09-25 | 1 | 1 | 0 | 0
2025-09-26 | 1 | 1 | 0 | 0
2025-09-27 | 1 | 1 | 0 | 0
2025-09-28 | 1 | 1 | 0 | 0
2025-09-29 | 1 | 1 | 0 | 0
2025-09-30 | 1 | 1 | 0 | 0
2025-10-01 | 1 | 1 | 0 | 0
2025-10-02 | 3 | 1 | 0 | 0
2025-10-03 | 3 | 1 | 0 | 0
2025-10-04 | 3 | 1 | 0 | 0
2025-10-05 | 3 | 1 | 0 | 0
2025-10-06 | 3 | 1 | 0 | 0
2025-10-07 | 3 | 1 | 0 | 0
2025-10-08 | 3 | 1 | 0 | 0
2025-10-09 | 3 | 1 | 0 | 0
2025-10-10 | 3 | 1 | 0 | 0
2025-10-11 | 3 | 1 | 0 | 0
2025-10-12 | 3 | 1 | 0 | 0
2025-10-13 | 3 | 1 | 0 | 0
2025-10-14 | 3 | 1 | 0 | 0
2025-10-15 | 2 | 1 | 0 | 0
2025-10-16 | 2 | 1 | 0 | 0
2025-10-17 | 10 | 1 | 0 | 2
2025-10-18 | 10 | 1 | 0 | 2
2025-10-19 | 10 | 1 | 0 | 2
2025-10-20 | 10 | 1 | 0 | 2
2025-10-21 | 10 | 1 | 0 | 2
2025-10-22 | 10 | 1 | 0 | 2
2025-10-23 | 10 | 1 | 0 | 2
2025-10-24 | 10 | 1 | 0 | 2
2025-10-25 | 10 | 1 | 0 | 2
2025-10-26 | 10 | 1 | 0 | 2
2025-10-27 | 10 | 1 | 0 | 2
2025-10-28 | 10 | 1 | 0 | 2
2025-10-29 | 10 | 1 | 0 | 2
2025-10-30 | 10 | 1 | 0 | 2
2025-10-31 | 9 | 1 | 0 | 2
2025-11-01 | 9 | 1 | 0 | 2
2025-11-02 | 9 | 1 | 0 | 2
2025-11-03 | 9 | 1 | 0 | 2
2025-11-04 | 9 | 1 | 0 | 3
2025-11-05 | 9 | 1 | 0 | 3
2025-11-06 | 9 | 1 | 0 | 3
2025-11-07 | 9 | 1 | 0 | 3
2025-11-08 | 9 | 1 | 0 | 3
2025-11-09 | 9 | 1 | 0 | 3
2025-11-10 | 9 | 1 | 0 | 3
2025-11-11 | 10 | 1 | 0 | 3
2025-11-12 | 18 | 1 | 0 | 3
2025-11-13 | 18 | 1 | 0 | 3
2025-11-14 | 18 | 1 | 0 | 3
2025-11-15 | 18 | 1 | 0 | 3
2025-11-16 | 18 | 1 | 0 | 3
2025-11-17 | 18 | 1 | 0 | 3
2025-11-18 | 18 | 1 | 0 | 3
2025-11-19 | 18 | 1 | 0 | 3
2025-11-20 | 18 | 1 | 0 | 3
2025-11-21 | 18 | 1 | 0 | 3
2025-11-22 | 18 | 1 | 0 | 3
2025-11-23 | 18 | 1 | 0 | 3
2025-11-24 | 18 | 1 | 0 | 3
2025-11-25 | 18 | 1 | 0 | 3
2025-11-26 | 18 | 1 | 0 | 3
2025-11-27 | 18 | 1 | 0 | 3
2025-11-28 | 18 | 1 | 0 | 3
2025-11-29 | 18 | 1 | 0 | 3
2025-11-30 | 17 | 1 | 0 | 3
2025-12-01 | 17 | 1 | 0 | 3
2025-12-02 | 17 | 1 | 0 | 4
2025-12-03 | 17 | 1 | 0 | 4
2025-12-04 | 17 | 1 | 0 | 4
2025-12-05 | 17 | 1 | 0 | 4
2025-12-06 | 17 | 1 | 0 | 4
2025-12-07 | 17 | 1 | 0 | 4
2025-12-08 | 17 | 1 | 0 | 4
2025-12-09 | 17 | 1 | 0 | 4
2025-12-10 | 9 | 1 | 0 | 4
2025-12-11 | 9 | 1 | 0 | 4
2025-12-12 | 9 | 1 | 0 | 4
2025-12-13 | 9 | 1 | 0 | 4
2025-12-14 | 9 | 1 | 0 | 4
2025-12-15 | 9 | 1 | 0 | 4
2025-12-16 | 9 | 1 | 0 | 4
2025-12-17 | 9 | 1 | 0 | 4
2025-12-18 | 9 | 1 | 0 | 4
2025-12-19 | 9 | 1 | 0 | 4
2025-12-20 | 9 | 1 | 0 | 4
2025-12-21 | 9 | 1 | 0 | 4
2025-12-22 | 9 | 1 | 0 | 4
2025-12-23 | 8 | 1 | 0 | 4
2025-12-24 | 8 | 1 | 0 | 4
2025-12-25 | 8 | 1 | 0 | 4
2025-12-26 | 8 | 1 | 0 | 4
2025-12-27 | 8 | 1 | 0 | 4
2025-12-28 | 8 | 1 | 0 | 4
2025-12-29 | 8 | 1 | 0 | 4
2025-12-30 | 8 | 1 | 0 | 4
2025-12-31 | 6 | 1 | 0 | 3
2026-01-01 | 6 | 1 | 0 | 3
2026-01-02 | 6 | 1 | 0 | 6
2026-01-03 | 6 | 1 | 0 | 6
2026-01-04 | 6 | 1 | 0 | 6
2026-01-05 | 6 | 1 | 0 | 6
2026-01-06 | 6 | 1 | 0 | 6
2026-01-07 | 6 | 1 | 0 | 6
2026-01-08 | 13 | 2 | 0 | 6
2026-01-09 | 13 | 2 | 0 | 6
2026-01-10 | 13 | 2 | 0 | 6
2026-01-11 | 13 | 2 | 0 | 6
2026-01-12 | 13 | 2 | 0 | 6
2026-01-13 | 23 | 2 | 0 | 6
2026-01-14 | 25 | 2 | 0 | 6
2026-01-15 | 26 | 2 | 0 | 6
2026-01-16 | 29 | 2 | 0 | 6
2026-01-17 | 29 | 1 | 0 | 6
2026-01-18 | 29 | 1 | 0 | 6
2026-01-19 | 29 | 1 | 0 | 6
2026-01-20 | 29 | 1 | 0 | 6
2026-01-21 | 30 | 1 | 0 | 6
2026-01-22 | 30 | 1 | 0 | 6
2026-01-23 | 30 | 1 | 0 | 6
2026-01-24 | 30 | 1 | 0 | 6
2026-01-25 | 30 | 1 | 0 | 6
2026-01-26 | 30 | 1 | 0 | 6
2026-01-27 | 30 | 1 | 0 | 6
2026-01-28 | 30 | 1 | 0 | 6
2026-01-29 | 29 | 1 | 0 | 6
2026-01-30 | 28 | 1 | 0 | 6
2026-01-31 | 27 | 1 | 0 | 6
2026-02-01 | 27 | 1 | 0 | 6
2026-02-02 | 27 | 1 | 0 | 5
2026-02-03 | 28 | 2 | 0 | 7
2026-02-04 | 28 | 2 | 0 | 7
2026-02-05 | 28 | 2 | 0 | 7
2026-02-06 | 29 | 2 | 0 | 7
2026-02-07 | 29 | 2 | 0 | 7
2026-02-08 | 29 | 2 | 0 | 7
2026-02-09 | 29 | 2 | 0 | 7
2026-02-10 | 30 | 2 | 0 | 7
2026-02-11 | 30 | 2 | 0 | 7
2026-02-12 | 30 | 2 | 0 | 7
2026-02-13 | 30 | 2 | 0 | 7
2026-02-14 | 30 | 2 | 0 | 7
2026-02-15 | 29 | 2 | 0 | 7
2026-02-16 | 29 | 2 | 0 | 7
2026-02-17 | 31 | 3 | 0 | 8
2026-02-18 | 31 | 3 | 0 | 8
2026-02-19 | 31 | 3 | 0 | 8
2026-02-20 | 31 | 3 | 0 | 8
2026-02-21 | 31 | 3 | 0 | 8
2026-02-22 | 31 | 3 | 0 | 8
2026-02-23 | 31 | 3 | 0 | 8
2026-02-24 | 32 | 3 | 0 | 8
2026-02-25 | 28 | 3 | 0 | 8
2026-02-26 | 28 | 3 | 0 | 8
2026-02-27 | 28 | 3 | 0 | 8
2026-02-28 | 28 | 3 | 0 | 7
2026-03-01 | 28 | 3 | 0 | 7
2026-03-02 | 28 | 3 | 0 | 7
2026-03-03 | 28 | 3 | 0 | 7
2026-03-04 | 28 | 3 | 0 | 7
2026-03-05 | 28 | 3 | 0 | 7
2026-03-06 | 28 | 3 | 0 | 7
2026-03-07 | 28 | 3 | 0 | 7
2026-03-08 | 28 | 3 | 0 | 7
2026-03-09 | 28 | 3 | 0 | 7
2026-03-10 | 28 | 3 | 0 | 7
2026-03-11 | 28 | 3 | 0 | 7
2026-03-12 | 28 | 3 | 0 | 7
2026-03-13 | 28 | 3 | 0 | 7
2026-03-14 | 28 | 3 | 0 | 7
2026-03-15 | 28 | 3 | 0 | 7
2026-03-16 | 22 | 3 | 0 | 7
2026-03-17 | 22 | 3 | 0 | 7
2026-03-18 | 22 | 3 | 0 | 7
2026-03-19 | 22 | 3 | 0 | 7
2026-03-20 | 22 | 3 | 0 | 7
2026-03-21 | 22 | 3 | 0 | 7
2026-03-22 | 22 | 3 | 0 | 7
2026-03-23 | 20 | 3 | 0 | 7
2026-03-24 | 20 | 3 | 0 | 7
2026-03-25 | 20 | 3 | 0 | 7
2026-03-26 | 20 | 3 | 0 | 7
2026-03-27 | 20 | 3 | 0 | 7
2026-03-28 | 20 | 3 | 0 | 7
2026-03-29 | 20 | 3 | 0 | 7
2026-03-30 | 11 | 3 | 0 | 7
2026-03-31 | 7 | 3 | 0 | 5
2026-04-01 | 7 | 3 | 0 | 5
2026-04-02 | 9 | 9 | 0 | 9
2026-04-03 | 9 | 9 | 0 | 9
2026-04-04 | 9 | 9 | 0 | 9
2026-04-05 | 9 | 9 | 0 | 9
2026-04-06 | 8 | 9 | 0 | 9
2026-04-07 | 8 | 11 | 0 | 9
2026-04-08 | 8 | 12 | 0 | 9
2026-04-09 | 8 | 12 | 0 | 9
2026-04-10 | 8 | 12 | 0 | 9
2026-04-11 | 8 | 12 | 0 | 9
2026-04-12 | 8 | 12 | 0 | 9
2026-04-13 | 8 | 12 | 0 | 9
2026-04-14 | 8 | 12 | 0 | 9
2026-04-15 | 8 | 12 | 0 | 9
2026-04-16 | 14 | 21 | 0 | 9
2026-04-17 | 14 | 21 | 0 | 9
2026-04-18 | 14 | 21 | 0 | 9
2026-04-19 | 14 | 21 | 0 | 9
2026-04-20 | 14 | 21 | 0 | 9
2026-04-21 | 14 | 21 | 0 | 9
2026-04-22 | 14 | 21 | 0 | 9
2026-04-23 | 14 | 22 | 0 | 9
2026-04-24 | 13 | 22 | 0 | 9
2026-04-25 | 13 | 23 | 0 | 9
2026-04-26 | 13 | 23 | 0 | 9
2026-04-27 | 13 | 23 | 0 | 9
2026-04-28 | 13 | 23 | 0 | 9
2026-04-29 | 13 | 23 | 0 | 9
2026-04-30 | 12 | 20 | 0 | 8
2026-05-01 | 12 | 20 | 0 | 8
2026-05-02 | 12 | 20 | 0 | 8
2026-05-03 | 12 | 20 | 0 | 8
2026-05-04 | 11 | 20 | 0 | 8
2026-05-05 | 11 | 20 | 0 | 10
2026-05-06 | 11 | 20 | 0 | 10
2026-05-07 | 11 | 20 | 0 | 10
2026-05-08 | 11 | 20 | 0 | 10
2026-05-09 | 11 | 20 | 0 | 10
2026-05-10 | 11 | 20 | 0 | 10
2026-05-11 | 11 | 20 | 0 | 10
2026-05-12 | 11 | 20 | 0 | 10
2026-05-13 | 11 | 20 | 0 | 10
2026-05-14 | 11 | 20 | 0 | 10
2026-05-15 | 9 | 20 | 0 | 10
2026-05-16 | 9 | 20 | 0 | 10
2026-05-17 | 9 | 20 | 0 | 10
2026-05-18 | 9 | 20 | 0 | 10
2026-05-19 | 9 | 21 | 0 | 11
2026-05-20 | 9 | 21 | 0 | 11
2026-05-21 | 9 | 21 | 0 | 11
2026-05-22 | 9 | 21 | 0 | 11
2026-05-23 | 9 | 21 | 0 | 11
2026-05-24 | 9 | 21 | 0 | 11
2026-05-25 | 9 | 21 | 0 | 11
2026-05-26 | 9 | 21 | 0 | 11
2026-05-27 | 9 | 21 | 0 | 11
2026-05-28 | 9 | 21 | 0 | 11
2026-05-29 | 9 | 21 | 0 | 11
2026-05-30 | 9 | 21 | 0 | 11
2026-05-31 | 9 | 21 | 0 | 10
2026-06-01 | 9 | 21 | 0 | 10
2026-06-02 | 9 | 21 | 0 | 10
2026-06-03 | 9 | 21 | 0 | 10
2026-06-04 | 9 | 21 | 0 | 10
2026-06-05 | 9 | 21 | 0 | 10
2026-06-06 | 9 | 21 | 0 | 10
2026-06-07 | 9 | 21 | 0 | 10
2026-06-08 | 9 | 21 | 0 | 10
2026-06-09 | 9 | 21 | 0 | 10
2026-06-10 | 9 | 21 | 0 | 10
2026-06-11 | 9 | 21 | 0 | 10
2026-06-12 | 9 | 21 | 0 | 10
2026-06-13 | 9 | 21 | 0 | 10
2026-06-14 | 9 | 21 | 0 | 10
2026-06-15 | 5 | 14 | 0 | 8
2026-06-16 | 5 | 14 | 0 | 8
2026-06-17 | 5 | 14 | 0 | 8
2026-06-18 | 5 | 14 | 0 | 8
2026-06-19 | 5 | 14 | 0 | 8
2026-06-20 | 5 | 14 | 0 | 8
2026-06-21 | 5 | 14 | 0 | 8
2026-06-22 | 5 | 12 | 0 | 8
2026-06-23 | 5 | 12 | 0 | 8
2026-06-24 | 5 | 12 | 0 | 8
2026-06-25 | 5 | 12 | 0 | 8
2026-06-26 | 5 | 12 | 0 | 8
2026-06-27 | 5 | 12 | 0 | 8
2026-06-28 | 5 | 12 | 0 | 8
2026-06-29 | 5 | 11 | 0 | 8
2026-06-30 | 1 | 2 | 0 | 8
2026-07-01 | 1 | 2 | 0 | 7
2026-07-02 | 1 | 1 | 0 | 8
2026-07-03 | 1 | 1 | 0 | 8
2026-07-04 | 1 | 1 | 0 | 8
2026-07-05 | 1 | 1 | 0 | 8
2026-07-06 | 1 | 1 | 0 | 8
2026-07-07 | 1 | 1 | 0 | 8
2026-07-08 | 1 | 1 | 0 | 8
2026-07-09 | 1 | 1 | 0 | 8
2026-07-10 | 1 | 1 | 0 | 8
2026-07-11 | 1 | 1 | 0 | 8
2026-07-12 | 1 | 1 | 0 | 8
2026-07-13 | 1 | 1 | 0 | 8
2026-07-14 | 1 | 2 | 0 | 8
2026-07-15 | 1 | 2 | 0 | 8
2026-07-16 | 1 | 9 | 0 | 8
2026-07-17 | 1 | 9 | 0 | 8
2026-07-18 | 1 | 9 | 0 | 8
2026-07-19 | 1 | 9 | 0 | 8
2026-07-20 | 1 | 9 | 0 | 8
2026-07-21 | 1 | 9 | 0 | 8
2026-07-22 | 1 | 9 | 0 | 8
2026-07-23 | 1 | 9 | 0 | 8
2026-07-24 | 1 | 9 | 0 | 8
2026-07-25 | 1 | 9 | 0 | 8
2026-07-26 | 1 | 9 | 0 | 8
2026-07-27 | 1 | 9 | 0 | 8
2026-07-28 | 1 | 9 | 0 | 8
2026-07-29 | 1 | 9 | 0 | 8
2026-07-30 | 1 | 9 | 0 | 8
2026-07-31 | 1 | 9 | 0 | 8
2026-08-01 | 1 | 9 | 0 | 8
2026-08-02 | 1 | 9 | 0 | 8
2026-08-03 | 1 | 9 | 0 | 8
2026-08-04 | 1 | 9 | 0 | 8
2026-08-05 | 1 | 9 | 0 | 8
2026-08-06 | 1 | 9 | 0 | 8
2026-08-07 | 1 | 9 | 0 | 8
2026-08-08 | 1 | 9 | 0 | 8
2026-08-09 | 1 | 9 | 0 | 8
2026-08-10 | 1 | 9 | 0 | 8
2026-08-11 | 1 | 9 | 0 | 8
2026-08-12 | 1 | 9 | 0 | 8
2026-08-13 | 1 | 9 | 0 | 8
2026-08-14 | 1 | 8 | 0 | 8
2026-08-15 | 1 | 8 | 0 | 8
2026-08-16 | 1 | 8 | 0 | 8
2026-08-17 | 1 | 8 | 0 | 8
2026-08-18 | 1 | 8 | 0 | 8
2026-08-19 | 1 | 8 | 0 | 8
2026-08-20 | 1 | 8 | 0 | 8
2026-08-21 | 1 | 8 | 0 | 8
2026-08-22 | 1 | 8 | 0 | 8
2026-08-23 | 1 | 8 | 0 | 8
2026-08-24 | 1 | 8 | 0 | 8
2026-08-25 | 1 | 8 | 0 | 8
2026-08-26 | 1 | 8 | 0 | 8
2026-08-27 | 1 | 8 | 0 | 8
2026-08-28 | 1 | 8 | 0 | 8
2026-08-29 | 1 | 8 | 0 | 8
2026-08-30 | 1 | 8 | 0 | 8
2026-08-31 | 1 | 6 | 0 | 8
2026-09-01 | 1 | 6 | 0 | 8
2026-09-02 | 1 | 6 | 0 | 8
2026-09-03 | 1 | 6 | 0 | 8
2026-09-04 | 1 | 6 | 0 | 8
2026-09-05 | 1 | 6 | 0 | 8
2026-09-06 | 1 | 6 | 0 | 8
2026-09-07 | 1 | 6 | 0 | 8
2026-09-08 | 1 | 6 | 0 | 8
2026-09-09 | 1 | 6 | 0 | 8
2026-09-10 | 1 | 6 | 0 | 8
2026-09-11 | 1 | 6 | 0 | 8
2026-09-12 | 1 | 6 | 0 | 8
2026-09-13 | 1 | 6 | 0 | 8
2026-09-14 | 1 | 6 | 0 | 8
2026-09-15 | 1 | 6 | 0 | 8
2026-09-16 | 1 | 6 | 0 | 8
2026-09-17 | 1 | 6 | 0 | 8
2026-09-18 | 1 | 6 | 0 | 8
2026-09-19 | 1 | 6 | 0 | 8
2026-09-20 | 1 | 6 | 0 | 8
2026-09-21 | 1 | 6 | 0 | 8
2026-09-22 | 1 | 6 | 0 | 8
2026-09-23 | 1 | 6 | 0 | 8
2026-09-24 | 1 | 6 | 0 | 8
2026-09-25 | 1 | 6 | 0 | 8
2026-09-26 | 1 | 6 | 0 | 8
2026-09-27 | 1 | 6 | 0 | 8
2026-09-28 | 1 | 6 | 0 | 8
2026-09-29 | 1 | 6 | 0 | 8
2026-09-30 | 1 | 0 | 0 | 5
2026-10-01 | 1 | 0 | 0 | 5
2026-10-02 | 1 | 0 | 0 | 5
2026-10-03 | 1 | 0 | 0 | 5
2026-10-04 | 1 | 0 | 0 | 5
2026-10-05 | 1 | 0 | 0 | 5
2026-10-06 | 1 | 0 | 0 | 5
2026-10-07 | 1 | 0 | 0 | 5
2026-10-08 | 1 | 0 | 0 | 5
2026-10-09 | 1 | 0 | 0 | 5
2026-10-10 | 1 | 0 | 0 | 5
2026-10-11 | 1 | 0 | 0 | 5
2026-10-12 | 1 | 0 | 0 | 5
2026-10-13 | 1 | 0 | 0 | 5
2026-10-14 | 1 | 0 | 0 | 5
2026-10-15 | 1 | 0 | 0 | 5
2026-10-16 | 1 | 3 | 0 | 5
2026-10-17 | 1 | 3 | 0 | 5
2026-10-18 | 1 | 3 | 0 | 5
2026-10-19 | 1 | 3 | 0 | 5
2026-10-20 | 1 | 3 | 0 | 5
2026-10-21 | 1 | 3 | 0 | 5
2026-10-22 | 1 | 3 | 0 | 5
2026-10-23 | 1 | 3 | 0 | 5
2026-10-24 | 1 | 3 | 0 | 5
2026-10-25 | 1 | 3 | 0 | 5
2026-10-26 | 1 | 3 | 0 | 5
2026-10-27 | 1 | 3 | 0 | 5
2026-10-28 | 1 | 3 | 0 | 5
2026-10-29 | 1 | 3 | 0 | 5
2026-10-30 | 1 | 3 | 0 | 5
2026-10-31 | 1 | 3 | 0 | 5
2026-11-01 | 1 | 3 | 0 | 5
2026-11-02 | 1 | 3 | 0 | 5
2026-11-03 | 1 | 3 | 0 | 5
2026-11-04 | 1 | 3 | 0 | 5
2026-11-05 | 1 | 3 | 0 | 5
2026-11-06 | 1 | 3 | 0 | 5
2026-11-07 | 1 | 3 | 0 | 5
2026-11-08 | 1 | 3 | 0 | 5
2026-11-09 | 1 | 3 | 0 | 5
2026-11-10 | 1 | 3 | 0 | 5
2026-11-11 | 1 | 3 | 0 | 5
2026-11-12 | 1 | 3 | 0 | 5
2026-11-13 | 1 | 3 | 0 | 5
2026-11-14 | 1 | 3 | 0 | 5
2026-11-15 | 1 | 3 | 0 | 5
2026-11-16 | 1 | 3 | 0 | 5
2026-11-17 | 1 | 3 | 0 | 5
2026-11-18 | 1 | 3 | 0 | 5
2026-11-19 | 1 | 3 | 0 | 5
2026-11-20 | 1 | 3 | 0 | 5
2026-11-21 | 1 | 3 | 0 | 5
2026-11-22 | 1 | 3 | 0 | 5
2026-11-23 | 1 | 3 | 0 | 5
2026-11-24 | 1 | 3 | 0 | 5
2026-11-25 | 1 | 3 | 0 | 5
2026-11-26 | 1 | 3 | 0 | 5
2026-11-27 | 1 | 3 | 0 | 5
2026-11-28 | 1 | 3 | 0 | 5
2026-11-29 | 1 | 3 | 0 | 5
2026-11-30 | 1 | 3 | 0 | 3
2026-12-01 | 1 | 3 | 0 | 3
2026-12-02 | 1 | 3 | 0 | 3
2026-12-03 | 1 | 3 | 0 | 3
2026-12-04 | 1 | 3 | 0 | 3
2026-12-05 | 1 | 3 | 0 | 3
2026-12-06 | 1 | 3 | 0 | 3
2026-12-07 | 1 | 3 | 0 | 3
2026-12-08 | 1 | 3 | 0 | 3
2026-12-09 | 1 | 3 | 0 | 3
2026-12-10 | 1 | 3 | 0 | 3
2026-12-11 | 1 | 3 | 0 | 3
2026-12-12 | 1 | 3 | 0 | 3
2026-12-13 | 1 | 3 | 0 | 3
2026-12-14 | 1 | 3 | 0 | 3
2026-12-15 | 1 | 3 | 0 | 3
2026-12-16 | 1 | 3 | 0 | 3
2026-12-17 | 1 | 3 | 0 | 3
2026-12-18 | 1 | 3 | 0 | 3
2026-12-19 | 1 | 3 | 0 | 3
2026-12-20 | 1 | 3 | 0 | 3
2026-12-21 | 1 | 3 | 0 | 3
2026-12-22 | 1 | 3 | 0 | 3
2026-12-23 | 1 | 0 | 0 | 3
2026-12-24 | 1 | 0 | 0 | 3
2026-12-25 | 1 | 0 | 0 | 3
2026-12-26 | 1 | 0 | 0 | 3
2026-12-27 | 1 | 0 | 0 | 3
2026-12-28 | 1 | 0 | 0 | 3
2026-12-29 | 1 | 0 | 0 | 3
2026-12-30 | 1 | 0 | 0 | 3
2026-12-31 | 1 | 0 | 0 | 0
2027-01-01 | 1 | 0 | 0 | 0

## Task_table_03_26 (hidden)
Initiative | Process | Phase | Process level | Process Group | % Arbeit abgeschlossen | IT Process Consultant | IT Process Initiative Lead | IT Process Manager | Anfang | Ende | Dauer2 | Process Approval Date | Actual Phase | Planned phase | Associated Process on L1 | 📌 Analyse
Corporate IT body | Manage IT strategy | Total | L1 | MP | 50% |  |  |  | 46055 | 46232 | 128 | Mit 06.05.26 |  | 1 | Manage IT strategy | Prozesse in Elaboration | 39
Corporate IT body | Manage IT strategy | Elaboration | L1 | MP | 50% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 46055 | 46142 | 64 | NV | Elaboration in progress | Elaboration in progress | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LIS | L1 | MP | 0% |  |  |  | 46156 | 46232 | 55 | NV |  | Scheduled | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT strategy
Corporate IT body | Manage IT governance framework | Total | L1 | MP | 50% |  |  |  | 46029 | 46265 | 169 | NV |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Elaboration | L1 | MP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 46097 | 46163 | 49 | NV | Elaboration in progress | Elaboration in progress | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LIS | L1 | MP | 0% |  |  |  | 46167 | 46265 | 71 | NV |  | Scheduled | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Total | L2 | MP | 25% |  |  |  | 46029 | 46039 | 8 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Elaboration | L2 | MP | 25% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 46029 | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LIS | L2 | MP | 0% |  |  |  | 46029 | 46039 | 7 | NV | Delayed | Implementation LIS Done | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation COT | L2 | MP | 0% |  |  |  | 46029 | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Manage enterprise architecture | Total | L1 | MP | 24% |  |  |  | 45946 | 46219 | 195.85 | NV |  |  | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Elaboration | L1 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 46076 | 46150 | 54.85 | NV | Delayed | Elaboration in progress | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LIS | L1 | MP | 0% |  |  |  | 46150 | 46219 | 49 | NV |  | Scheduled | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation COT | L1 | MP | 0% |  |  |  | 46150 | 46153 | 1 | NV |  | Scheduled | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LUS | L1 | MP | 0% |  |  |  | 46150 | 46153 | 1 | NV |  | Scheduled | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Total | L2 | MP | 50% |  |  |  | 45946 | 46142 | 141 | NV |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Elaboration | L2 | MP | 50% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 46076 | 46142 | 49 | NV | Elaboration in progress | Elaboration in progress | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage enterprise architecture
ITSM | Manage IT portfolio | Total | L1 | MP | 69% |  |  |  | 45971 | 46157 | 135 | NV |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Elaboration | L1 | MP | 100% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) |  |  | 45972 | 46051 | 58 | NV | Elaboration Done | Elaboration Done | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LIS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Total | L2 | MP | 100% |  |  |  | 45971 | 46173 | 145 | NV |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Elaboration | L2 | MP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45971 | 46001 | 23 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 46054 | 46173 | 85 | NV | Delayed | Implementation LIS | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Total | L2 | MP | 0% |  |  |  | 46113 | 46273 | 115 | NV |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Elaboration | L2 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Ceilia Roser (LIS) | Reiner Heiko (HAU-ITSA) | 46113 | 46155 | 31 | NV |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 46188 | 46273 | 62 | NV |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
IT planning and steering | Manage and control IT financials | Total | L1 | MP | 50% |  |  | Moser Mario (LIS-LAH) | 45945 | 46234 | 208 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Elaboration | L1 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | 46142 | 142 | NV | Elaboration in progress | Elaboration in progress | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LIS | L1 | MP | 0% |  |  |  | 46143 | 46234 | 66 | NV |  | Scheduled | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Total | L2 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  | 18 | Manage and control IT financials
IT planning and steering | Review budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Total | L2 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Total | L2 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation COT |  | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Total | L2 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Total | L3 | MP | 50% |  |  |  | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 45945 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
Corporate IT body | Manage IT stakeholder relationships | Total | L1 | MP | 0% |  |  |  | 46113 | 46379 | 191 | NV |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Elaboration | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 46113 | 46188 | 54 | NV |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LIS | L1 | MP | 0% |  |  |  | 46310 | 46379 | 50 | NV |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT stakeholder relationships
ITSM | Manage IT processes and continuous improvement | Total | L1 | MP | 21% |  |  |  | 45931 | 46173 | 173 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Elaboration | L1 | MP | 100% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 45931 | 45931 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LIS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Total | L2 | MP | 100% |  |  |  | 45945 | 45946 | 1 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Elaboration | L2 | MP | 100% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 45873 | 45899 | 20 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Total | L2 | MP | 0% |  |  |  | 45931 | 46052 | 88 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | 45931 | 46052 | 88 | NV | Delayed | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Total | L3 | MP | 0% |  |  |  | ? | 45946 | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Elaboration | L3 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Total | L3 | MP | 0% |  |  |  | ? | 45946 | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Elaboration | L3 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Total | L2 | MP | 25% |  |  |  | 45931 | 46173 | 173 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Perform operational process management (V 2.0) | Elaboration | L2 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 46034 | 46173 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Total | L3 | MP | 25% |  |  |  | 46034 | 46173 | 100 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Identify process and determine goals (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 46034 | 46173 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Total | L3 | MP | 25% |  |  |  | 46034 | 46173 | 100 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Elaborate to-be process (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 46034 | 46173 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Total | L3 | MP | 25% |  |  |  | 46034 | 46173 | 100 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Plan process execution (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 46034 | 46173 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Total | L3 | MP | 25% |  |  |  | 46034 | 46173 | 100 | Fre 19.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Implement process (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 46034 | 46173 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Total | L3 | MP | 100% |  |  |  | 45931 | 45931 | 1 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Perform and measure process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 45931 | 45931 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Total | L3 | MP | 100% |  |  |  | 45931 | 45931 | 1 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Analyse process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 45931 | 45931 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
Central area (Jan Müskens) | Manage IT risks and compliance | Total | L1 | MP | 19% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Elaboration | L1 | MP | 100% | Kreis Andreas (LLI);Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 45931 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LIS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Total | L2 | MP | 0% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Moser Mario (LIS-LAH) |  | Monnier Murielle (LEC) | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Total | L2 | MP | 25% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Elaboration | L2 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 46295 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Total | L3 | MP | 25% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 46295 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Total | L3 | MP | 25% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 46295 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Total | L3 | MP | 25% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 46295 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Total | L3 | MP | 25% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 46295 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Total | L3 | MP | 25% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 46295 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Total | L3 | MP | 25% |  |  |  | 45931 | 46295 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 45931 | 46295 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Corporate IT body | Plan IT service | Total | L1 | CP | 100% |  |  |  | 45870 | 46142 | 195 | NV |  |  | Plan IT service
Corporate IT body | Plan IT service | Elaboration | L1 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 45946 | 45961 | 12 | Mit 10.12.25 | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Plan IT service | Implementation LIS | L1 | CP | 75% |  |  |  | 45962 | 46081 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Plan IT service | Implementation COT | L1 | CP | 0% |  |  |  | 45964 | 46112 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Plan IT service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Total | L2 | CP | 100% |  |  |  | 45870 | 45874 | 3 | Die 19.08.25 |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 45870 | 45870 | 1 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LIS | L2 | CP | 0% |  |  |  | 45962 | 46081 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation COT | L2 | CP | 0% |  |  |  | 45964 | 46112 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Total | L2 | CP | 100% |  |  |  | 45870 | 46142 | 195 | Mit 10.12.25 |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 45870 | 45870 | 1 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LIS | L2 | CP | 0% |  |  |  | 45962 | 46081 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation COT | L2 | CP | 0% |  |  |  | 45964 | 46112 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Total | L3 | CP | 100% |  |  |  | 45870 | 46142 | 195 | NV |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Elaboration | L3 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 45870 | 45945 | 54 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation COT | L3 | CP | 0% |  |  |  | 45946 | 46142 | 141 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Approve IT demand | Total | L2 | CP | 100% |  |  |  | 45870 | 45870 | 1 | Die 19.08.25 |  |  | Plan IT service
Corporate IT body | Approve IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 45870 | 45870 | 1 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Approve IT demand | Implementation LIS | L2 | CP | 0% |  |  |  | 45962 | 46081 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Approve IT demand | Implementation COT | L2 | CP | 0% |  |  |  | 45964 | 46112 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Approve IT demand | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
ITSM | Build IT Service | Total | L1 | CP | 41% |  |  |  | 45748 | 46265 | 370 | NV |  |  | Build IT Service
ITSM | Build IT Service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Build IT Service | Implementation LIS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Build IT Service | Implementation COT | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Build IT Service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Design IT service | Total | L2 | CP | 50% |  |  |  | 45931 | 46248 | 228 | NV |  |  | Build IT Service
ITSM | Design IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 46069 | 46157 | 65 | NV | Delayed | Elaboration in progress | Build IT Service
ITSM | Design IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 46160 | 46248 | 65 | NV |  | Scheduled | Build IT Service
ITSM | Design IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Design IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
Architecture management | Define solution target architecture | Total | L3 | CP | 50% |  |  |  | 46036 | 46195 | 114 | NV |  |  | Build IT Service
Architecture management | Define solution target architecture | Elaboration | L3 | CP | 50% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) | 46058 | 46133 | 54 | NV | Elaboration in progress | Elaboration in progress | Build IT Service
Architecture management | Define solution target architecture | Implementation LIS | L3 | CP | 0% |  |  |  | 46134 | 46195 | 44 | NV |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation COT | L3 | CP | 0% |  |  |  | 46134 | 46134 | 1 | NV |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation LUS | L3 | CP | 0% |  |  |  | 46036 | 46036 | 0 | NV | Delayed | Implementation LUS Done | Build IT Service
ITSM | Develop and customise IT service | Total | L2 | CP | 0% |  |  |  | 45803 | 46157 | 255 | NV |  |  | Build IT Service
ITSM | Develop and customise IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 46069 | 46157 | 65 | NV | Delayed | Elaboration in progress | Build IT Service
ITSM | Develop and customise IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 45803 | 45884 | 60 | NV | Delayed | Implementation LIS Done | Build IT Service
ITSM | Develop and customise IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Develop and customise IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Deploy IT service | Total | L2 | CP | 0% |  |  |  | 46127 | 46265 | 99 | NV |  |  | Build IT Service
ITSM | Deploy IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 46127 | 46188 | 44 | NV |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 46218 | 46265 | 34 | NV |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Deploy IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
| Test and validate IT service | Total | L2 | CP | 0% |  |  |  | 46127 | 46265 | 99 | NV |  |  | Build IT Service
ITSM | Test and validate IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 46127 | 46188 | 44 | NV |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 46218 | 46265 | 34 | NV |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Test and validate IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Total | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LIS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manage IT service change | Total | L2 | CP | 100% |  |  |  | 46034 | 46203 | 122 | Mit 15.04.26 |  |  | Build IT Service
ITSM | Manag IT service change | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 46034 | 46099 | 48 | Mit 15.04.26 | Elaboration Done | Elaboration Done | Build IT Service
ITSM | Manag IT service change | Implementation LIS | L2 | CP | 0% |  |  |  | 46127 | 46203 | 55 | NV |  | Scheduled | Build IT Service
ITSM | Manag IT service change | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manag IT service change | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manage IT service release | Total | L2 | CP | 50% |  |  |  | 46073 | 46203 | 93 | NV |  |  | Build IT Service
ITSM | Manage IT service release | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 46073 | 46150 | 56 | NV | Elaboration in progress | Elaboration in progress | Build IT Service
ITSM | Manage IT service release | Implementation LIS | L2 | CP | 0% |  |  |  | 46127 | 46203 | 55 | NV |  | Scheduled | Build IT Service
ITSM | Manage IT service release | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manage IT service release | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Deliver IT service | Total | L1 | CP | 0% |  |  |  | 46113 | 46190 | 56 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Elaboration | L1 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LIS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation COT | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Manage IT service provision request | Total | L2 | CP | 0% |  |  |  | 46113 | 46190 | 56 | NV |  |  | Deliver IT service
ITSM | Manage IT service provision request | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | 46113 | 46190 | 56 | NV |  | Scheduled | Deliver IT service
ITSM | Manage IT service provision request | Implementation LIS | L2 | CP | 0% |  |  |  | 46113 | 46188 | 54 | NV |  | Scheduled | Deliver IT service
ITSM | Manage IT service provision request | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Manage IT service provision request | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Handle IT service order | Total | L2 | CP | 0% |  |  |  | 46113 | 46190 | 56 | NV |  |  | Deliver IT service
ITSM | Handle IT service order | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | 46113 | 46190 | 56 | NV |  | Scheduled | Deliver IT service
ITSM | Handle IT service order | Implementation LIS | L2 | CP | 0% |  |  |  | 46113 | 46188 | 54 | NV |  | Scheduled | Deliver IT service
ITSM | Handle IT service order | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Handle IT service order | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Run IT service | Total | L1 | CP | 17% |  |  |  | 45945 | 46290 | 248 | NV |  |  | Run IT service
ITSM | Run IT service | Elaboration | L1 | CP | 0% | Schroeder Michael (LIS);Böhme Matthias (ext.) | Oey Kai (LIS) | Sint Rachel (LBH) | 45946 | 46203 | 184 | NV | Delayed | Elaboration in progress | Run IT service
ITSM | Run IT service | Implementation LIS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Run IT service | Implementation COT | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Run IT service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Total | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation LIS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service performance | Total | L2 | CP | 0% |  |  |  | 46127 | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation LIS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Operate and maintain IT service | Total | L2 | CP | 21% |  |  |  | 45945 | 46203 | 185 | NV |  |  | Run IT service
ITSM | Operate and maintain IT service | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 46034 | 46203 | 122 | NV | Delayed | Elaboration in progress | Run IT service
ITSM | Operate and maintain IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 46127 | 46203 | 55 | NV |  | Scheduled | Run IT service
ITSM | Operate and maintain IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Operate and maintain IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Total | L3 | CP | 50% |  |  |  | 46036 | 46162 | 91 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Elaboration | L3 | CP | 50% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 46036 | 46162 | 91 | NV | Elaboration in progress | Elaboration in progress | Run IT service
ITSM | Maintain CMDB | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Total | L3 | CP | 0% |  |  |  | 46127 | 46203 | 55 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Provide IT service support | Total | L2 | CP | 57% |  |  |  | 45946 | 46188 | 173 | NV |  |  | Run IT service
ITSM | Provide IT service support | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 46034 | 46111 | 56 | NV | Delayed | Elaboration in progress | Run IT service
ITSM | Provide IT service support | Implementation LIS | L2 | CP | 0% |  |  |  | 46113 | 46188 | 54 | NV |  | Scheduled | Run IT service
ITSM | Provide IT service support | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Provide IT service support | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT Incident | Total | L3 | CP | 75% |  |  |  | 46035 | 46100 | 48 | Don 19.03.26 |  |  | Run IT service
ITSM | Handle IT Incident | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 46035 | 46100 | 48 | Don 19.03.26 | Elaboration in progress | Elaboration Done | Run IT service
ITSM | Handle IT Incident | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT Incident | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT Incident | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT problem | Total | L3 | CP | 75% |  |  |  | 46035 | 46100 | 48 | Don 19.03.26 |  |  | Run IT service
ITSM | Handle IT problem | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 46035 | 46100 | 48 | Don 19.03.26 | Elaboration in progress | Elaboration Done | Run IT service
ITSM | Handle IT problem | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT problem | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT problem | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT service request | Total | L3 | CP | 100% |  |  |  | 46055 | 46100 | 34 | Don 19.03.26 |  |  | Run IT service
ITSM | Handle IT service request | Elaboration | L3 | CP | 100% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 46055 | 46100 | 34 | Don 19.03.26 | Elaboration Done | Elaboration Done | Run IT service
ITSM | Handle IT service request | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT service request | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT service request | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
Information security | Ensure Information security | Total | L1 | SP | 50% |  |  |  | 45946 | 45946 | 1 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Elaboration | L1 | SP | 50% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | 45946 | ? | 0 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Total | L2 | SP | 50% |  |  |  | 45946 | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Elaboration | L2 | SP | 50% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | 45949 | 46142 | 139 | NV | Elaboration in progress | Elaboration in progress | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
IT project management | Manage IT project | Total | L1 | SP | 100% |  |  |  | 45852 | 46001 | 108 | Don 18.09.25 |  |  | Manage IT project
IT project management | Manage IT project | Elaboration | L1 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45972 | 46001 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Manage IT project | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Initiate IT project | Total | L2 | SP | 100% |  |  |  | 45852 | 45852 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Initiate IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45972 | 46001 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Initiate IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Initiate IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Initiate IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Plan IT project | Total | L2 | SP | 100% |  |  |  | 45852 | 45852 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Plan IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45972 | 46001 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Plan IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Plan IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Plan IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Steer and execute IT project | Total | L2 | SP | 100% |  |  |  | 45852 | 45852 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Steer and execute IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45972 | 46001 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Steer and execute IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Steer and execute IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Steer and execute IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Close IT project | Total | L2 | SP | 100% |  |  |  | 45852 | 45852 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Close IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45972 | 46001 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Close IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Close IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Close IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project change request | Total | L2 | SP | 100% |  |  |  | 45852 | 45852 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Manage IT project change request | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45972 | 46001 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Manage IT project change request | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Assign personnel resources to IT project | Total | L2 | SP | 100% |  |  |  | 45852 | 45852 | 1 | NV |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 45972 | 46001 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
ITSM | Manage IT sourcing and procurement | Total | L1 | SP | 0% |  |  |  | 46132 | 46295 | 118 | NV |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS);Schoeberl Lorena (LBH) | tbd | Monnier Murielle (LEC) | 46132 | 46203 | 52 | NV |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LIS | L1 | SP | 0% |  |  |  | 46216 | 46295 | 58 | NV |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT sourcing and procurement
HR initiatives for IT | Provide and develop IT workforce | Total | L1 | SP | 4% |  |  |  | 45931 | 46568 | 456 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Elaboration | L1 | SP | 100% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 45931 | 45931 | 1 | NV | Elaboration Done | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
| Manage HR4IT strategy, governane and framework |  | L2 |  | 0% |  |  |  | 45931 | 46387 | 327 | NV
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Elaboration | L2 | SP | 100% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 45931 | 45931 | 1 | NV | Elaboration Done | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Total | L3 | SP | 0% |  |  |  | 45946 | 46387 | 316 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 45946 | 46022 | 55 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LIS | L3 | SP | 0% |  |  |  | 46023 | 46387 | 261 | NV | Delayed | Implementation LIS | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Total | L3 | SP | 0% |  |  |  | 45946 | 46173 | 162 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 45946 | 46173 | 162 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand |  | L3 | SP | 0% |  |  |  | 45931 | 46203 | 195 | NV
HR initiatives for IT | Manage HR4IT service demand | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 45931 | 46173 | 173 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand | Implementation LIS | L3 | SP | 0% |  |  |  | 46174 | 46203 | 22 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand | Implementation COT | L3 | SP | 0% |  |  |  | 46174 | 46203 | 22 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand | Implementation LUS | L3 | SP | 0% |  |  |  | 46174 | 46203 | 22 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Total | L2 | SP | 0% |  |  |  | 45931 | 46387 | 327 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Elaboration | L2 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 46029 | 46097 | 49 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Implementation LIS | L2 | SP | 0% |  |  |  | 46113 | 46188 | 54 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Implementation COT | L2 | SP | 0% |  |  |  | 46113 | 46188 | 54 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing |  | L3 | SP | 0% |  |  |  | 45931 | 46387 | 327 | NV
HR initiatives for IT | Perform active sourcing | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 45931 | 46081 | 108 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing | Implementation LIS | L3 | SP | 0% |  |  |  | 46082 | 46387 | 219 | NV | Delayed | Implementation LIS | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers |  | L3 | SP | 0% |  |  |  | 45931 | 46387 | 327 | NV
HR initiatives for IT | Recruit employees and managers | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 45931 | 46081 | 108 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers | Implementation LIS | L3 | SP | 0% |  |  |  | 46082 | 46387 | 219 | NV | Delayed | Implementation LIS | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Total | L2 | SP | 0% |  |  |  | 45946 | 45946 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Elaboration | L2 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Total | L3 | SP | 0% |  |  |  | 45946 | 45946 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Total | L3 | SP | 0% |  |  |  | 45946 | 45946 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Total | L2 | SP | 10% |  |  |  | 45931 | 46568 | 456 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Elaboration | L2 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue |  | L3 | SP | 50% |  |  |  | 45931 | 46094 | 118 | NV
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Elaboration | L3 | SP | 50% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 45931 | 46094 | 118 | NV | Elaboration in progress | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Total | L3 | SP | 0% |  |  |  | 46112 | 46203 | 66 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 46112 | 46112 | 1 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Implementation LIS | L3 | SP | 0% |  |  |  | 46113 | 46203 | 65 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Implementation COT | L3 | SP | 0% |  |  |  | 46113 | 46203 | 65 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Implementation LUS | L3 | SP | 0% |  |  |  | 46113 | 46203 | 65 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Total | L3 | SP | 0% |  |  |  | 45946 | 45946 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Total | L3 | SP | 0% |  |  |  | 46023 | 46568 | 390 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 46023 | 46387 | 261 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LIS | L3 | SP | 0% |  |  |  | 46388 | 46568 | 129 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation COT | L3 | SP | 0% |  |  |  | 46388 | 46568 | 129 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LUS | L3 | SP | 0% |  |  |  | 46388 | 46568 | 129 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent pool and identify potential | Total | L3 | SP | 0% |  |  |  | 45946 | 45946 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Total | L3 | SP | 0% |  |  |  | 46037 | 46204 | 120 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 46037 | 46112 | 54 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LIS | L3 | SP | 0% |  |  |  | 46113 | 46204 | 66 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation COT | L3 | SP | 0% |  |  |  | 46113 | 46204 | 66 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LUS | L3 | SP | 0% |  |  |  | 46113 | 46204 | 66 | NV |  | Scheduled | Provide and develop IT workforce
ITSM | Ensure performance and conformance of IT services | Total | L1 | SP | 0% |  |  |  | 46127 | 46203 | 55 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Elaboration | L1 | SP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) | Sint Rachel (LBH) | 46127 | 46203 | 55 | NV |  | Scheduled | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Manage IT knowledge | Total | L1 | SP | 75% |  |  |  | 46042 | 46203 | 116 | Don 19.03.26 |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Elaboration | L1 | SP | 75% | Schroeder Michael (LIS) | Kürschner Philipp (LIS) | Sint Rachel (LBH) | 46042 | 46078 | 27 | NV | Elaboration in progress | Elaboration Done | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LIS | L1 | SP | 0% |  |  |  | 46127 | 46203 | 55 | NV |  | Scheduled | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT knowledge
ITSM | Leverage IT innovation | Total | L1 | SP | 0% |  |  |  | 45946 | 45946 | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Leverage IT innovtion

## Date_table_03_26 (hidden)
Datum | Elaboration | Implementation LIS | Implementation LUS | Implementation COT
2025-08-01 | 0 | 1 | 0 | 0
2025-08-02 | 1 | 1 | 0 | 0
2025-08-03 | 1 | 1 | 0 | 0
2025-08-04 | 1 | 1 | 0 | 0
2025-08-05 | 2 | 1 | 0 | 0
2025-08-06 | 2 | 1 | 0 | 0
2025-08-07 | 2 | 1 | 0 | 0
2025-08-08 | 2 | 1 | 0 | 0
2025-08-09 | 2 | 1 | 0 | 0
2025-08-10 | 2 | 1 | 0 | 0
2025-08-11 | 2 | 1 | 0 | 0
2025-08-12 | 2 | 1 | 0 | 0
2025-08-13 | 2 | 1 | 0 | 0
2025-08-14 | 2 | 1 | 0 | 0
2025-08-15 | 2 | 0 | 0 | 0
2025-08-16 | 2 | 0 | 0 | 0
2025-08-17 | 2 | 0 | 0 | 0
2025-08-18 | 2 | 0 | 0 | 0
2025-08-19 | 2 | 0 | 0 | 0
2025-08-20 | 2 | 0 | 0 | 0
2025-08-21 | 2 | 0 | 0 | 0
2025-08-22 | 2 | 0 | 0 | 0
2025-08-23 | 2 | 0 | 0 | 0
2025-08-24 | 2 | 0 | 0 | 0
2025-08-25 | 2 | 0 | 0 | 0
2025-08-26 | 2 | 0 | 0 | 0
2025-08-27 | 2 | 0 | 0 | 0
2025-08-28 | 2 | 0 | 0 | 0
2025-08-29 | 2 | 0 | 0 | 0
2025-08-30 | 1 | 0 | 0 | 0
2025-08-31 | 1 | 0 | 0 | 0
2025-09-01 | 1 | 0 | 0 | 0
2025-09-02 | 1 | 0 | 0 | 0
2025-09-03 | 1 | 0 | 0 | 0
2025-09-04 | 1 | 0 | 0 | 0
2025-09-05 | 1 | 0 | 0 | 0
2025-09-06 | 1 | 0 | 0 | 0
2025-09-07 | 1 | 0 | 0 | 0
2025-09-08 | 1 | 0 | 0 | 0
2025-09-09 | 1 | 0 | 0 | 0
2025-09-10 | 1 | 0 | 0 | 0
2025-09-11 | 1 | 0 | 0 | 0
2025-09-12 | 1 | 0 | 0 | 0
2025-09-13 | 1 | 0 | 0 | 0
2025-09-14 | 1 | 0 | 0 | 0
2025-09-15 | 1 | 0 | 0 | 0
2025-09-16 | 1 | 0 | 0 | 0
2025-09-17 | 1 | 0 | 0 | 0
2025-09-18 | 1 | 0 | 0 | 0
2025-09-19 | 1 | 0 | 0 | 0
2025-09-20 | 1 | 0 | 0 | 0
2025-09-21 | 1 | 0 | 0 | 0
2025-09-22 | 1 | 0 | 0 | 0
2025-09-23 | 1 | 0 | 0 | 0
2025-09-24 | 1 | 0 | 0 | 0
2025-09-25 | 1 | 0 | 0 | 0
2025-09-26 | 1 | 0 | 0 | 0
2025-09-27 | 1 | 0 | 0 | 0
2025-09-28 | 1 | 0 | 0 | 0
2025-09-29 | 1 | 0 | 0 | 0
2025-09-30 | 1 | 0 | 0 | 0
2025-10-01 | 1 | 0 | 0 | 0
2025-10-02 | 13 | 0 | 0 | 0
2025-10-03 | 13 | 0 | 0 | 0
2025-10-04 | 13 | 0 | 0 | 0
2025-10-05 | 13 | 0 | 0 | 0
2025-10-06 | 13 | 0 | 0 | 0
2025-10-07 | 13 | 0 | 0 | 0
2025-10-08 | 13 | 0 | 0 | 0
2025-10-09 | 13 | 0 | 0 | 0
2025-10-10 | 13 | 0 | 0 | 0
2025-10-11 | 13 | 0 | 0 | 0
2025-10-12 | 13 | 0 | 0 | 0
2025-10-13 | 13 | 0 | 0 | 0
2025-10-14 | 13 | 0 | 0 | 0
2025-10-15 | 12 | 0 | 0 | 0
2025-10-16 | 33 | 0 | 0 | 0
2025-10-17 | 38 | 0 | 0 | 1
2025-10-18 | 38 | 0 | 0 | 1
2025-10-19 | 38 | 0 | 0 | 1
2025-10-20 | 39 | 0 | 0 | 1
2025-10-21 | 39 | 0 | 0 | 1
2025-10-22 | 39 | 0 | 0 | 1
2025-10-23 | 39 | 0 | 0 | 1
2025-10-24 | 39 | 0 | 0 | 1
2025-10-25 | 39 | 0 | 0 | 1
2025-10-26 | 39 | 0 | 0 | 1
2025-10-27 | 39 | 0 | 0 | 1
2025-10-28 | 39 | 0 | 0 | 1
2025-10-29 | 39 | 0 | 0 | 1
2025-10-30 | 39 | 0 | 0 | 1
2025-10-31 | 38 | 0 | 0 | 1
2025-11-01 | 38 | 0 | 0 | 1
2025-11-02 | 38 | 4 | 0 | 1
2025-11-03 | 38 | 4 | 0 | 1
2025-11-04 | 38 | 4 | 0 | 5
2025-11-05 | 38 | 4 | 0 | 5
2025-11-06 | 38 | 4 | 0 | 5
2025-11-07 | 38 | 4 | 0 | 5
2025-11-08 | 38 | 4 | 0 | 5
2025-11-09 | 38 | 4 | 0 | 5
2025-11-10 | 38 | 4 | 0 | 5
2025-11-11 | 39 | 4 | 0 | 5
2025-11-12 | 47 | 4 | 0 | 5
2025-11-13 | 47 | 4 | 0 | 5
2025-11-14 | 47 | 4 | 0 | 5
2025-11-15 | 47 | 4 | 0 | 5
2025-11-16 | 47 | 4 | 0 | 5
2025-11-17 | 47 | 4 | 0 | 5
2025-11-18 | 47 | 4 | 0 | 5
2025-11-19 | 47 | 4 | 0 | 5
2025-11-20 | 47 | 4 | 0 | 5
2025-11-21 | 47 | 4 | 0 | 5
2025-11-22 | 47 | 4 | 0 | 5
2025-11-23 | 47 | 4 | 0 | 5
2025-11-24 | 47 | 4 | 0 | 5
2025-11-25 | 47 | 4 | 0 | 5
2025-11-26 | 47 | 4 | 0 | 5
2025-11-27 | 47 | 4 | 0 | 5
2025-11-28 | 47 | 4 | 0 | 5
2025-11-29 | 47 | 4 | 0 | 5
2025-11-30 | 47 | 4 | 0 | 5
2025-12-01 | 47 | 4 | 0 | 5
2025-12-02 | 47 | 4 | 0 | 5
2025-12-03 | 47 | 4 | 0 | 5
2025-12-04 | 47 | 4 | 0 | 5
2025-12-05 | 47 | 4 | 0 | 5
2025-12-06 | 47 | 4 | 0 | 5
2025-12-07 | 47 | 4 | 0 | 5
2025-12-08 | 47 | 4 | 0 | 5
2025-12-09 | 47 | 4 | 0 | 5
2025-12-10 | 39 | 4 | 0 | 5
2025-12-11 | 39 | 4 | 0 | 5
2025-12-12 | 39 | 4 | 0 | 5
2025-12-13 | 39 | 4 | 0 | 5
2025-12-14 | 39 | 4 | 0 | 5
2025-12-15 | 39 | 4 | 0 | 5
2025-12-16 | 39 | 4 | 0 | 5
2025-12-17 | 39 | 4 | 0 | 5
2025-12-18 | 39 | 4 | 0 | 5
2025-12-19 | 39 | 4 | 0 | 5
2025-12-20 | 39 | 4 | 0 | 5
2025-12-21 | 39 | 4 | 0 | 5
2025-12-22 | 39 | 4 | 0 | 5
2025-12-23 | 39 | 4 | 0 | 5
2025-12-24 | 39 | 4 | 0 | 5
2025-12-25 | 39 | 4 | 0 | 5
2025-12-26 | 39 | 4 | 0 | 5
2025-12-27 | 39 | 4 | 0 | 5
2025-12-28 | 39 | 4 | 0 | 5
2025-12-29 | 39 | 4 | 0 | 5
2025-12-30 | 39 | 4 | 0 | 5
2025-12-31 | 38 | 4 | 0 | 5
2026-01-01 | 38 | 4 | 0 | 5
2026-01-02 | 39 | 5 | 0 | 5
2026-01-03 | 39 | 5 | 0 | 5
2026-01-04 | 39 | 5 | 0 | 5
2026-01-05 | 39 | 5 | 0 | 5
2026-01-06 | 39 | 5 | 0 | 5
2026-01-07 | 39 | 5 | 0 | 5
2026-01-08 | 41 | 6 | 0 | 6
2026-01-09 | 41 | 6 | 0 | 6
2026-01-10 | 41 | 6 | 0 | 6
2026-01-11 | 41 | 6 | 0 | 6
2026-01-12 | 41 | 6 | 0 | 6
2026-01-13 | 49 | 6 | 0 | 6
2026-01-14 | 51 | 6 | 0 | 6
2026-01-15 | 52 | 6 | 0 | 6
2026-01-16 | 53 | 6 | 0 | 6
2026-01-17 | 53 | 5 | 0 | 6
2026-01-18 | 53 | 5 | 0 | 6
2026-01-19 | 53 | 5 | 0 | 6
2026-01-20 | 53 | 5 | 0 | 6
2026-01-21 | 54 | 5 | 0 | 6
2026-01-22 | 54 | 5 | 0 | 6
2026-01-23 | 54 | 5 | 0 | 6
2026-01-24 | 54 | 5 | 0 | 6
2026-01-25 | 54 | 5 | 0 | 6
2026-01-26 | 54 | 5 | 0 | 6
2026-01-27 | 54 | 5 | 0 | 6
2026-01-28 | 54 | 5 | 0 | 6
2026-01-29 | 53 | 5 | 0 | 6
2026-01-30 | 52 | 5 | 0 | 6
2026-01-31 | 52 | 5 | 0 | 6
2026-02-01 | 52 | 5 | 0 | 6
2026-02-02 | 52 | 6 | 0 | 6
2026-02-03 | 54 | 6 | 0 | 6
2026-02-04 | 54 | 6 | 0 | 6
2026-02-05 | 54 | 6 | 0 | 6
2026-02-06 | 55 | 6 | 0 | 6
2026-02-07 | 55 | 6 | 0 | 6
2026-02-08 | 55 | 6 | 0 | 6
2026-02-09 | 55 | 6 | 0 | 6
2026-02-10 | 55 | 6 | 0 | 6
2026-02-11 | 55 | 6 | 0 | 6
2026-02-12 | 55 | 6 | 0 | 6
2026-02-13 | 55 | 6 | 0 | 6
2026-02-14 | 55 | 6 | 0 | 6
2026-02-15 | 55 | 6 | 0 | 6
2026-02-16 | 55 | 6 | 0 | 6
2026-02-17 | 57 | 6 | 0 | 6
2026-02-18 | 57 | 6 | 0 | 6
2026-02-19 | 57 | 6 | 0 | 6
2026-02-20 | 57 | 6 | 0 | 6
2026-02-21 | 58 | 6 | 0 | 6
2026-02-22 | 58 | 6 | 0 | 6
2026-02-23 | 58 | 6 | 0 | 6
2026-02-24 | 60 | 6 | 0 | 6
2026-02-25 | 59 | 6 | 0 | 6
2026-02-26 | 59 | 6 | 0 | 6
2026-02-27 | 59 | 6 | 0 | 6
2026-02-28 | 57 | 2 | 0 | 6
2026-03-01 | 57 | 2 | 0 | 6
2026-03-02 | 57 | 4 | 0 | 6
2026-03-03 | 57 | 4 | 0 | 6
2026-03-04 | 57 | 4 | 0 | 6
2026-03-05 | 57 | 4 | 0 | 6
2026-03-06 | 57 | 4 | 0 | 6
2026-03-07 | 57 | 4 | 0 | 6
2026-03-08 | 57 | 4 | 0 | 6
2026-03-09 | 57 | 4 | 0 | 6
2026-03-10 | 57 | 4 | 0 | 6
2026-03-11 | 57 | 4 | 0 | 6
2026-03-12 | 57 | 4 | 0 | 6
2026-03-13 | 56 | 4 | 0 | 6
2026-03-14 | 56 | 4 | 0 | 6
2026-03-15 | 56 | 4 | 0 | 6
2026-03-16 | 55 | 4 | 0 | 6
2026-03-17 | 56 | 4 | 0 | 6
2026-03-18 | 55 | 4 | 0 | 6
2026-03-19 | 52 | 4 | 0 | 6
2026-03-20 | 52 | 4 | 0 | 6
2026-03-21 | 52 | 4 | 0 | 6
2026-03-22 | 52 | 4 | 0 | 6
2026-03-23 | 52 | 4 | 0 | 6
2026-03-24 | 52 | 4 | 0 | 6
2026-03-25 | 52 | 4 | 0 | 6
2026-03-26 | 52 | 4 | 0 | 6
2026-03-27 | 52 | 4 | 0 | 6
2026-03-28 | 52 | 4 | 0 | 6
2026-03-29 | 52 | 4 | 0 | 6
2026-03-30 | 51 | 4 | 0 | 6
2026-03-31 | 50 | 4 | 0 | 2
2026-04-01 | 50 | 4 | 0 | 2
2026-04-02 | 54 | 10 | 2 | 5
2026-04-03 | 54 | 10 | 2 | 5
2026-04-04 | 54 | 10 | 2 | 5
2026-04-05 | 54 | 10 | 2 | 5
2026-04-06 | 54 | 10 | 2 | 5
2026-04-07 | 54 | 10 | 2 | 5
2026-04-08 | 54 | 10 | 2 | 5
2026-04-09 | 54 | 10 | 2 | 5
2026-04-10 | 54 | 10 | 2 | 5
2026-04-11 | 54 | 10 | 2 | 5
2026-04-12 | 54 | 10 | 2 | 5
2026-04-13 | 54 | 10 | 2 | 5
2026-04-14 | 54 | 10 | 2 | 5
2026-04-15 | 54 | 10 | 2 | 5
2026-04-16 | 57 | 14 | 2 | 5
2026-04-17 | 57 | 14 | 2 | 5
2026-04-18 | 57 | 14 | 2 | 5
2026-04-19 | 57 | 14 | 2 | 5
2026-04-20 | 57 | 14 | 2 | 5
2026-04-21 | 57 | 14 | 2 | 5
2026-04-22 | 57 | 14 | 2 | 5
2026-04-23 | 57 | 15 | 2 | 5
2026-04-24 | 57 | 15 | 2 | 5
2026-04-25 | 57 | 15 | 2 | 5
2026-04-26 | 57 | 15 | 2 | 5
2026-04-27 | 57 | 15 | 2 | 5
2026-04-28 | 57 | 15 | 2 | 5
2026-04-29 | 57 | 15 | 2 | 5
2026-04-30 | 53 | 15 | 2 | 4
2026-05-01 | 53 | 15 | 2 | 4
2026-05-02 | 53 | 16 | 2 | 4
2026-05-03 | 53 | 16 | 2 | 4
2026-05-04 | 53 | 16 | 2 | 4
2026-05-05 | 53 | 16 | 2 | 4
2026-05-06 | 53 | 16 | 2 | 4
2026-05-07 | 53 | 16 | 2 | 4
2026-05-08 | 51 | 16 | 2 | 4
2026-05-09 | 51 | 17 | 3 | 5
2026-05-10 | 51 | 17 | 3 | 5
2026-05-11 | 51 | 17 | 2 | 4
2026-05-12 | 51 | 17 | 2 | 4
2026-05-13 | 50 | 17 | 2 | 4
2026-05-14 | 50 | 17 | 2 | 4
2026-05-15 | 48 | 18 | 2 | 4
2026-05-16 | 48 | 18 | 2 | 4
2026-05-17 | 48 | 18 | 2 | 4
2026-05-18 | 48 | 18 | 2 | 4
2026-05-19 | 48 | 19 | 2 | 4
2026-05-20 | 47 | 19 | 2 | 4
2026-05-21 | 46 | 19 | 2 | 4
2026-05-22 | 46 | 19 | 2 | 4
2026-05-23 | 46 | 19 | 2 | 4
2026-05-24 | 46 | 19 | 2 | 4
2026-05-25 | 46 | 19 | 2 | 4
2026-05-26 | 46 | 20 | 2 | 4
2026-05-27 | 46 | 20 | 2 | 4
2026-05-28 | 46 | 20 | 2 | 4
2026-05-29 | 46 | 20 | 2 | 4
2026-05-30 | 46 | 20 | 2 | 4
2026-05-31 | 39 | 19 | 2 | 4
2026-06-01 | 39 | 19 | 2 | 4
2026-06-02 | 39 | 20 | 3 | 5
2026-06-03 | 39 | 20 | 3 | 5
2026-06-04 | 39 | 20 | 3 | 5
2026-06-05 | 39 | 20 | 3 | 5
2026-06-06 | 39 | 20 | 3 | 5
2026-06-07 | 39 | 20 | 3 | 5
2026-06-08 | 39 | 20 | 3 | 5
2026-06-09 | 39 | 20 | 3 | 5
2026-06-10 | 39 | 20 | 3 | 5
2026-06-11 | 39 | 20 | 3 | 5
2026-06-12 | 39 | 20 | 3 | 5
2026-06-13 | 39 | 20 | 3 | 5
2026-06-14 | 39 | 20 | 3 | 5
2026-06-15 | 36 | 16 | 3 | 4
2026-06-16 | 36 | 17 | 3 | 4
2026-06-17 | 34 | 17 | 3 | 4
2026-06-18 | 34 | 17 | 3 | 4
2026-06-19 | 34 | 17 | 3 | 4
2026-06-20 | 34 | 17 | 3 | 4
2026-06-21 | 34 | 17 | 3 | 4
2026-06-22 | 34 | 16 | 3 | 4
2026-06-23 | 34 | 16 | 3 | 4
2026-06-24 | 34 | 16 | 3 | 4
2026-06-25 | 34 | 16 | 3 | 4
2026-06-26 | 34 | 16 | 3 | 4
2026-06-27 | 34 | 16 | 3 | 4
2026-06-28 | 34 | 16 | 3 | 4
2026-06-29 | 34 | 16 | 3 | 4
2026-06-30 | 30 | 10 | 1 | 2
2026-07-01 | 30 | 9 | 0 | 1
2026-07-02 | 30 | 9 | 0 | 1
2026-07-03 | 30 | 9 | 0 | 1
2026-07-04 | 30 | 9 | 0 | 1
2026-07-05 | 30 | 9 | 0 | 1
2026-07-06 | 30 | 9 | 0 | 1
2026-07-07 | 30 | 9 | 0 | 1
2026-07-08 | 30 | 9 | 0 | 1
2026-07-09 | 30 | 9 | 0 | 1
2026-07-10 | 30 | 9 | 0 | 1
2026-07-11 | 30 | 9 | 0 | 1
2026-07-12 | 30 | 9 | 0 | 1
2026-07-13 | 30 | 9 | 0 | 1
2026-07-14 | 30 | 10 | 0 | 1
2026-07-15 | 30 | 10 | 0 | 1
2026-07-16 | 30 | 11 | 0 | 1
2026-07-17 | 30 | 11 | 0 | 1
2026-07-18 | 30 | 11 | 0 | 1
2026-07-19 | 30 | 11 | 0 | 1
2026-07-20 | 30 | 11 | 0 | 1
2026-07-21 | 30 | 11 | 0 | 1
2026-07-22 | 30 | 11 | 0 | 1
2026-07-23 | 30 | 11 | 0 | 1
2026-07-24 | 30 | 11 | 0 | 1
2026-07-25 | 30 | 11 | 0 | 1
2026-07-26 | 30 | 11 | 0 | 1
2026-07-27 | 30 | 11 | 0 | 1
2026-07-28 | 30 | 11 | 0 | 1
2026-07-29 | 30 | 10 | 0 | 1
2026-07-30 | 30 | 10 | 0 | 1
2026-07-31 | 30 | 9 | 0 | 1
2026-08-01 | 30 | 9 | 0 | 1
2026-08-02 | 30 | 9 | 0 | 1
2026-08-03 | 30 | 9 | 0 | 1
2026-08-04 | 30 | 9 | 0 | 1
2026-08-05 | 30 | 9 | 0 | 1
2026-08-06 | 30 | 9 | 0 | 1
2026-08-07 | 30 | 9 | 0 | 1
2026-08-08 | 30 | 9 | 0 | 1
2026-08-09 | 30 | 9 | 0 | 1
2026-08-10 | 30 | 9 | 0 | 1
2026-08-11 | 30 | 9 | 0 | 1
2026-08-12 | 30 | 9 | 0 | 1
2026-08-13 | 30 | 9 | 0 | 1
2026-08-14 | 30 | 8 | 0 | 1
2026-08-15 | 30 | 8 | 0 | 1
2026-08-16 | 30 | 8 | 0 | 1
2026-08-17 | 30 | 8 | 0 | 1
2026-08-18 | 30 | 8 | 0 | 1
2026-08-19 | 30 | 8 | 0 | 1
2026-08-20 | 30 | 8 | 0 | 1
2026-08-21 | 30 | 8 | 0 | 1
2026-08-22 | 30 | 8 | 0 | 1
2026-08-23 | 30 | 8 | 0 | 1
2026-08-24 | 30 | 8 | 0 | 1
2026-08-25 | 30 | 8 | 0 | 1
2026-08-26 | 30 | 8 | 0 | 1
2026-08-27 | 30 | 8 | 0 | 1
2026-08-28 | 30 | 8 | 0 | 1
2026-08-29 | 30 | 8 | 0 | 1
2026-08-30 | 30 | 8 | 0 | 1
2026-08-31 | 30 | 5 | 0 | 1
2026-09-01 | 30 | 5 | 0 | 1
2026-09-02 | 30 | 5 | 0 | 1
2026-09-03 | 30 | 5 | 0 | 1
2026-09-04 | 30 | 5 | 0 | 1
2026-09-05 | 30 | 5 | 0 | 1
2026-09-06 | 30 | 5 | 0 | 1
2026-09-07 | 30 | 5 | 0 | 1
2026-09-08 | 30 | 4 | 0 | 1
2026-09-09 | 30 | 4 | 0 | 1
2026-09-10 | 30 | 4 | 0 | 1
2026-09-11 | 30 | 4 | 0 | 1
2026-09-12 | 30 | 4 | 0 | 1
2026-09-13 | 30 | 4 | 0 | 1
2026-09-14 | 30 | 4 | 0 | 1
2026-09-15 | 30 | 4 | 0 | 1
2026-09-16 | 30 | 4 | 0 | 1
2026-09-17 | 30 | 4 | 0 | 1
2026-09-18 | 30 | 4 | 0 | 1
2026-09-19 | 30 | 4 | 0 | 1
2026-09-20 | 30 | 4 | 0 | 1
2026-09-21 | 30 | 4 | 0 | 1
2026-09-22 | 30 | 4 | 0 | 1
2026-09-23 | 30 | 4 | 0 | 1
2026-09-24 | 30 | 4 | 0 | 1
2026-09-25 | 30 | 4 | 0 | 1
2026-09-26 | 30 | 4 | 0 | 1
2026-09-27 | 30 | 4 | 0 | 1
2026-09-28 | 30 | 4 | 0 | 1
2026-09-29 | 30 | 4 | 0 | 1
2026-09-30 | 23 | 3 | 0 | 1
2026-10-01 | 23 | 3 | 0 | 1
2026-10-02 | 23 | 3 | 0 | 1
2026-10-03 | 23 | 3 | 0 | 1
2026-10-04 | 23 | 3 | 0 | 1
2026-10-05 | 23 | 3 | 0 | 1
2026-10-06 | 23 | 3 | 0 | 1
2026-10-07 | 23 | 3 | 0 | 1
2026-10-08 | 23 | 3 | 0 | 1
2026-10-09 | 23 | 3 | 0 | 1
2026-10-10 | 23 | 3 | 0 | 1
2026-10-11 | 23 | 3 | 0 | 1
2026-10-12 | 23 | 3 | 0 | 1
2026-10-13 | 23 | 3 | 0 | 1
2026-10-14 | 23 | 3 | 0 | 1
2026-10-15 | 23 | 3 | 0 | 1
2026-10-16 | 23 | 4 | 0 | 1
2026-10-17 | 23 | 4 | 0 | 1
2026-10-18 | 23 | 4 | 0 | 1
2026-10-19 | 23 | 4 | 0 | 1
2026-10-20 | 23 | 4 | 0 | 1
2026-10-21 | 23 | 4 | 0 | 1
2026-10-22 | 23 | 4 | 0 | 1
2026-10-23 | 23 | 4 | 0 | 1
2026-10-24 | 23 | 4 | 0 | 1
2026-10-25 | 23 | 4 | 0 | 1
2026-10-26 | 23 | 4 | 0 | 1
2026-10-27 | 23 | 4 | 0 | 1
2026-10-28 | 23 | 4 | 0 | 1
2026-10-29 | 23 | 4 | 0 | 1
2026-10-30 | 23 | 4 | 0 | 1
2026-10-31 | 23 | 4 | 0 | 1
2026-11-01 | 23 | 4 | 0 | 1
2026-11-02 | 23 | 4 | 0 | 1
2026-11-03 | 23 | 4 | 0 | 1
2026-11-04 | 23 | 4 | 0 | 1
2026-11-05 | 23 | 4 | 0 | 1
2026-11-06 | 23 | 4 | 0 | 1
2026-11-07 | 23 | 4 | 0 | 1
2026-11-08 | 23 | 4 | 0 | 1
2026-11-09 | 23 | 4 | 0 | 1
2026-11-10 | 23 | 4 | 0 | 1
2026-11-11 | 23 | 4 | 0 | 1
2026-11-12 | 23 | 4 | 0 | 1
2026-11-13 | 23 | 4 | 0 | 1
2026-11-14 | 23 | 4 | 0 | 1
2026-11-15 | 23 | 4 | 0 | 1
2026-11-16 | 23 | 4 | 0 | 1
2026-11-17 | 23 | 4 | 0 | 1
2026-11-18 | 23 | 4 | 0 | 1
2026-11-19 | 23 | 4 | 0 | 1
2026-11-20 | 23 | 4 | 0 | 1
2026-11-21 | 23 | 4 | 0 | 1
2026-11-22 | 23 | 4 | 0 | 1
2026-11-23 | 23 | 4 | 0 | 1
2026-11-24 | 23 | 4 | 0 | 1
2026-11-25 | 23 | 4 | 0 | 1
2026-11-26 | 23 | 4 | 0 | 1
2026-11-27 | 23 | 4 | 0 | 1
2026-11-28 | 23 | 4 | 0 | 1
2026-11-29 | 23 | 4 | 0 | 1
2026-11-30 | 23 | 4 | 0 | 1
2026-12-01 | 23 | 4 | 0 | 1
2026-12-02 | 23 | 4 | 0 | 1
2026-12-03 | 23 | 4 | 0 | 1
2026-12-04 | 23 | 4 | 0 | 1
2026-12-05 | 23 | 4 | 0 | 1
2026-12-06 | 23 | 4 | 0 | 1
2026-12-07 | 23 | 4 | 0 | 1
2026-12-08 | 23 | 4 | 0 | 1
2026-12-09 | 23 | 4 | 0 | 1
2026-12-10 | 23 | 4 | 0 | 1
2026-12-11 | 23 | 4 | 0 | 1
2026-12-12 | 23 | 4 | 0 | 1
2026-12-13 | 23 | 4 | 0 | 1
2026-12-14 | 23 | 4 | 0 | 1
2026-12-15 | 23 | 4 | 0 | 1
2026-12-16 | 23 | 4 | 0 | 1
2026-12-17 | 23 | 4 | 0 | 1
2026-12-18 | 23 | 4 | 0 | 1
2026-12-19 | 23 | 4 | 0 | 1
2026-12-20 | 23 | 4 | 0 | 1
2026-12-21 | 23 | 4 | 0 | 1
2026-12-22 | 23 | 4 | 0 | 1
2026-12-23 | 23 | 3 | 0 | 1
2026-12-24 | 23 | 3 | 0 | 1
2026-12-25 | 23 | 3 | 0 | 1
2026-12-26 | 23 | 3 | 0 | 1
2026-12-27 | 23 | 3 | 0 | 1
2026-12-28 | 23 | 3 | 0 | 1
2026-12-29 | 23 | 3 | 0 | 1
2026-12-30 | 23 | 3 | 0 | 1
2026-12-31 | 22 | 0 | 0 | 1
2027-01-01 | 22 | 0 | 0 | 1

## Task_table_03_2_26 (hidden)
Initiative | Process | Phase | Process level | Process Group | % Arbeit abgeschlossen | IT Process Consultant | IT Process Initiative Lead | IT Process Manager | Anfang | Ende | Dauer2 | Process Approval Date | Actual Phase | Planned phase | Associated Process on L1 | 📌 Analyse
Corporate IT body | Manage IT strategy | Total | L1 | MP | 50% |  |  |  | 2026-02-02 | 2026-07-29 | 128 | Mit 06.05.26 |  | 1 | Manage IT strategy | Prozesse in Elaboration | 39
Corporate IT body | Manage IT strategy | Elaboration | L1 | MP | 50% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-02-02 | 2026-04-30 | 64 | NV | Elaboration in progress | Elaboration in progress | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-14 | 2026-07-29 | 55 | NV |  | Scheduled | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT strategy
Corporate IT body | Manage IT strategy | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT strategy
Corporate IT body | Manage IT governance framework | Total | L1 | MP | 50% |  |  |  | 2026-01-07 | 2026-08-31 | 169 | NV |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Elaboration | L1 | MP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-03-16 | 2026-05-21 | 49 | NV | Elaboration in progress | Elaboration in progress | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-25 | 2026-08-31 | 71 | NV |  | Scheduled | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Manage IT governance framework | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Total | L2 | MP | 25% |  |  |  | 2026-01-07 | 2026-01-17 | 8 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Elaboration | L2 | MP | 25% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-01-07 | 2026-01-17 | 7 | NV | Delayed | Implementation LIS Done | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation COT | L2 | MP | 0% |  |  |  | 2026-01-07 | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Maintain IT glossary | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT governance framework
Corporate IT body | Manage enterprise architecture | Total | L1 | MP | 24% |  |  |  | 2025-10-16 | 2026-07-16 | 195.85 | NV |  |  | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Elaboration | L1 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 2026-02-23 | 2026-05-08 | 54.85 | NV | Delayed | Elaboration in progress | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-08 | 2026-07-16 | 49 | NV |  | Scheduled | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation COT | L1 | MP | 0% |  |  |  | 2026-05-08 | 2026-05-11 | 1 | NV |  | Scheduled | Manage enterprise architecture
Corporate IT body | Manage enterprise architecture | Implementation LUS | L1 | MP | 0% |  |  |  | 2026-05-08 | 2026-05-11 | 1 | NV |  | Scheduled | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Total | L2 | MP | 50% |  |  |  | 2025-10-16 | 2026-04-30 | 141 | NV |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Elaboration | L2 | MP | 50% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 2026-02-23 | 2026-04-30 | 49 | NV | Elaboration in progress | Elaboration in progress | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage enterprise architecture
Corporate IT body | Strategic architecture process | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage enterprise architecture
ITSM | Manage IT portfolio | Total | L1 | MP | 69% |  |  |  | 2025-11-10 | 2026-05-15 | 135 | NV |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Elaboration | L1 | MP | 100% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) |  |  | 2025-11-11 | 2026-01-29 | 58 | NV | Elaboration Done | Elaboration Done | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LIS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT portfolio | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Total | L2 | MP | 100% |  |  |  | 2025-11-10 | 2026-05-31 | 145 | NV |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Elaboration | L2 | MP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-10 | 2025-12-10 | 23 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-02-01 | 2026-05-31 | 85 | NV | Delayed | Implementation LIS | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
IT project management | Manage IT project portfolio | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Total | L2 | MP | 0% |  |  |  | 2026-04-01 | 2026-09-08 | 115 | NV |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Elaboration | L2 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Ceilia Roser (LIS) | Reiner Heiko (HAU-ITSA) | 2026-04-01 | 2026-05-13 | 31 | NV |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-06-15 | 2026-09-08 | 62 | NV |  | Scheduled | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
ITSM | Manage IT service portfolio | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT portfolio
IT planning and steering | Manage and control IT financials | Total | L1 | MP | 50% |  |  | Moser Mario (LIS-LAH) | 2025-10-15 | 2026-07-31 | 208 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Elaboration | L1 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | 2026-04-30 | 142 | NV | Elaboration in progress | Elaboration in progress | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-01 | 2026-07-31 | 66 | NV |  | Scheduled | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage and control IT financials | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Total | L2 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Create and maintain IT budgets | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Approve and communicate budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Develop preliminary budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Maintan and adjust budget | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  | 18 | Manage and control IT financials
IT planning and steering | Review budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Review budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Revise and optimize budget plan | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Total | L2 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage finance and accounting | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define financial management framework | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish financial accounting structure | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Total | L2 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation COT |  | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Manage IT costs | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Compare actual cost to budget forecast | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Initiate corrective or preventive actions | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Report actual IT costs | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Total | L2 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Model and allocate IT costs | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Define cost allocation principles | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Establish cost allocation model | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Total | L3 | MP | 50% |  |  |  | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
IT planning and steering | Gather relevant cost and consumption data | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage and control IT financials
Corporate IT body | Manage IT stakeholder relationships | Total | L1 | MP | 0% |  |  |  | 2026-04-01 | 2026-12-23 | 191 | NV |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Elaboration | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-06-15 | 54 | NV |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 | NV |  | Scheduled | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT stakeholder relationships
Corporate IT body | Manage IT stakeholder relationships | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT stakeholder relationships
ITSM | Manage IT processes and continuous improvement | Total | L1 | MP | 21% |  |  |  | 2025-10-01 | 2026-05-31 | 173 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Elaboration | L1 | MP | 100% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LIS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage IT processes and continuous improvement | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Total | L2 | MP | 100% |  |  |  | 2025-10-15 | 2025-10-16 | 1 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Elaboration | L2 | MP | 100% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-08-04 | 2025-08-30 | 20 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Develop and maintain IT BPM framework | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Total | L2 | MP | 0% |  |  |  | 2025-10-01 | 2026-01-30 | 88 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-01-30 | 88 | NV | Delayed | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continuous improvement | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Total | L3 | MP | 0% |  |  |  | ? | 2025-10-16 | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Elaboration | L3 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage a common approach to contiual improvement | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Total | L3 | MP | 0% |  |  |  | ? | 2025-10-16 | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Elaboration | L3 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Manage continual improvement initiative | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Total | L2 | MP | 25% |  |  |  | 2025-10-01 | 2026-05-31 | 173 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Perform operational process management (V 2.0) | Elaboration | L2 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform operational process management | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Identify process and determine goals (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Identify process and determine goals | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Elaborate to-be process (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Elaborate to-be process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Plan process execution (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Plan process execution | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | Fre 19.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Implement process (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | NV | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Implement process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Total | L3 | MP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Perform and measure process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Perform and measure process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Total | L3 | MP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | Don 18.09.25 |  |  | Manage IT processes and continuous improvement
Corporate IT body | Analyse process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
ITSM | Analyse process | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT processes and continuous improvement
Central area (Jan Müskens) | Manage IT risks and compliance | Total | L1 | MP | 19% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Elaboration | L1 | MP | 100% | Kreis Andreas (LLI);Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2025-10-01 | 1 | NV | Elaboration Done | Elaboration Done | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LIS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation COT | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LUS | L1 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Total | L2 | MP | 0% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Moser Mario (LIS-LAH) |  | Monnier Murielle (LEC) | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT risks | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Total | L2 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Elaboration | L2 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Implementation LIS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Implementation COT | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT compliance | Implementation LUS | L2 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Monitor to delegate | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Requirements to measures | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Implement to improve | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | Manage IT-C framework | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 | NV | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LIS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation COT | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LUS | L3 | MP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT risks and compliance
Corporate IT body | Plan IT service | Total | L1 | CP | 100% |  |  |  | 2025-08-01 | 2026-04-30 | 195 | NV |  |  | Plan IT service
Corporate IT body | Plan IT service | Elaboration | L1 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-10-16 | 2025-10-31 | 12 | Mit 10.12.25 | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Plan IT service | Implementation LIS | L1 | CP | 75% |  |  |  | 2025-11-01 | 2026-02-28 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Plan IT service | Implementation COT | L1 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Plan IT service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Total | L2 | CP | 100% |  |  |  | 2025-08-01 | 2025-08-05 | 3 | Die 19.08.25 |  |  | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-11-01 | 2026-02-28 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation COT | L2 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Perform initial assessment of customer need | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Total | L2 | CP | 100% |  |  |  | 2025-08-01 | 2026-04-30 | 195 | Mit 10.12.25 |  |  | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-11-01 | 2026-02-28 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation COT | L2 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Evaluate and qualify IT demand | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Total | L3 | CP | 100% |  |  |  | 2025-08-01 | 2026-04-30 | 195 | NV |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Elaboration | L3 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-10-15 | 54 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation COT | L3 | CP | 0% |  |  |  | 2025-10-16 | 2026-04-30 | 141 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Analyse architecture impact | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
Corporate IT body | Approve IT demand | Total | L2 | CP | 100% |  |  |  | 2025-08-01 | 2025-08-01 | 1 | Die 19.08.25 |  |  | Plan IT service
Corporate IT body | Approve IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 | NV | Elaboration Done | Elaboration Done | Plan IT service
Corporate IT body | Approve IT demand | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-11-01 | 2026-02-28 | 85 | NV | Delayed | Implementation LIS Done | Plan IT service
Corporate IT body | Approve IT demand | Implementation COT | L2 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 | NV | Delayed | Implementation COT | Plan IT service
Corporate IT body | Approve IT demand | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Plan IT service
ITSM | Build IT Service | Total | L1 | CP | 41% |  |  |  | 2025-04-01 | 2026-08-31 | 370 | NV |  |  | Build IT Service
ITSM | Build IT Service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Build IT Service | Implementation LIS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Build IT Service | Implementation COT | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Build IT Service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Design IT service | Total | L2 | CP | 50% |  |  |  | 2025-10-01 | 2026-08-14 | 228 | NV |  |  | Build IT Service
ITSM | Design IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-02-16 | 2026-05-15 | 65 | NV | Delayed | Elaboration in progress | Build IT Service
ITSM | Design IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-05-18 | 2026-08-14 | 65 | NV |  | Scheduled | Build IT Service
ITSM | Design IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Design IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
Architecture management | Define solution target architecture | Total | L3 | CP | 50% |  |  |  | 2026-01-14 | 2026-06-22 | 114 | NV |  |  | Build IT Service
Architecture management | Define solution target architecture | Elaboration | L3 | CP | 50% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) | 2026-02-05 | 2026-04-21 | 54 | NV | Elaboration in progress | Elaboration in progress | Build IT Service
Architecture management | Define solution target architecture | Implementation LIS | L3 | CP | 0% |  |  |  | 2026-04-22 | 2026-06-22 | 44 | NV |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation COT | L3 | CP | 0% |  |  |  | 2026-04-22 | 2026-04-22 | 1 | NV |  | Scheduled | Build IT Service
Architecture management | Define solution target architecture | Implementation LUS | L3 | CP | 0% |  |  |  | 2026-01-14 | 2026-01-14 | 0 | NV | Delayed | Implementation LUS Done | Build IT Service
ITSM | Develop and customise IT service | Total | L2 | CP | 0% |  |  |  | 2025-05-26 | 2026-05-15 | 255 | NV |  |  | Build IT Service
ITSM | Develop and customise IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-02-16 | 2026-05-15 | 65 | NV | Delayed | Elaboration in progress | Build IT Service
ITSM | Develop and customise IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-05-26 | 2025-08-15 | 60 | NV | Delayed | Implementation LIS Done | Build IT Service
ITSM | Develop and customise IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Develop and customise IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Deploy IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 | NV |  |  | Build IT Service
ITSM | Deploy IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-04-15 | 2026-06-15 | 44 | NV |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 | NV |  | Scheduled | Build IT Service
ITSM | Deploy IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Deploy IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
| Test and validate IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 | NV |  |  | Build IT Service
ITSM | Test and validate IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-04-15 | 2026-06-15 | 44 | NV |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 | NV |  | Scheduled | Build IT Service
ITSM | Test and validate IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Test and validate IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Total | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LIS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Evaluate success of IT service rollout | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manage IT service change | Total | L2 | CP | 100% |  |  |  | 2026-01-12 | 2026-06-30 | 122 | Mit 15.04.26 |  |  | Build IT Service
ITSM | Manag IT service change | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 2026-01-12 | 2026-03-18 | 48 | Mit 15.04.26 | Elaboration Done | Elaboration Done | Build IT Service
ITSM | Manag IT service change | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 | NV |  | Scheduled | Build IT Service
ITSM | Manag IT service change | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manag IT service change | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manage IT service release | Total | L2 | CP | 50% |  |  |  | 2026-02-20 | 2026-06-30 | 93 | NV |  |  | Build IT Service
ITSM | Manage IT service release | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 2026-02-20 | 2026-05-08 | 56 | NV | Elaboration in progress | Elaboration in progress | Build IT Service
ITSM | Manage IT service release | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 | NV |  | Scheduled | Build IT Service
ITSM | Manage IT service release | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Manage IT service release | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Build IT Service
ITSM | Deliver IT service | Total | L1 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-17 | 56 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Elaboration | L1 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LIS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation COT | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Deliver IT service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Manage IT service provision request | Total | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-17 | 56 | NV |  |  | Deliver IT service
ITSM | Manage IT service provision request | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 | NV |  | Scheduled | Deliver IT service
ITSM | Manage IT service provision request | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 | NV |  | Scheduled | Deliver IT service
ITSM | Manage IT service provision request | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Manage IT service provision request | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Handle IT service order | Total | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-17 | 56 | NV |  |  | Deliver IT service
ITSM | Handle IT service order | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 | NV |  | Scheduled | Deliver IT service
ITSM | Handle IT service order | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 | NV |  | Scheduled | Deliver IT service
ITSM | Handle IT service order | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Handle IT service order | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Deliver IT service
ITSM | Run IT service | Total | L1 | CP | 17% |  |  |  | 2025-10-15 | 2026-09-25 | 248 | NV |  |  | Run IT service
ITSM | Run IT service | Elaboration | L1 | CP | 0% | Schroeder Michael (LIS);Böhme Matthias (ext.) | Oey Kai (LIS) | Sint Rachel (LBH) | 2025-10-16 | 2026-06-30 | 184 | NV | Delayed | Elaboration in progress | Run IT service
ITSM | Run IT service | Implementation LIS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Run IT service | Implementation COT | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Run IT service | Implementation LUS | L1 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Total | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation LIS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Ensure IT service continuity | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service capacity | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Review and maintain IT service continuity plan | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service performance | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation LIS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Montior and report IT service performance | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service level | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and report IT service financials | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor and analyse events | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor IT service risk and compliance | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Monitor user experience | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Operate and maintain IT service | Total | L2 | CP | 21% |  |  |  | 2025-10-15 | 2026-06-30 | 185 | NV |  |  | Run IT service
ITSM | Operate and maintain IT service | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-12 | 2026-06-30 | 122 | NV | Delayed | Elaboration in progress | Run IT service
ITSM | Operate and maintain IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 | NV |  | Scheduled | Run IT service
ITSM | Operate and maintain IT service | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Operate and maintain IT service | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Total | L3 | CP | 50% |  |  |  | 2026-01-14 | 2026-05-20 | 91 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Elaboration | L3 | CP | 50% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-14 | 2026-05-20 | 91 | NV | Elaboration in progress | Elaboration in progress | Run IT service
ITSM | Maintain CMDB | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain CMDB | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Total | L3 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain IT asset database | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Maintain standard change catalouge for IT service | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Provide IT service support | Total | L2 | CP | 57% |  |  |  | 2025-10-16 | 2026-06-15 | 173 | NV |  |  | Run IT service
ITSM | Provide IT service support | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 | NV | Delayed | Elaboration in progress | Run IT service
ITSM | Provide IT service support | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 | NV |  | Scheduled | Run IT service
ITSM | Provide IT service support | Implementation COT | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Provide IT service support | Implementation LUS | L2 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT Incident | Total | L3 | CP | 75% |  |  |  | 2026-01-13 | 2026-03-19 | 48 | Don 19.03.26 |  |  | Run IT service
ITSM | Handle IT Incident | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | Don 19.03.26 | Elaboration in progress | Elaboration Done | Run IT service
ITSM | Handle IT Incident | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT Incident | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT Incident | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT problem | Total | L3 | CP | 75% |  |  |  | 2026-01-13 | 2026-03-19 | 48 | Don 19.03.26 |  |  | Run IT service
ITSM | Handle IT problem | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | Don 19.03.26 | Elaboration in progress | Elaboration Done | Run IT service
ITSM | Handle IT problem | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT problem | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT problem | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT service request | Total | L3 | CP | 100% |  |  |  | 2026-02-02 | 2026-03-19 | 34 | Don 19.03.26 |  |  | Run IT service
ITSM | Handle IT service request | Elaboration | L3 | CP | 100% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-02-02 | 2026-03-19 | 34 | Don 19.03.26 | Elaboration Done | Elaboration Done | Run IT service
ITSM | Handle IT service request | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT service request | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Handle IT service request | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Total | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LIS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Implementation COT | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
ITSM | Manage IT service desk | Implementation LUS | L3 | CP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Run IT service
Information security | Ensure Information security | Total | L1 | SP | 50% |  |  |  | 2025-10-16 | 2025-10-16 | 1 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Elaboration | L1 | SP | 50% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | 2025-10-16 | ? | 0 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Ensure Information security | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Total | L2 | SP | 50% |  |  |  | 2025-10-16 | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Elaboration | L2 | SP | 50% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-19 | 2026-04-30 | 139 | NV | Elaboration in progress | Elaboration in progress | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
Information security | Perform SaaS Security Assessment | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure Information security
IT project management | Manage IT project | Total | L1 | SP | 100% |  |  |  | 2025-07-14 | 2025-12-10 | 108 | Don 18.09.25 |  |  | Manage IT project
IT project management | Manage IT project | Elaboration | L1 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Manage IT project | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Initiate IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Initiate IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Initiate IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Initiate IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Initiate IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Plan IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Plan IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Plan IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Plan IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Plan IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Steer and execute IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Steer and execute IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Steer and execute IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Steer and execute IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Steer and execute IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Close IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Close IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Close IT project | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Close IT project | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Close IT project | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project change request | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | Don 18.09.25 |  |  | Manage IT project
IT project management | Manage IT project change request | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Manage IT project change request | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Manage IT project change request | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Assign personnel resources to IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | NV |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | Mit 28.01.26 | Elaboration Done | Elaboration Done | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
IT project management | Ressourcemanagement for IT projects | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT project
ITSM | Manage IT sourcing and procurement | Total | L1 | SP | 0% |  |  |  | 2026-04-20 | 2026-09-30 | 118 | NV |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS);Schoeberl Lorena (LBH) | tbd | Monnier Murielle (LEC) | 2026-04-20 | 2026-06-30 | 52 | NV |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-13 | 2026-09-30 | 58 | NV |  | Scheduled | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT sourcing and procurement
ITSM | Manage IT sourcing and procurement | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT sourcing and procurement
HR initiatives for IT | Provide and develop IT workforce | Total | L1 | SP | 4% |  |  |  | 2025-10-01 | 2027-06-30 | 456 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Elaboration | L1 | SP | 100% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2025-10-01 | 1 | NV | Elaboration Done | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Provide and develop IT workforce | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
| Manage HR4IT strategy, governane and framework |  | L2 |  | 0% |  |  |  | 2025-10-01 | 2026-12-31 | 327 | NV
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Elaboration | L2 | SP | 100% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2025-10-01 | 1 | NV | Elaboration Done | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2026-12-31 | 316 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2025-12-31 | 55 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-01-01 | 2026-12-31 | 261 | NV | Delayed | Implementation LIS | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Plan IT workforce | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2026-05-31 | 162 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2026-05-31 | 162 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand |  | L3 | SP | 0% |  |  |  | 2025-10-01 | 2026-06-30 | 195 | NV
HR initiatives for IT | Manage HR4IT service demand | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2026-05-31 | 173 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-06-01 | 2026-06-30 | 22 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand | Implementation COT | L3 | SP | 0% |  |  |  | 2026-06-01 | 2026-06-30 | 22 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage HR4IT service demand | Implementation LUS | L3 | SP | 0% |  |  |  | 2026-06-01 | 2026-06-30 | 22 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Total | L2 | SP | 0% |  |  |  | 2025-10-01 | 2026-12-31 | 327 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Elaboration | L2 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Attract and hire employees | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing |  | L3 | SP | 0% |  |  |  | 2025-10-01 | 2026-12-31 | 327 | NV
HR initiatives for IT | Perform active sourcing | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-02-28 | 108 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-03-01 | 2026-12-31 | 219 | NV | Delayed | Implementation LIS | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform active sourcing | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers |  | L3 | SP | 0% |  |  |  | 2025-10-01 | 2026-12-31 | 327 | NV
HR initiatives for IT | Recruit employees and managers | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-02-28 | 108 | NV | Delayed | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-03-01 | 2026-12-31 | 219 | NV | Delayed | Implementation LIS | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Recruit employees and managers | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Total | L2 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Elaboration | L2 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform onboarding | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Pre-board new IT employee and manager | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Onboard new IT employee and manager | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Total | L2 | SP | 10% |  |  |  | 2025-10-01 | 2027-06-30 | 456 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Elaboration | L2 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Implementation LIS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Implementation COT | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Perform, learn and grow | Implementation LUS | L2 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue |  | L3 | SP | 50% |  |  |  | 2025-10-01 | 2026-03-13 | 118 | NV
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Elaboration | L3 | SP | 50% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-03-13 | 118 | NV | Elaboration in progress | Elaboration Done | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Total | L3 | SP | 0% |  |  |  | 2026-03-31 | 2026-06-30 | 66 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-03-31 | 2026-03-31 | 1 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-30 | 65 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Implementation COT | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-30 | 65 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Mapping and evaluate IT career level | Implementation LUS | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-30 | 65 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT development programme | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Total | L3 | SP | 0% |  |  |  | 2026-01-01 | 2027-06-30 | 390 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-01 | 2026-12-31 | 261 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LIS | L3 | SP | 0% |  |  |  | 2027-01-01 | 2027-06-30 | 129 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation COT | L3 | SP | 0% |  |  |  | 2027-01-01 | 2027-06-30 | 129 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT skills | Implementation LUS | L3 | SP | 0% |  |  |  | 2027-01-01 | 2027-06-30 | 129 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT talent pool and identify potential | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LIS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation COT | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme | Implementation LUS | L3 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Total | L3 | SP | 0% |  |  |  | 2026-01-15 | 2026-07-01 | 120 | NV |  |  | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-03-31 | 54 | NV | Delayed | Elaboration in progress | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation COT | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 | NV |  | Scheduled | Provide and develop IT workforce
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LUS | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 | NV |  | Scheduled | Provide and develop IT workforce
ITSM | Ensure performance and conformance of IT services | Total | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Elaboration | L1 | SP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 | NV |  | Scheduled | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Ensure performance and conformance of IT services | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Ensure performance and conformance of IT services
ITSM | Manage IT knowledge | Total | L1 | SP | 75% |  |  |  | 2026-01-20 | 2026-06-30 | 116 | Don 19.03.26 |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Elaboration | L1 | SP | 75% | Schroeder Michael (LIS) | Kürschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-20 | 2026-02-25 | 27 | NV | Elaboration in progress | Elaboration Done | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 | NV |  | Scheduled | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT knowledge
ITSM | Manage IT knowledge | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Manage IT knowledge
ITSM | Leverage IT innovation | Total | L1 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | ? | ? | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Implementation LIS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Implementation COT | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Leverage IT innovtion
ITSM | Leverage IT innovation | Implementation LUS | L1 | SP | 0% |  |  |  | ? | ? | 0 | NV |  |  | Leverage IT innovtion

## Date_table_03_2_26 (hidden)
Datum | Elaboration | Implementation LIS | Implementation LUS | Implementation COT
2025-08-01 | 0 | 1 | 0 | 0
2025-08-02 | 1 | 1 | 0 | 0
2025-08-03 | 1 | 1 | 0 | 0
2025-08-04 | 1 | 1 | 0 | 0
2025-08-05 | 2 | 1 | 0 | 0
2025-08-06 | 2 | 1 | 0 | 0
2025-08-07 | 2 | 1 | 0 | 0
2025-08-08 | 2 | 1 | 0 | 0
2025-08-09 | 2 | 1 | 0 | 0
2025-08-10 | 2 | 1 | 0 | 0
2025-08-11 | 2 | 1 | 0 | 0
2025-08-12 | 2 | 1 | 0 | 0
2025-08-13 | 2 | 1 | 0 | 0
2025-08-14 | 2 | 1 | 0 | 0
2025-08-15 | 2 | 0 | 0 | 0
2025-08-16 | 2 | 0 | 0 | 0
2025-08-17 | 2 | 0 | 0 | 0
2025-08-18 | 2 | 0 | 0 | 0
2025-08-19 | 2 | 0 | 0 | 0
2025-08-20 | 2 | 0 | 0 | 0
2025-08-21 | 2 | 0 | 0 | 0
2025-08-22 | 2 | 0 | 0 | 0
2025-08-23 | 2 | 0 | 0 | 0
2025-08-24 | 2 | 0 | 0 | 0
2025-08-25 | 2 | 0 | 0 | 0
2025-08-26 | 2 | 0 | 0 | 0
2025-08-27 | 2 | 0 | 0 | 0
2025-08-28 | 2 | 0 | 0 | 0
2025-08-29 | 2 | 0 | 0 | 0
2025-08-30 | 1 | 0 | 0 | 0
2025-08-31 | 1 | 0 | 0 | 0
2025-09-01 | 1 | 0 | 0 | 0
2025-09-02 | 1 | 0 | 0 | 0
2025-09-03 | 1 | 0 | 0 | 0
2025-09-04 | 1 | 0 | 0 | 0
2025-09-05 | 1 | 0 | 0 | 0
2025-09-06 | 1 | 0 | 0 | 0
2025-09-07 | 1 | 0 | 0 | 0
2025-09-08 | 1 | 0 | 0 | 0
2025-09-09 | 1 | 0 | 0 | 0
2025-09-10 | 1 | 0 | 0 | 0
2025-09-11 | 1 | 0 | 0 | 0
2025-09-12 | 1 | 0 | 0 | 0
2025-09-13 | 1 | 0 | 0 | 0
2025-09-14 | 1 | 0 | 0 | 0
2025-09-15 | 1 | 0 | 0 | 0
2025-09-16 | 1 | 0 | 0 | 0
2025-09-17 | 1 | 0 | 0 | 0
2025-09-18 | 1 | 0 | 0 | 0
2025-09-19 | 1 | 0 | 0 | 0
2025-09-20 | 1 | 0 | 0 | 0
2025-09-21 | 1 | 0 | 0 | 0
2025-09-22 | 1 | 0 | 0 | 0
2025-09-23 | 1 | 0 | 0 | 0
2025-09-24 | 1 | 0 | 0 | 0
2025-09-25 | 1 | 0 | 0 | 0
2025-09-26 | 1 | 0 | 0 | 0
2025-09-27 | 1 | 0 | 0 | 0
2025-09-28 | 1 | 0 | 0 | 0
2025-09-29 | 1 | 0 | 0 | 0
2025-09-30 | 1 | 0 | 0 | 0
2025-10-01 | 1 | 0 | 0 | 0
2025-10-02 | 13 | 0 | 0 | 0
2025-10-03 | 13 | 0 | 0 | 0
2025-10-04 | 13 | 0 | 0 | 0
2025-10-05 | 13 | 0 | 0 | 0
2025-10-06 | 13 | 0 | 0 | 0
2025-10-07 | 13 | 0 | 0 | 0
2025-10-08 | 13 | 0 | 0 | 0
2025-10-09 | 13 | 0 | 0 | 0
2025-10-10 | 13 | 0 | 0 | 0
2025-10-11 | 13 | 0 | 0 | 0
2025-10-12 | 13 | 0 | 0 | 0
2025-10-13 | 13 | 0 | 0 | 0
2025-10-14 | 13 | 0 | 0 | 0
2025-10-15 | 12 | 0 | 0 | 0
2025-10-16 | 33 | 0 | 0 | 0
2025-10-17 | 38 | 0 | 0 | 1
2025-10-18 | 38 | 0 | 0 | 1
2025-10-19 | 38 | 0 | 0 | 1
2025-10-20 | 39 | 0 | 0 | 1
2025-10-21 | 39 | 0 | 0 | 1
2025-10-22 | 39 | 0 | 0 | 1
2025-10-23 | 39 | 0 | 0 | 1
2025-10-24 | 39 | 0 | 0 | 1
2025-10-25 | 39 | 0 | 0 | 1
2025-10-26 | 39 | 0 | 0 | 1
2025-10-27 | 39 | 0 | 0 | 1
2025-10-28 | 39 | 0 | 0 | 1
2025-10-29 | 39 | 0 | 0 | 1
2025-10-30 | 39 | 0 | 0 | 1
2025-10-31 | 38 | 0 | 0 | 1
2025-11-01 | 38 | 0 | 0 | 1
2025-11-02 | 38 | 4 | 0 | 1
2025-11-03 | 38 | 4 | 0 | 1
2025-11-04 | 38 | 4 | 0 | 5
2025-11-05 | 38 | 4 | 0 | 5
2025-11-06 | 38 | 4 | 0 | 5
2025-11-07 | 38 | 4 | 0 | 5
2025-11-08 | 38 | 4 | 0 | 5
2025-11-09 | 38 | 4 | 0 | 5
2025-11-10 | 38 | 4 | 0 | 5
2025-11-11 | 39 | 4 | 0 | 5
2025-11-12 | 47 | 4 | 0 | 5
2025-11-13 | 47 | 4 | 0 | 5
2025-11-14 | 47 | 4 | 0 | 5
2025-11-15 | 47 | 4 | 0 | 5
2025-11-16 | 47 | 4 | 0 | 5
2025-11-17 | 47 | 4 | 0 | 5
2025-11-18 | 47 | 4 | 0 | 5
2025-11-19 | 47 | 4 | 0 | 5
2025-11-20 | 47 | 4 | 0 | 5
2025-11-21 | 47 | 4 | 0 | 5
2025-11-22 | 47 | 4 | 0 | 5
2025-11-23 | 47 | 4 | 0 | 5
2025-11-24 | 47 | 4 | 0 | 5
2025-11-25 | 47 | 4 | 0 | 5
2025-11-26 | 47 | 4 | 0 | 5
2025-11-27 | 47 | 4 | 0 | 5
2025-11-28 | 47 | 4 | 0 | 5
2025-11-29 | 47 | 4 | 0 | 5
2025-11-30 | 47 | 4 | 0 | 5
2025-12-01 | 47 | 4 | 0 | 5
2025-12-02 | 47 | 4 | 0 | 5
2025-12-03 | 47 | 4 | 0 | 5
2025-12-04 | 47 | 4 | 0 | 5
2025-12-05 | 47 | 4 | 0 | 5
2025-12-06 | 47 | 4 | 0 | 5
2025-12-07 | 47 | 4 | 0 | 5
2025-12-08 | 47 | 4 | 0 | 5
2025-12-09 | 47 | 4 | 0 | 5
2025-12-10 | 39 | 4 | 0 | 5
2025-12-11 | 39 | 4 | 0 | 5
2025-12-12 | 39 | 4 | 0 | 5
2025-12-13 | 39 | 4 | 0 | 5
2025-12-14 | 39 | 4 | 0 | 5
2025-12-15 | 39 | 4 | 0 | 5
2025-12-16 | 39 | 4 | 0 | 5
2025-12-17 | 39 | 4 | 0 | 5
2025-12-18 | 39 | 4 | 0 | 5
2025-12-19 | 39 | 4 | 0 | 5
2025-12-20 | 39 | 4 | 0 | 5
2025-12-21 | 39 | 4 | 0 | 5
2025-12-22 | 39 | 4 | 0 | 5
2025-12-23 | 39 | 4 | 0 | 5
2025-12-24 | 39 | 4 | 0 | 5
2025-12-25 | 39 | 4 | 0 | 5
2025-12-26 | 39 | 4 | 0 | 5
2025-12-27 | 39 | 4 | 0 | 5
2025-12-28 | 39 | 4 | 0 | 5
2025-12-29 | 39 | 4 | 0 | 5
2025-12-30 | 39 | 4 | 0 | 5
2025-12-31 | 38 | 4 | 0 | 5
2026-01-01 | 38 | 4 | 0 | 5
2026-01-02 | 39 | 5 | 0 | 5
2026-01-03 | 39 | 5 | 0 | 5
2026-01-04 | 39 | 5 | 0 | 5
2026-01-05 | 39 | 5 | 0 | 5
2026-01-06 | 39 | 5 | 0 | 5
2026-01-07 | 39 | 5 | 0 | 5
2026-01-08 | 41 | 6 | 0 | 6
2026-01-09 | 41 | 6 | 0 | 6
2026-01-10 | 41 | 6 | 0 | 6
2026-01-11 | 41 | 6 | 0 | 6
2026-01-12 | 41 | 6 | 0 | 6
2026-01-13 | 49 | 6 | 0 | 6
2026-01-14 | 51 | 6 | 0 | 6
2026-01-15 | 52 | 6 | 0 | 6
2026-01-16 | 53 | 6 | 0 | 6
2026-01-17 | 53 | 5 | 0 | 6
2026-01-18 | 53 | 5 | 0 | 6
2026-01-19 | 53 | 5 | 0 | 6
2026-01-20 | 53 | 5 | 0 | 6
2026-01-21 | 54 | 5 | 0 | 6
2026-01-22 | 54 | 5 | 0 | 6
2026-01-23 | 54 | 5 | 0 | 6
2026-01-24 | 54 | 5 | 0 | 6
2026-01-25 | 54 | 5 | 0 | 6
2026-01-26 | 54 | 5 | 0 | 6
2026-01-27 | 54 | 5 | 0 | 6
2026-01-28 | 54 | 5 | 0 | 6
2026-01-29 | 53 | 5 | 0 | 6
2026-01-30 | 52 | 5 | 0 | 6
2026-01-31 | 52 | 5 | 0 | 6
2026-02-01 | 52 | 5 | 0 | 6
2026-02-02 | 52 | 6 | 0 | 6
2026-02-03 | 54 | 6 | 0 | 6
2026-02-04 | 54 | 6 | 0 | 6
2026-02-05 | 54 | 6 | 0 | 6
2026-02-06 | 55 | 6 | 0 | 6
2026-02-07 | 55 | 6 | 0 | 6
2026-02-08 | 55 | 6 | 0 | 6
2026-02-09 | 55 | 6 | 0 | 6
2026-02-10 | 55 | 6 | 0 | 6
2026-02-11 | 55 | 6 | 0 | 6
2026-02-12 | 55 | 6 | 0 | 6
2026-02-13 | 55 | 6 | 0 | 6
2026-02-14 | 55 | 6 | 0 | 6
2026-02-15 | 55 | 6 | 0 | 6
2026-02-16 | 55 | 6 | 0 | 6
2026-02-17 | 57 | 6 | 0 | 6
2026-02-18 | 57 | 6 | 0 | 6
2026-02-19 | 57 | 6 | 0 | 6
2026-02-20 | 57 | 6 | 0 | 6
2026-02-21 | 58 | 6 | 0 | 6
2026-02-22 | 58 | 6 | 0 | 6
2026-02-23 | 58 | 6 | 0 | 6
2026-02-24 | 60 | 6 | 0 | 6
2026-02-25 | 59 | 6 | 0 | 6
2026-02-26 | 59 | 6 | 0 | 6
2026-02-27 | 59 | 6 | 0 | 6
2026-02-28 | 57 | 2 | 0 | 6
2026-03-01 | 57 | 2 | 0 | 6
2026-03-02 | 57 | 4 | 0 | 6
2026-03-03 | 57 | 4 | 0 | 6
2026-03-04 | 57 | 4 | 0 | 6
2026-03-05 | 57 | 4 | 0 | 6
2026-03-06 | 57 | 4 | 0 | 6
2026-03-07 | 57 | 4 | 0 | 6
2026-03-08 | 57 | 4 | 0 | 6
2026-03-09 | 57 | 4 | 0 | 6
2026-03-10 | 57 | 4 | 0 | 6
2026-03-11 | 57 | 4 | 0 | 6
2026-03-12 | 57 | 4 | 0 | 6
2026-03-13 | 56 | 4 | 0 | 6
2026-03-14 | 56 | 4 | 0 | 6
2026-03-15 | 56 | 4 | 0 | 6
2026-03-16 | 55 | 4 | 0 | 6
2026-03-17 | 56 | 4 | 0 | 6
2026-03-18 | 55 | 4 | 0 | 6
2026-03-19 | 52 | 4 | 0 | 6
2026-03-20 | 52 | 4 | 0 | 6
2026-03-21 | 52 | 4 | 0 | 6
2026-03-22 | 52 | 4 | 0 | 6
2026-03-23 | 52 | 4 | 0 | 6
2026-03-24 | 52 | 4 | 0 | 6
2026-03-25 | 52 | 4 | 0 | 6
2026-03-26 | 52 | 4 | 0 | 6
2026-03-27 | 52 | 4 | 0 | 6
2026-03-28 | 52 | 4 | 0 | 6
2026-03-29 | 52 | 4 | 0 | 6
2026-03-30 | 51 | 4 | 0 | 6
2026-03-31 | 50 | 4 | 0 | 2
2026-04-01 | 50 | 4 | 0 | 2
2026-04-02 | 54 | 10 | 2 | 5
2026-04-03 | 54 | 10 | 2 | 5
2026-04-04 | 54 | 10 | 2 | 5
2026-04-05 | 54 | 10 | 2 | 5
2026-04-06 | 54 | 10 | 2 | 5
2026-04-07 | 54 | 10 | 2 | 5
2026-04-08 | 54 | 10 | 2 | 5
2026-04-09 | 54 | 10 | 2 | 5
2026-04-10 | 54 | 10 | 2 | 5
2026-04-11 | 54 | 10 | 2 | 5
2026-04-12 | 54 | 10 | 2 | 5
2026-04-13 | 54 | 10 | 2 | 5
2026-04-14 | 54 | 10 | 2 | 5
2026-04-15 | 54 | 10 | 2 | 5
2026-04-16 | 57 | 14 | 2 | 5
2026-04-17 | 57 | 14 | 2 | 5
2026-04-18 | 57 | 14 | 2 | 5
2026-04-19 | 57 | 14 | 2 | 5
2026-04-20 | 57 | 14 | 2 | 5
2026-04-21 | 57 | 14 | 2 | 5
2026-04-22 | 57 | 14 | 2 | 5
2026-04-23 | 57 | 15 | 2 | 5
2026-04-24 | 57 | 15 | 2 | 5
2026-04-25 | 57 | 15 | 2 | 5
2026-04-26 | 57 | 15 | 2 | 5
2026-04-27 | 57 | 15 | 2 | 5
2026-04-28 | 57 | 15 | 2 | 5
2026-04-29 | 57 | 15 | 2 | 5
2026-04-30 | 53 | 15 | 2 | 4
2026-05-01 | 53 | 15 | 2 | 4
2026-05-02 | 53 | 16 | 2 | 4
2026-05-03 | 53 | 16 | 2 | 4
2026-05-04 | 53 | 16 | 2 | 4
2026-05-05 | 53 | 16 | 2 | 4
2026-05-06 | 53 | 16 | 2 | 4
2026-05-07 | 53 | 16 | 2 | 4
2026-05-08 | 51 | 16 | 2 | 4
2026-05-09 | 51 | 17 | 3 | 5
2026-05-10 | 51 | 17 | 3 | 5
2026-05-11 | 51 | 17 | 2 | 4
2026-05-12 | 51 | 17 | 2 | 4
2026-05-13 | 50 | 17 | 2 | 4
2026-05-14 | 50 | 17 | 2 | 4
2026-05-15 | 48 | 18 | 2 | 4
2026-05-16 | 48 | 18 | 2 | 4
2026-05-17 | 48 | 18 | 2 | 4
2026-05-18 | 48 | 18 | 2 | 4
2026-05-19 | 48 | 19 | 2 | 4
2026-05-20 | 47 | 19 | 2 | 4
2026-05-21 | 46 | 19 | 2 | 4
2026-05-22 | 46 | 19 | 2 | 4
2026-05-23 | 46 | 19 | 2 | 4
2026-05-24 | 46 | 19 | 2 | 4
2026-05-25 | 46 | 19 | 2 | 4
2026-05-26 | 46 | 20 | 2 | 4
2026-05-27 | 46 | 20 | 2 | 4
2026-05-28 | 46 | 20 | 2 | 4
2026-05-29 | 46 | 20 | 2 | 4
2026-05-30 | 46 | 20 | 2 | 4
2026-05-31 | 39 | 19 | 2 | 4
2026-06-01 | 39 | 19 | 2 | 4
2026-06-02 | 39 | 20 | 3 | 5
2026-06-03 | 39 | 20 | 3 | 5
2026-06-04 | 39 | 20 | 3 | 5
2026-06-05 | 39 | 20 | 3 | 5
2026-06-06 | 39 | 20 | 3 | 5
2026-06-07 | 39 | 20 | 3 | 5
2026-06-08 | 39 | 20 | 3 | 5
2026-06-09 | 39 | 20 | 3 | 5
2026-06-10 | 39 | 20 | 3 | 5
2026-06-11 | 39 | 20 | 3 | 5
2026-06-12 | 39 | 20 | 3 | 5
2026-06-13 | 39 | 20 | 3 | 5
2026-06-14 | 39 | 20 | 3 | 5
2026-06-15 | 36 | 16 | 3 | 4
2026-06-16 | 36 | 17 | 3 | 4
2026-06-17 | 34 | 17 | 3 | 4
2026-06-18 | 34 | 17 | 3 | 4
2026-06-19 | 34 | 17 | 3 | 4
2026-06-20 | 34 | 17 | 3 | 4
2026-06-21 | 34 | 17 | 3 | 4
2026-06-22 | 34 | 16 | 3 | 4
2026-06-23 | 34 | 16 | 3 | 4
2026-06-24 | 34 | 16 | 3 | 4
2026-06-25 | 34 | 16 | 3 | 4
2026-06-26 | 34 | 16 | 3 | 4
2026-06-27 | 34 | 16 | 3 | 4
2026-06-28 | 34 | 16 | 3 | 4
2026-06-29 | 34 | 16 | 3 | 4
2026-06-30 | 30 | 10 | 1 | 2
2026-07-01 | 30 | 9 | 0 | 1
2026-07-02 | 30 | 9 | 0 | 1
2026-07-03 | 30 | 9 | 0 | 1
2026-07-04 | 30 | 9 | 0 | 1
2026-07-05 | 30 | 9 | 0 | 1
2026-07-06 | 30 | 9 | 0 | 1
2026-07-07 | 30 | 9 | 0 | 1
2026-07-08 | 30 | 9 | 0 | 1
2026-07-09 | 30 | 9 | 0 | 1
2026-07-10 | 30 | 9 | 0 | 1
2026-07-11 | 30 | 9 | 0 | 1
2026-07-12 | 30 | 9 | 0 | 1
2026-07-13 | 30 | 9 | 0 | 1
2026-07-14 | 30 | 10 | 0 | 1
2026-07-15 | 30 | 10 | 0 | 1
2026-07-16 | 30 | 11 | 0 | 1
2026-07-17 | 30 | 11 | 0 | 1
2026-07-18 | 30 | 11 | 0 | 1
2026-07-19 | 30 | 11 | 0 | 1
2026-07-20 | 30 | 11 | 0 | 1
2026-07-21 | 30 | 11 | 0 | 1
2026-07-22 | 30 | 11 | 0 | 1
2026-07-23 | 30 | 11 | 0 | 1
2026-07-24 | 30 | 11 | 0 | 1
2026-07-25 | 30 | 11 | 0 | 1
2026-07-26 | 30 | 11 | 0 | 1
2026-07-27 | 30 | 11 | 0 | 1
2026-07-28 | 30 | 11 | 0 | 1
2026-07-29 | 30 | 10 | 0 | 1
2026-07-30 | 30 | 10 | 0 | 1
2026-07-31 | 30 | 9 | 0 | 1
2026-08-01 | 30 | 9 | 0 | 1
2026-08-02 | 30 | 9 | 0 | 1
2026-08-03 | 30 | 9 | 0 | 1
2026-08-04 | 30 | 9 | 0 | 1
2026-08-05 | 30 | 9 | 0 | 1
2026-08-06 | 30 | 9 | 0 | 1
2026-08-07 | 30 | 9 | 0 | 1
2026-08-08 | 30 | 9 | 0 | 1
2026-08-09 | 30 | 9 | 0 | 1
2026-08-10 | 30 | 9 | 0 | 1
2026-08-11 | 30 | 9 | 0 | 1
2026-08-12 | 30 | 9 | 0 | 1
2026-08-13 | 30 | 9 | 0 | 1
2026-08-14 | 30 | 8 | 0 | 1
2026-08-15 | 30 | 8 | 0 | 1
2026-08-16 | 30 | 8 | 0 | 1
2026-08-17 | 30 | 8 | 0 | 1
2026-08-18 | 30 | 8 | 0 | 1
2026-08-19 | 30 | 8 | 0 | 1
2026-08-20 | 30 | 8 | 0 | 1
2026-08-21 | 30 | 8 | 0 | 1
2026-08-22 | 30 | 8 | 0 | 1
2026-08-23 | 30 | 8 | 0 | 1
2026-08-24 | 30 | 8 | 0 | 1
2026-08-25 | 30 | 8 | 0 | 1
2026-08-26 | 30 | 8 | 0 | 1
2026-08-27 | 30 | 8 | 0 | 1
2026-08-28 | 30 | 8 | 0 | 1
2026-08-29 | 30 | 8 | 0 | 1
2026-08-30 | 30 | 8 | 0 | 1
2026-08-31 | 30 | 5 | 0 | 1
2026-09-01 | 30 | 5 | 0 | 1
2026-09-02 | 30 | 5 | 0 | 1
2026-09-03 | 30 | 5 | 0 | 1
2026-09-04 | 30 | 5 | 0 | 1
2026-09-05 | 30 | 5 | 0 | 1
2026-09-06 | 30 | 5 | 0 | 1
2026-09-07 | 30 | 5 | 0 | 1
2026-09-08 | 30 | 4 | 0 | 1
2026-09-09 | 30 | 4 | 0 | 1
2026-09-10 | 30 | 4 | 0 | 1
2026-09-11 | 30 | 4 | 0 | 1
2026-09-12 | 30 | 4 | 0 | 1
2026-09-13 | 30 | 4 | 0 | 1
2026-09-14 | 30 | 4 | 0 | 1
2026-09-15 | 30 | 4 | 0 | 1
2026-09-16 | 30 | 4 | 0 | 1
2026-09-17 | 30 | 4 | 0 | 1
2026-09-18 | 30 | 4 | 0 | 1
2026-09-19 | 30 | 4 | 0 | 1
2026-09-20 | 30 | 4 | 0 | 1
2026-09-21 | 30 | 4 | 0 | 1
2026-09-22 | 30 | 4 | 0 | 1
2026-09-23 | 30 | 4 | 0 | 1
2026-09-24 | 30 | 4 | 0 | 1
2026-09-25 | 30 | 4 | 0 | 1
2026-09-26 | 30 | 4 | 0 | 1
2026-09-27 | 30 | 4 | 0 | 1
2026-09-28 | 30 | 4 | 0 | 1
2026-09-29 | 30 | 4 | 0 | 1
2026-09-30 | 23 | 3 | 0 | 1
2026-10-01 | 23 | 3 | 0 | 1
2026-10-02 | 23 | 3 | 0 | 1
2026-10-03 | 23 | 3 | 0 | 1
2026-10-04 | 23 | 3 | 0 | 1
2026-10-05 | 23 | 3 | 0 | 1
2026-10-06 | 23 | 3 | 0 | 1
2026-10-07 | 23 | 3 | 0 | 1
2026-10-08 | 23 | 3 | 0 | 1
2026-10-09 | 23 | 3 | 0 | 1
2026-10-10 | 23 | 3 | 0 | 1
2026-10-11 | 23 | 3 | 0 | 1
2026-10-12 | 23 | 3 | 0 | 1
2026-10-13 | 23 | 3 | 0 | 1
2026-10-14 | 23 | 3 | 0 | 1
2026-10-15 | 23 | 3 | 0 | 1
2026-10-16 | 23 | 4 | 0 | 1
2026-10-17 | 23 | 4 | 0 | 1
2026-10-18 | 23 | 4 | 0 | 1
2026-10-19 | 23 | 4 | 0 | 1
2026-10-20 | 23 | 4 | 0 | 1
2026-10-21 | 23 | 4 | 0 | 1
2026-10-22 | 23 | 4 | 0 | 1
2026-10-23 | 23 | 4 | 0 | 1
2026-10-24 | 23 | 4 | 0 | 1
2026-10-25 | 23 | 4 | 0 | 1
2026-10-26 | 23 | 4 | 0 | 1
2026-10-27 | 23 | 4 | 0 | 1
2026-10-28 | 23 | 4 | 0 | 1
2026-10-29 | 23 | 4 | 0 | 1
2026-10-30 | 23 | 4 | 0 | 1
2026-10-31 | 23 | 4 | 0 | 1
2026-11-01 | 23 | 4 | 0 | 1
2026-11-02 | 23 | 4 | 0 | 1
2026-11-03 | 23 | 4 | 0 | 1
2026-11-04 | 23 | 4 | 0 | 1
2026-11-05 | 23 | 4 | 0 | 1
2026-11-06 | 23 | 4 | 0 | 1
2026-11-07 | 23 | 4 | 0 | 1
2026-11-08 | 23 | 4 | 0 | 1
2026-11-09 | 23 | 4 | 0 | 1
2026-11-10 | 23 | 4 | 0 | 1
2026-11-11 | 23 | 4 | 0 | 1
2026-11-12 | 23 | 4 | 0 | 1
2026-11-13 | 23 | 4 | 0 | 1
2026-11-14 | 23 | 4 | 0 | 1
2026-11-15 | 23 | 4 | 0 | 1
2026-11-16 | 23 | 4 | 0 | 1
2026-11-17 | 23 | 4 | 0 | 1
2026-11-18 | 23 | 4 | 0 | 1
2026-11-19 | 23 | 4 | 0 | 1
2026-11-20 | 23 | 4 | 0 | 1
2026-11-21 | 23 | 4 | 0 | 1
2026-11-22 | 23 | 4 | 0 | 1
2026-11-23 | 23 | 4 | 0 | 1
2026-11-24 | 23 | 4 | 0 | 1
2026-11-25 | 23 | 4 | 0 | 1
2026-11-26 | 23 | 4 | 0 | 1
2026-11-27 | 23 | 4 | 0 | 1
2026-11-28 | 23 | 4 | 0 | 1
2026-11-29 | 23 | 4 | 0 | 1
2026-11-30 | 23 | 4 | 0 | 1
2026-12-01 | 23 | 4 | 0 | 1
2026-12-02 | 23 | 4 | 0 | 1
2026-12-03 | 23 | 4 | 0 | 1
2026-12-04 | 23 | 4 | 0 | 1
2026-12-05 | 23 | 4 | 0 | 1
2026-12-06 | 23 | 4 | 0 | 1
2026-12-07 | 23 | 4 | 0 | 1
2026-12-08 | 23 | 4 | 0 | 1
2026-12-09 | 23 | 4 | 0 | 1
2026-12-10 | 23 | 4 | 0 | 1
2026-12-11 | 23 | 4 | 0 | 1
2026-12-12 | 23 | 4 | 0 | 1
2026-12-13 | 23 | 4 | 0 | 1
2026-12-14 | 23 | 4 | 0 | 1
2026-12-15 | 23 | 4 | 0 | 1
2026-12-16 | 23 | 4 | 0 | 1
2026-12-17 | 23 | 4 | 0 | 1
2026-12-18 | 23 | 4 | 0 | 1
2026-12-19 | 23 | 4 | 0 | 1
2026-12-20 | 23 | 4 | 0 | 1
2026-12-21 | 23 | 4 | 0 | 1
2026-12-22 | 23 | 4 | 0 | 1
2026-12-23 | 23 | 3 | 0 | 1
2026-12-24 | 23 | 3 | 0 | 1
2026-12-25 | 23 | 3 | 0 | 1
2026-12-26 | 23 | 3 | 0 | 1
2026-12-27 | 23 | 3 | 0 | 1
2026-12-28 | 23 | 3 | 0 | 1
2026-12-29 | 23 | 3 | 0 | 1
2026-12-30 | 23 | 3 | 0 | 1
2026-12-31 | 22 | 0 | 0 | 1
2027-01-01 | 22 | 0 | 0 | 1

## task_table_13_4_26 (hidden)
Initiative | Process | Phase | Process level | Process Group | % Arbeit abgeschlossen | IT Process Consultant | IT Process Initiative Lead | IT Process Manager | Start | Finish | Dauer2 | Process Approval Date | Planned phase | Associated Process on L1 | Comment | Text19 | LookupKey
Corporate IT body | Manage IT strategy | Total | L1 | MP | 50% |  |  |  | 2026-02-02 | 2026-07-29 | 128 | 2026-05-06 |  | Manage IT strategy |  |  | Corporate IT body♦Manage IT strategy♦Total♦L1♦MP
Corporate IT body | Manage IT strategy | Elaboration | L1 | MP | 50% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-02-02 | 2026-04-30 | 64 |  | Elaboration in progress | Manage IT strategy |  |  | Corporate IT body♦Manage IT strategy♦Elaboration♦L1♦MP
Corporate IT body | Manage IT strategy | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-14 | 2026-07-29 | 55 |  | Scheduled | Manage IT strategy |  |  | Corporate IT body♦Manage IT strategy♦Implementation LIS♦L1♦MP
Corporate IT body | Manage IT strategy | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT strategy |  |  | Corporate IT body♦Manage IT strategy♦Implementation COT♦L1♦MP
Corporate IT body | Manage IT strategy | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT strategy |  |  | Corporate IT body♦Manage IT strategy♦Implementation LUS♦L1♦MP
Corporate IT body | Manage IT governance framework | Total | L1 | MP | 50% |  |  |  | 2026-01-07 | 2026-08-31 | 169 |  |  | Manage IT governance framework |  |  | Corporate IT body♦Manage IT governance framework♦Total♦L1♦MP
Corporate IT body | Manage IT governance framework | Elaboration | L1 | MP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-03-16 | 2026-05-21 | 49 |  | Elaboration in progress | Manage IT governance framework |  |  | Corporate IT body♦Manage IT governance framework♦Elaboration♦L1♦MP
Corporate IT body | Manage IT governance framework | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-25 | 2026-08-31 | 71 |  | Scheduled | Manage IT governance framework |  |  | Corporate IT body♦Manage IT governance framework♦Implementation LIS♦L1♦MP
Corporate IT body | Manage IT governance framework | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT governance framework |  |  | Corporate IT body♦Manage IT governance framework♦Implementation COT♦L1♦MP
Corporate IT body | Manage IT governance framework | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT governance framework |  |  | Corporate IT body♦Manage IT governance framework♦Implementation LUS♦L1♦MP
Corporate IT body | Maintain IT glossary | Total | L2 | MP | 25% |  |  |  | 2026-01-07 | 2026-01-17 | 8 |  |  | Manage IT governance framework |  |  | Corporate IT body♦Maintain IT glossary♦Total♦L2♦MP
Corporate IT body | Maintain IT glossary | Elaboration | L2 | MP | 25% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 |  | 0 |  |  | Manage IT governance framework |  |  | Corporate IT body♦Maintain IT glossary♦Elaboration♦L2♦MP
Corporate IT body | Maintain IT glossary | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-01-07 | 2026-01-17 | 7 |  | Implementation LIS Done | Manage IT governance framework |  |  | Corporate IT body♦Maintain IT glossary♦Implementation LIS♦L2♦MP
Corporate IT body | Maintain IT glossary | Implementation COT | L2 | MP | 0% |  |  |  | 2026-01-07 |  | 0 |  |  | Manage IT governance framework |  |  | Corporate IT body♦Maintain IT glossary♦Implementation COT♦L2♦MP
Corporate IT body | Maintain IT glossary | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT governance framework |  |  | Corporate IT body♦Maintain IT glossary♦Implementation LUS♦L2♦MP
Corporate IT body | Manage enterprise architecture | Total | L1 | MP | 0% |  |  |  | 2025-10-16 | 2026-07-16 | 195.85 |  |  | Manage enterprise architecture |  |  | Corporate IT body♦Manage enterprise architecture♦Total♦L1♦MP
ITSM | Manage IT portfolio | Total | L1 | MP | 78% |  |  |  | 2025-11-10 | 2026-05-15 | 135 |  |  | Manage IT portfolio |  |  | ITSM♦Manage IT portfolio♦Total♦L1♦MP
ITSM | Manage IT portfolio | Elaboration | L1 | MP | 100% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) |  |  | 2025-11-11 | 2026-01-29 | 58 |  | Elaboration Done | Manage IT portfolio |  |  | ITSM♦Manage IT portfolio♦Elaboration♦L1♦MP
ITSM | Manage IT portfolio | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT portfolio |  |  | ITSM♦Manage IT portfolio♦Implementation LIS♦L1♦MP
ITSM | Manage IT portfolio | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT portfolio |  |  | ITSM♦Manage IT portfolio♦Implementation COT♦L1♦MP
ITSM | Manage IT portfolio | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT portfolio |  |  | ITSM♦Manage IT portfolio♦Implementation LUS♦L1♦MP
IT project management | Manage IT project portfolio | Total | L2 | MP | 100% |  |  |  | 2025-11-10 | 2026-05-31 | 145 |  |  | Manage IT portfolio |  |  | IT project management♦Manage IT project portfolio♦Total♦L2♦MP
IT project management | Manage IT project portfolio | Elaboration | L2 | MP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-10 | 2025-12-10 | 23 | 2026-01-28 | Elaboration Done | Manage IT portfolio |  |  | IT project management♦Manage IT project portfolio♦Elaboration♦L2♦MP
IT project management | Manage IT project portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-02-01 | 2026-05-31 | 85 |  | Implementation LIS | Manage IT portfolio |  |  | IT project management♦Manage IT project portfolio♦Implementation LIS♦L2♦MP
IT project management | Manage IT project portfolio | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT portfolio |  |  | IT project management♦Manage IT project portfolio♦Implementation COT♦L2♦MP
IT project management | Manage IT project portfolio | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT portfolio |  |  | IT project management♦Manage IT project portfolio♦Implementation LUS♦L2♦MP
ITSM | Manage IT service portfolio | Total | L2 | MP | 50% |  |  |  | 2026-04-01 | 2026-09-08 | 115 |  |  | Manage IT portfolio |  |  | ITSM♦Manage IT service portfolio♦Total♦L2♦MP
ITSM | Manage IT service portfolio | Elaboration | L2 | MP | 50% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Ceilia Roser (LIS) | Reiner Heiko (HAU-ITSA) | 2026-04-01 | 2026-06-15 | 54 |  | Elaboration in progress | Manage IT portfolio | Uwe Kranich is second responsible; 16.06. Vorstellung Comittee |  | ITSM♦Manage IT service portfolio♦Elaboration♦L2♦MP
ITSM | Manage IT service portfolio | Implementation LIS | L2 | MP | 0% |  |  |  | 2026-06-15 | 2026-09-08 | 62 |  | Scheduled | Manage IT portfolio |  |  | ITSM♦Manage IT service portfolio♦Implementation LIS♦L2♦MP
ITSM | Manage IT service portfolio | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT portfolio |  |  | ITSM♦Manage IT service portfolio♦Implementation COT♦L2♦MP
ITSM | Manage IT service portfolio | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT portfolio |  |  | ITSM♦Manage IT service portfolio♦Implementation LUS♦L2♦MP
IT planning and steering | Manage and control IT financials | Total | L1 | MP | 50% |  |  | Moser Mario (LIS-LAH) | 2025-10-15 | 2026-07-31 | 208 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage and control IT financials♦Total♦L1♦MP
IT planning and steering | Manage and control IT financials | Elaboration | L1 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | 2026-04-30 | 142 |  | Elaboration in progress | Manage and control IT financials |  |  | IT planning and steering♦Manage and control IT financials♦Elaboration♦L1♦MP
IT planning and steering | Manage and control IT financials | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-01 | 2026-07-31 | 66 |  | Scheduled | Manage and control IT financials |  |  | IT planning and steering♦Manage and control IT financials♦Implementation LIS♦L1♦MP
IT planning and steering | Manage and control IT financials | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage and control IT financials♦Implementation COT♦L2♦MP
IT planning and steering | Manage and control IT financials | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage and control IT financials♦Implementation LUS♦L1♦MP
IT planning and steering | Create and maintain IT budgets | Total | L2 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Create and maintain IT budgets♦Total♦L2♦MP
IT planning and steering | Create and maintain IT budgets | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Create and maintain IT budgets♦Elaboration♦L2♦MP
IT planning and steering | Create and maintain IT budgets | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Create and maintain IT budgets♦Implementation LIS♦L2♦MP
IT planning and steering | Create and maintain IT budgets | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Create and maintain IT budgets♦Implementation COT♦L2♦MP
IT planning and steering | Create and maintain IT budgets | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Create and maintain IT budgets♦Implementation LUS♦L2♦MP
IT planning and steering | Approve and communicate budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Approve and communicate budget plan♦Total♦L3♦MP
IT planning and steering | Approve and communicate budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Approve and communicate budget plan♦Elaboration♦L3♦MP
IT planning and steering | Approve and communicate budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Approve and communicate budget plan♦Implementation LIS♦L3♦MP
IT planning and steering | Approve and communicate budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Approve and communicate budget plan♦Implementation COT♦L3♦MP
IT planning and steering | Approve and communicate budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Approve and communicate budget plan♦Implementation LUS♦L3♦MP
IT planning and steering | Collect and consolidate budget from stakeholders | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Collect and consolidate budget from stakeholders♦Total♦L3♦MP
IT planning and steering | Collect and consolidate budget from stakeholders | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Collect and consolidate budget from stakeholders♦Elaboration♦L3♦MP
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Collect and consolidate budget from stakeholders♦Implementation LIS♦L3♦MP
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Collect and consolidate budget from stakeholders♦Implementation COT♦L3♦MP
IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Collect and consolidate budget from stakeholders♦Implementation LUS♦L3♦MP
IT planning and steering | Develop preliminary budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Develop preliminary budget plan♦Total♦L3♦MP
IT planning and steering | Develop preliminary budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Develop preliminary budget plan♦Elaboration♦L3♦MP
IT planning and steering | Develop preliminary budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Develop preliminary budget plan♦Implementation LIS♦L3♦MP
IT planning and steering | Develop preliminary budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Develop preliminary budget plan♦Implementation COT♦L3♦MP
IT planning and steering | Develop preliminary budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Develop preliminary budget plan♦Implementation LUS♦L3♦MP
IT planning and steering | Maintan and adjust budget | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Maintan and adjust budget♦Total♦L3♦MP
IT planning and steering | Maintan and adjust budget | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Maintan and adjust budget♦Elaboration♦L3♦MP
IT planning and steering | Maintan and adjust budget | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Maintan and adjust budget♦Implementation LIS♦L3♦MP
IT planning and steering | Maintan and adjust budget | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Maintan and adjust budget♦Implementation COT♦L3♦MP
IT planning and steering | Maintan and adjust budget | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Maintan and adjust budget♦Implementation LUS♦L3♦MP
IT planning and steering | Review budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  | 18 | Manage and control IT financials |  |  | IT planning and steering♦Review budget plan♦Total♦L3♦MP
IT planning and steering | Review budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Review budget plan♦Elaboration♦L3♦MP
IT planning and steering | Review budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Review budget plan♦Implementation LIS♦L3♦MP
IT planning and steering | Review budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Review budget plan♦Implementation COT♦L3♦MP
IT planning and steering | Review budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Review budget plan♦Implementation LUS♦L3♦MP
IT planning and steering | Revise and optimize budget plan | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Revise and optimize budget plan♦Total♦L3♦MP
IT planning and steering | Revise and optimize budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Revise and optimize budget plan♦Elaboration♦L3♦MP
IT planning and steering | Revise and optimize budget plan | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Revise and optimize budget plan♦Implementation LIS♦L3♦MP
IT planning and steering | Revise and optimize budget plan | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Revise and optimize budget plan♦Implementation COT♦L3♦MP
IT planning and steering | Revise and optimize budget plan | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Revise and optimize budget plan♦Implementation LUS♦L3♦MP
IT planning and steering | Manage finance and accounting | Total | L2 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage finance and accounting♦Total♦L2♦MP
IT planning and steering | Manage finance and accounting | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage finance and accounting♦Elaboration♦L2♦MP
IT planning and steering | Manage finance and accounting | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage finance and accounting♦Implementation LIS♦L2♦MP
IT planning and steering | Manage finance and accounting | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage finance and accounting♦Implementation COT♦L2♦MP
IT planning and steering | Manage finance and accounting | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage finance and accounting♦Implementation LUS♦L2♦MP
IT planning and steering | Define financial management framework | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define financial management framework♦Total♦L3♦MP
IT planning and steering | Define financial management framework | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define financial management framework♦Elaboration♦L3♦MP
IT planning and steering | Define financial management framework | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define financial management framework♦Implementation LIS♦L3♦MP
IT planning and steering | Define financial management framework | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define financial management framework♦Implementation COT♦L3♦MP
IT planning and steering | Define financial management framework | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define financial management framework♦Implementation LUS♦L3♦MP
IT planning and steering | Establish financial accounting structure | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish financial accounting structure♦Total♦L3♦MP
IT planning and steering | Establish financial accounting structure | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish financial accounting structure♦Elaboration♦L3♦MP
IT planning and steering | Establish financial accounting structure | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish financial accounting structure♦Implementation LIS♦L3♦MP
IT planning and steering | Establish financial accounting structure | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish financial accounting structure♦Implementation COT♦L3♦MP
IT planning and steering | Establish financial accounting structure | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish financial accounting structure♦Implementation LUS♦L3♦MP
IT planning and steering | Manage IT costs | Total | L2 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage IT costs♦Total♦L2♦MP
IT planning and steering | Manage IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage IT costs♦Elaboration♦L2♦MP
IT planning and steering | Manage IT costs | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage IT costs♦Implementation LIS♦L2♦MP
IT planning and steering | Manage IT costs | Implementation COT |  | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage IT costs♦Implementation COT♦♦MP
IT planning and steering | Manage IT costs | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Manage IT costs♦Implementation LUS♦L2♦MP
IT planning and steering | Compare actual cost to budget forecast | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Compare actual cost to budget forecast♦Total♦L3♦MP
IT planning and steering | Compare actual cost to budget forecast | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Compare actual cost to budget forecast♦Elaboration♦L3♦MP
IT planning and steering | Compare actual cost to budget forecast | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Compare actual cost to budget forecast♦Implementation LIS♦L3♦MP
IT planning and steering | Compare actual cost to budget forecast | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Compare actual cost to budget forecast♦Implementation COT♦L3♦MP
IT planning and steering | Compare actual cost to budget forecast | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Compare actual cost to budget forecast♦Implementation LUS♦L3♦MP
IT planning and steering | Initiate corrective or preventive actions | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Initiate corrective or preventive actions♦Total♦L3♦MP
IT planning and steering | Initiate corrective or preventive actions | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Initiate corrective or preventive actions♦Elaboration♦L3♦MP
IT planning and steering | Initiate corrective or preventive actions | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Initiate corrective or preventive actions♦Implementation LIS♦L3♦MP
IT planning and steering | Initiate corrective or preventive actions | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Initiate corrective or preventive actions♦Implementation COT♦L3♦MP
IT planning and steering | Initiate corrective or preventive actions | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Initiate corrective or preventive actions♦Implementation LUS♦L3♦MP
IT planning and steering | Report actual IT costs | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Report actual IT costs♦Total♦L3♦MP
IT planning and steering | Report actual IT costs | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Report actual IT costs♦Elaboration♦L3♦MP
IT planning and steering | Report actual IT costs | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Report actual IT costs♦Implementation LIS♦L3♦MP
IT planning and steering | Report actual IT costs | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Report actual IT costs♦Implementation COT♦L3♦MP
IT planning and steering | Report actual IT costs | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Report actual IT costs♦Implementation LUS♦L3♦MP
IT planning and steering | Model and allocate IT costs | Total | L2 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Model and allocate IT costs♦Total♦L2♦MP
IT planning and steering | Model and allocate IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Model and allocate IT costs♦Elaboration♦L2♦MP
IT planning and steering | Model and allocate IT costs | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Model and allocate IT costs♦Implementation LIS♦L2♦MP
IT planning and steering | Model and allocate IT costs | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Model and allocate IT costs♦Implementation COT♦L2♦MP
IT planning and steering | Model and allocate IT costs | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Model and allocate IT costs♦Implementation LUS♦L2♦MP
IT planning and steering | Apply cost model to calculate service cost per unit | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Apply cost model to calculate service cost per unit♦Total♦L3♦MP
IT planning and steering | Apply cost model to calculate service cost per unit | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Apply cost model to calculate service cost per unit♦Elaboration♦L3♦MP
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Apply cost model to calculate service cost per unit♦Implementation LIS♦L3♦MP
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Apply cost model to calculate service cost per unit♦Implementation COT♦L3♦MP
IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Apply cost model to calculate service cost per unit♦Implementation LUS♦L3♦MP
IT planning and steering | Implement cost allocation to stakeholders or companies | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Implement cost allocation to stakeholders or companies♦Total♦L3♦MP
IT planning and steering | Implement cost allocation to stakeholders or companies | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Implement cost allocation to stakeholders or companies♦Elaboration♦L3♦MP
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Implement cost allocation to stakeholders or companies♦Implementation LIS♦L3♦MP
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Implement cost allocation to stakeholders or companies♦Implementation COT♦L3♦MP
IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Implement cost allocation to stakeholders or companies♦Implementation LUS♦L3♦MP
IT planning and steering | Define cost allocation principles | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define cost allocation principles♦Total♦L3♦MP
IT planning and steering | Define cost allocation principles | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define cost allocation principles♦Elaboration♦L3♦MP
IT planning and steering | Define cost allocation principles | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define cost allocation principles♦Implementation LIS♦L3♦MP
IT planning and steering | Define cost allocation principles | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define cost allocation principles♦Implementation COT♦L3♦MP
IT planning and steering | Define cost allocation principles | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Define cost allocation principles♦Implementation LUS♦L3♦MP
IT planning and steering | Establish cost allocation model | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish cost allocation model♦Total♦L3♦MP
IT planning and steering | Establish cost allocation model | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish cost allocation model♦Elaboration♦L3♦MP
IT planning and steering | Establish cost allocation model | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish cost allocation model♦Implementation LIS♦L3♦MP
IT planning and steering | Establish cost allocation model | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish cost allocation model♦Implementation COT♦L3♦MP
IT planning and steering | Establish cost allocation model | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Establish cost allocation model♦Implementation LUS♦L3♦MP
IT planning and steering | Gather relevant cost and consumption data | Total | L3 | MP | 50% |  |  |  | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Gather relevant cost and consumption data♦Total♦L3♦MP
IT planning and steering | Gather relevant cost and consumption data | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 |  | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Gather relevant cost and consumption data♦Elaboration♦L3♦MP
IT planning and steering | Gather relevant cost and consumption data | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Gather relevant cost and consumption data♦Implementation LIS♦L3♦MP
IT planning and steering | Gather relevant cost and consumption data | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Gather relevant cost and consumption data♦Implementation COT♦L3♦MP
IT planning and steering | Gather relevant cost and consumption data | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage and control IT financials |  |  | IT planning and steering♦Gather relevant cost and consumption data♦Implementation LUS♦L3♦MP
Corporate IT body | Manage IT stakeholder relationships | Total | L1 | MP | 0% |  |  |  | 2026-04-01 | 2026-12-23 | 191 |  |  | Manage IT stakeholder relationships |  |  | Corporate IT body♦Manage IT stakeholder relationships♦Total♦L1♦MP
Corporate IT body | Manage IT stakeholder relationships | Elaboration | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-06-15 | 54 |  | Elaboration in progress | Manage IT stakeholder relationships |  |  | Corporate IT body♦Manage IT stakeholder relationships♦Elaboration♦L1♦MP
Corporate IT body | Manage IT stakeholder relationships | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-10-15 | 2026-12-23 | 50 |  | Scheduled | Manage IT stakeholder relationships |  |  | Corporate IT body♦Manage IT stakeholder relationships♦Implementation LIS♦L1♦MP
Corporate IT body | Manage IT stakeholder relationships | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT stakeholder relationships |  |  | Corporate IT body♦Manage IT stakeholder relationships♦Implementation COT♦L1♦MP
Corporate IT body | Manage IT stakeholder relationships | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT stakeholder relationships |  |  | Corporate IT body♦Manage IT stakeholder relationships♦Implementation LUS♦L1♦MP
ITSM | Manage IT processes and continuous improvement | Total | L1 | MP | 21% |  |  |  | 2025-10-01 | 2026-05-31 | 173 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage IT processes and continuous improvement♦Total♦L1♦MP
ITSM | Manage IT processes and continuous improvement | Elaboration | L1 | MP | 100% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Manage IT processes and continuous improvement |  |  | ITSM♦Manage IT processes and continuous improvement♦Elaboration♦L1♦MP
ITSM | Manage IT processes and continuous improvement | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage IT processes and continuous improvement♦Implementation LIS♦L1♦MP
ITSM | Manage IT processes and continuous improvement | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage IT processes and continuous improvement♦Implementation COT♦L1♦MP
ITSM | Manage IT processes and continuous improvement | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage IT processes and continuous improvement♦Implementation LUS♦L1♦MP
ITSM | Develop and maintain IT BPM framework | Total | L2 | MP | 100% |  |  |  | 2025-10-15 | 2025-10-16 | 1 | 2025-09-18 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Develop and maintain IT BPM framework♦Total♦L2♦MP
ITSM | Develop and maintain IT BPM framework | Elaboration | L2 | MP | 100% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-08-04 | 2025-08-30 | 20 |  | Elaboration Done | Manage IT processes and continuous improvement |  |  | ITSM♦Develop and maintain IT BPM framework♦Elaboration♦L2♦MP
ITSM | Develop and maintain IT BPM framework | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Develop and maintain IT BPM framework♦Implementation LIS♦L2♦MP
ITSM | Develop and maintain IT BPM framework | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Develop and maintain IT BPM framework♦Implementation COT♦L2♦MP
ITSM | Develop and maintain IT BPM framework | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Develop and maintain IT BPM framework♦Implementation LUS♦L2♦MP
ITSM | Manage continuous improvement | Total | L2 | MP | 0% |  |  |  | 2025-10-01 | 2026-01-30 | 88 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continuous improvement♦Total♦L2♦MP
ITSM | Manage continuous improvement | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-01-30 | 88 |  | Elaboration Done | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continuous improvement♦Elaboration♦L2♦MP
ITSM | Manage continuous improvement | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continuous improvement♦Implementation LIS♦L2♦MP
ITSM | Manage continuous improvement | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continuous improvement♦Implementation COT♦L2♦MP
ITSM | Manage continuous improvement | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continuous improvement♦Implementation LUS♦L2♦MP
ITSM | Manage a common approach to contiual improvement | Total | L3 | MP | 0% |  |  |  |  | 2025-10-16 | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage a common approach to contiual improvement♦Total♦L3♦MP
ITSM | Manage a common approach to contiual improvement | Elaboration | L3 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage a common approach to contiual improvement♦Elaboration♦L3♦MP
ITSM | Manage a common approach to contiual improvement | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage a common approach to contiual improvement♦Implementation LIS♦L3♦MP
ITSM | Manage a common approach to contiual improvement | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage a common approach to contiual improvement♦Implementation COT♦L3♦MP
ITSM | Manage a common approach to contiual improvement | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage a common approach to contiual improvement♦Implementation LUS♦L3♦MP
ITSM | Manage continual improvement initiative | Total | L3 | MP | 0% |  |  |  |  | 2025-10-16 | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continual improvement initiative♦Total♦L3♦MP
ITSM | Manage continual improvement initiative | Elaboration | L3 | MP | 0% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Kuerschner Phillip (LIS) | Reiner Heiko (HAU-ITSA) |  |  | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continual improvement initiative♦Elaboration♦L3♦MP
ITSM | Manage continual improvement initiative | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continual improvement initiative♦Implementation LIS♦L3♦MP
ITSM | Manage continual improvement initiative | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continual improvement initiative♦Implementation COT♦L3♦MP
ITSM | Manage continual improvement initiative | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Manage continual improvement initiative♦Implementation LUS♦L3♦MP
ITSM | Perform operational process management | Total | L2 | MP | 25% |  |  |  | 2025-10-01 | 2026-05-31 | 173 | 2025-09-18 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform operational process management♦Total♦L2♦MP
Corporate IT body | Perform operational process management (V 2.0) | Elaboration | L2 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Manage IT processes and continuous improvement | approximate date |  | Corporate IT body♦Perform operational process management (V 2.0)♦Elaboration♦L2♦MP
ITSM | Perform operational process management | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform operational process management♦Implementation LIS♦L2♦MP
ITSM | Perform operational process management | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform operational process management♦Implementation COT♦L2♦MP
ITSM | Perform operational process management | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform operational process management♦Implementation LUS♦L2♦MP
ITSM | Identify process and determine goals | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | 2025-09-18 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Identify process and determine goals♦Total♦L3♦MP
Corporate IT body | Identify process and determine goals (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Manage IT processes and continuous improvement | approximate date |  | Corporate IT body♦Identify process and determine goals (V 2.0)♦Elaboration♦L3♦MP
ITSM | Identify process and determine goals | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Identify process and determine goals♦Implementation LIS♦L3♦MP
ITSM | Identify process and determine goals | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Identify process and determine goals♦Implementation COT♦L3♦MP
ITSM | Identify process and determine goals | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Identify process and determine goals♦Implementation LUS♦L3♦MP
ITSM | Elaborate to-be process | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | 2025-09-18 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Elaborate to-be process♦Total♦L3♦MP
Corporate IT body | Elaborate to-be process (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Manage IT processes and continuous improvement | approximate date |  | Corporate IT body♦Elaborate to-be process (V 2.0)♦Elaboration♦L3♦MP
ITSM | Elaborate to-be process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Elaborate to-be process♦Implementation LIS♦L3♦MP
ITSM | Elaborate to-be process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Elaborate to-be process♦Implementation COT♦L3♦MP
ITSM | Elaborate to-be process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Elaborate to-be process♦Implementation LUS♦L3♦MP
ITSM | Plan process execution | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | 2025-09-18 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Plan process execution♦Total♦L3♦MP
Corporate IT body | Plan process execution (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Manage IT processes and continuous improvement | approximate date |  | Corporate IT body♦Plan process execution (V 2.0)♦Elaboration♦L3♦MP
ITSM | Plan process execution | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Plan process execution♦Implementation LIS♦L3♦MP
ITSM | Plan process execution | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Plan process execution♦Implementation COT♦L3♦MP
ITSM | Plan process execution | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Plan process execution♦Implementation LUS♦L3♦MP
ITSM | Implement process | Total | L3 | MP | 25% |  |  |  | 2026-01-12 | 2026-05-31 | 100 | 2025-09-19 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Implement process♦Total♦L3♦MP
Corporate IT body | Implement process (V 2.0) | Elaboration | L3 | MP | 25% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Manage IT processes and continuous improvement |  |  | Corporate IT body♦Implement process (V 2.0)♦Elaboration♦L3♦MP
ITSM | Implement process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Implement process♦Implementation LIS♦L3♦MP
ITSM | Implement process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Implement process♦Implementation COT♦L3♦MP
ITSM | Implement process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Implement process♦Implementation LUS♦L3♦MP
ITSM | Perform and measure process | Total | L3 | MP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | 2025-09-18 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform and measure process♦Total♦L3♦MP
Corporate IT body | Perform and measure process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Manage IT processes and continuous improvement | approximate date |  | Corporate IT body♦Perform and measure process♦Elaboration♦L3♦MP
ITSM | Perform and measure process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform and measure process♦Implementation LIS♦L3♦MP
ITSM | Perform and measure process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform and measure process♦Implementation COT♦L3♦MP
ITSM | Perform and measure process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Perform and measure process♦Implementation LUS♦L3♦MP
ITSM | Analyse process | Total | L3 | MP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | 2025-09-18 |  | Manage IT processes and continuous improvement |  |  | ITSM♦Analyse process♦Total♦L3♦MP
Corporate IT body | Analyse process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Manage IT processes and continuous improvement | approximate date |  | Corporate IT body♦Analyse process♦Elaboration♦L3♦MP
ITSM | Analyse process | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Analyse process♦Implementation LIS♦L3♦MP
ITSM | Analyse process | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Analyse process♦Implementation COT♦L3♦MP
ITSM | Analyse process | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT processes and continuous improvement |  |  | ITSM♦Analyse process♦Implementation LUS♦L3♦MP
Central area (Jan Müskens) | Manage IT risks and compliance | Total | L1 | MP | 19% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks and compliance♦Total♦L1♦MP
Central area (Jan Müskens) | Manage IT risks and compliance | Elaboration | L1 | MP | 100% | Kreis Andreas (LLI);Rollinger Alexander (LIS) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦Manage IT risks and compliance♦Elaboration♦L1♦MP
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LIS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks and compliance♦Implementation LIS♦L1♦MP
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation COT | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks and compliance♦Implementation COT♦L1♦MP
Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LUS | L1 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks and compliance♦Implementation LUS♦L1♦MP
Central area (Jan Müskens) | Manage IT risks | Total | L2 | MP | 0% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks♦Total♦L2♦MP
Central area (Jan Müskens) | Manage IT risks | Elaboration | L2 | MP | 0% | Rollinger Alexander (LIS);Moser Mario (LIS-LAH) |  | Monnier Murielle (LEC) |  |  | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks♦Elaboration♦L2♦MP
Central area (Jan Müskens) | Manage IT risks | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks♦Implementation LIS♦L2♦MP
Central area (Jan Müskens) | Manage IT risks | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks♦Implementation COT♦L2♦MP
Central area (Jan Müskens) | Manage IT risks | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT risks♦Implementation LUS♦L2♦MP
Central area (Jan Müskens) | Manage IT compliance | Total | L2 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT compliance♦Total♦L2♦MP
Central area (Jan Müskens) | Manage IT compliance | Elaboration | L2 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦Manage IT compliance♦Elaboration♦L2♦MP
Central area (Jan Müskens) | Manage IT compliance | Implementation LIS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT compliance♦Implementation LIS♦L2♦MP
Central area (Jan Müskens) | Manage IT compliance | Implementation COT | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT compliance♦Implementation COT♦L2♦MP
Central area (Jan Müskens) | Manage IT compliance | Implementation LUS | L2 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT compliance♦Implementation LUS♦L2♦MP
Central area (Jan Müskens) | Monitor to delegate | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Monitor to delegate♦Total♦L3♦MP
Central area (Jan Müskens) | Monitor to delegate | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦Monitor to delegate♦Elaboration♦L3♦MP
Central area (Jan Müskens) | Monitor to delegate | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Monitor to delegate♦Implementation LIS♦L3♦MP
Central area (Jan Müskens) | Monitor to delegate | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Monitor to delegate♦Implementation COT♦L3♦MP
Central area (Jan Müskens) | Monitor to delegate | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Monitor to delegate♦Implementation LUS♦L3♦MP
Central area (Jan Müskens) | Requirements to measures | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Requirements to measures♦Total♦L3♦MP
Central area (Jan Müskens) | Requirements to measures | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦Requirements to measures♦Elaboration♦L3♦MP
Central area (Jan Müskens) | Requirements to measures | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Requirements to measures♦Implementation LIS♦L3♦MP
Central area (Jan Müskens) | Requirements to measures | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Requirements to measures♦Implementation COT♦L3♦MP
Central area (Jan Müskens) | Requirements to measures | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Requirements to measures♦Implementation LUS♦L3♦MP
Central area (Jan Müskens) | Implement to improve | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Implement to improve♦Total♦L3♦MP
Central area (Jan Müskens) | Implement to improve | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦Implement to improve♦Elaboration♦L3♦MP
Central area (Jan Müskens) | Implement to improve | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Implement to improve♦Implementation LIS♦L3♦MP
Central area (Jan Müskens) | Implement to improve | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Implement to improve♦Implementation COT♦L3♦MP
Central area (Jan Müskens) | Implement to improve | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Implement to improve♦Implementation LUS♦L3♦MP
Central area (Jan Müskens) | Manage IT-C strategy | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C strategy♦Total♦L3♦MP
Central area (Jan Müskens) | Manage IT-C strategy | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦Manage IT-C strategy♦Elaboration♦L3♦MP
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C strategy♦Implementation LIS♦L3♦MP
Central area (Jan Müskens) | Manage IT-C strategy | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C strategy♦Implementation COT♦L3♦MP
Central area (Jan Müskens) | Manage IT-C strategy | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C strategy♦Implementation LUS♦L3♦MP
Central area (Jan Müskens) | Manage IT-C framework | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C framework♦Total♦L3♦MP
Central area (Jan Müskens) | Manage IT-C framework | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦Manage IT-C framework♦Elaboration♦L3♦MP
Central area (Jan Müskens) | Manage IT-C framework | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C framework♦Implementation LIS♦L3♦MP
Central area (Jan Müskens) | Manage IT-C framework | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C framework♦Implementation COT♦L3♦MP
Central area (Jan Müskens) | Manage IT-C framework | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦Manage IT-C framework♦Implementation LUS♦L3♦MP
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Total | L3 | MP | 25% |  |  |  | 2025-10-01 | 2026-09-30 | 261 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦DC/DCC/MSC IT-compliance♦Total♦L3♦MP
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Manage IT risks and compliance | date to be reviewed |  | Central area (Jan Müskens)♦DC/DCC/MSC IT-compliance♦Elaboration♦L3♦MP
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LIS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦DC/DCC/MSC IT-compliance♦Implementation LIS♦L3♦MP
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation COT | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦DC/DCC/MSC IT-compliance♦Implementation COT♦L3♦MP
Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LUS | L3 | MP | 0% | [5 empty] | 0 |  |  | Manage IT risks and compliance |  |  | Central area (Jan Müskens)♦DC/DCC/MSC IT-compliance♦Implementation LUS♦L3♦MP
Corporate IT body | Plan IT service | Total | L1 | CP | 100% |  |  |  | 2025-08-01 | 2026-04-30 | 195 |  |  | Plan IT service |  |  | Corporate IT body♦Plan IT service♦Total♦L1♦CP
Corporate IT body | Plan IT service | Elaboration | L1 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-10-16 | 2025-10-31 | 12 | 2025-12-10 | Elaboration Done | Plan IT service |  |  | Corporate IT body♦Plan IT service♦Elaboration♦L1♦CP
Corporate IT body | Plan IT service | Implementation LIS | L1 | CP | 75% |  |  |  | 2025-11-01 | 2026-02-28 | 85 |  | Implementation LIS Done | Plan IT service |  |  | Corporate IT body♦Plan IT service♦Implementation LIS♦L1♦CP
Corporate IT body | Plan IT service | Implementation COT | L1 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 |  | Implementation COT Done | Plan IT service |  |  | Corporate IT body♦Plan IT service♦Implementation COT♦L1♦CP
Corporate IT body | Plan IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  | Plan IT service |  |  | Corporate IT body♦Plan IT service♦Implementation LUS♦L1♦CP
Corporate IT body | Perform initial assessment of customer need | Total | L2 | CP | 100% |  |  |  | 2025-08-01 | 2025-08-05 | 3 | 2025-08-19 |  | Plan IT service |  |  | Corporate IT body♦Perform initial assessment of customer need♦Total♦L2♦CP
Corporate IT body | Perform initial assessment of customer need | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 |  | Elaboration Done | Plan IT service |  |  | Corporate IT body♦Perform initial assessment of customer need♦Elaboration♦L2♦CP
Corporate IT body | Perform initial assessment of customer need | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-11-01 | 2026-02-28 | 85 |  | Implementation LIS Done | Plan IT service |  |  | Corporate IT body♦Perform initial assessment of customer need♦Implementation LIS♦L2♦CP
Corporate IT body | Perform initial assessment of customer need | Implementation COT | L2 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 |  | Implementation COT Done | Plan IT service |  |  | Corporate IT body♦Perform initial assessment of customer need♦Implementation COT♦L2♦CP
Corporate IT body | Perform initial assessment of customer need | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Plan IT service |  |  | Corporate IT body♦Perform initial assessment of customer need♦Implementation LUS♦L2♦CP
Corporate IT body | Evaluate and qualify IT demand | Total | L2 | CP | 100% |  |  |  | 2025-08-01 | 2026-04-30 | 195 | 2025-12-10 |  | Plan IT service |  |  | Corporate IT body♦Evaluate and qualify IT demand♦Total♦L2♦CP
Corporate IT body | Evaluate and qualify IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 |  | Elaboration Done | Plan IT service |  |  | Corporate IT body♦Evaluate and qualify IT demand♦Elaboration♦L2♦CP
Corporate IT body | Evaluate and qualify IT demand | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-11-01 | 2026-02-28 | 85 |  | Implementation LIS Done | Plan IT service |  |  | Corporate IT body♦Evaluate and qualify IT demand♦Implementation LIS♦L2♦CP
Corporate IT body | Evaluate and qualify IT demand | Implementation COT | L2 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 |  | Implementation COT Done | Plan IT service |  |  | Corporate IT body♦Evaluate and qualify IT demand♦Implementation COT♦L2♦CP
Corporate IT body | Evaluate and qualify IT demand | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Plan IT service |  |  | Corporate IT body♦Evaluate and qualify IT demand♦Implementation LUS♦L2♦CP
Corporate IT body | Analyse architecture impact | Total | L3 | CP | 100% |  |  |  | 2025-08-01 | 2026-04-30 | 195 |  |  | Plan IT service |  |  | Corporate IT body♦Analyse architecture impact♦Total♦L3♦CP
Corporate IT body | Analyse architecture impact | Elaboration | L3 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-10-15 | 54 |  | Elaboration Done | Plan IT service |  |  | Corporate IT body♦Analyse architecture impact♦Elaboration♦L3♦CP
Corporate IT body | Analyse architecture impact | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Plan IT service |  |  | Corporate IT body♦Analyse architecture impact♦Implementation LIS♦L3♦CP
Corporate IT body | Analyse architecture impact | Implementation COT | L3 | CP | 0% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  | Implementation COT | Plan IT service |  |  | Corporate IT body♦Analyse architecture impact♦Implementation COT♦L3♦CP
Corporate IT body | Analyse architecture impact | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Plan IT service |  |  | Corporate IT body♦Analyse architecture impact♦Implementation LUS♦L3♦CP
Corporate IT body | Approve IT demand | Total | L2 | CP | 100% |  |  |  | 2025-08-01 | 2025-08-01 | 1 | 2025-08-19 |  | Plan IT service |  |  | Corporate IT body♦Approve IT demand♦Total♦L2♦CP
Corporate IT body | Approve IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 |  | Elaboration Done | Plan IT service |  |  | Corporate IT body♦Approve IT demand♦Elaboration♦L2♦CP
Corporate IT body | Approve IT demand | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-11-01 | 2026-02-28 | 85 |  | Implementation LIS Done | Plan IT service |  |  | Corporate IT body♦Approve IT demand♦Implementation LIS♦L2♦CP
Corporate IT body | Approve IT demand | Implementation COT | L2 | CP | 0% |  |  |  | 2025-11-03 | 2026-03-31 | 107 |  | Implementation COT Done | Plan IT service |  |  | Corporate IT body♦Approve IT demand♦Implementation COT♦L2♦CP
Corporate IT body | Approve IT demand | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Plan IT service |  |  | Corporate IT body♦Approve IT demand♦Implementation LUS♦L2♦CP
ITSM | Build IT Service | Total | L1 | CP | 41% |  |  |  | 2025-04-01 | 2026-08-31 | 370 |  |  | Build IT Service |  |  | ITSM♦Build IT Service♦Total♦L1♦CP
ITSM | Build IT Service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) |  |  | 0 |  |  | Build IT Service |  |  | ITSM♦Build IT Service♦Elaboration♦L1♦CP
ITSM | Build IT Service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Build IT Service♦Implementation LIS♦L1♦CP
ITSM | Build IT Service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Build IT Service♦Implementation COT♦L1♦CP
ITSM | Build IT Service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Build IT Service♦Implementation LUS♦L1♦CP
ITSM | Design IT service | Total | L2 | CP | 50% |  |  |  | 2025-10-01 | 2026-08-14 | 228 |  |  | Build IT Service |  |  | ITSM♦Design IT service♦Total♦L2♦CP
ITSM | Design IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-02-16 | 2026-05-15 | 65 |  | Elaboration in progress | Build IT Service | approximate date |  | ITSM♦Design IT service♦Elaboration♦L2♦CP
ITSM | Design IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-05-18 | 2026-08-14 | 65 |  | Scheduled | Build IT Service | approximate date |  | ITSM♦Design IT service♦Implementation LIS♦L2♦CP
ITSM | Design IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Design IT service♦Implementation COT♦L2♦CP
ITSM | Design IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Design IT service♦Implementation LUS♦L2♦CP
Architecture management | Define solution target architecture | Total | L3 | CP | 50% |  |  |  | 2026-01-14 | 2026-06-22 | 114 |  |  | Build IT Service |  |  | Architecture management♦Define solution target architecture♦Total♦L3♦CP
Architecture management | Define solution target architecture | Elaboration | L3 | CP | 50% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) | 2026-02-05 | 2026-04-21 | 54 |  | Elaboration in progress | Build IT Service |  |  | Architecture management♦Define solution target architecture♦Elaboration♦L3♦CP
Architecture management | Define solution target architecture | Implementation LIS | L3 | CP | 0% |  |  |  | 2026-04-22 | 2026-06-22 | 44 |  | Scheduled | Build IT Service |  |  | Architecture management♦Define solution target architecture♦Implementation LIS♦L3♦CP
Architecture management | Define solution target architecture | Implementation COT | L3 | CP | 0% |  |  |  | 2026-04-22 | 2026-04-22 | 1 |  | Scheduled | Build IT Service |  |  | Architecture management♦Define solution target architecture♦Implementation COT♦L3♦CP
Architecture management | Define solution target architecture | Implementation LUS | L3 | CP | 0% |  |  |  | 2026-01-14 | 2026-01-14 | 0 |  | Implementation LUS Done | Build IT Service |  |  | Architecture management♦Define solution target architecture♦Implementation LUS♦L3♦CP
Architecture management | Perform software selection | Total | L3 | CP | 100% |  |  |  | 2025-10-01 | 2026-04-30 | 152 | 2025-10-14 |  | Build IT Service |  |  | Architecture management♦Perform software selection♦Total♦L3♦CP
Architecture management | Perform software selection | Elaboration | L3 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 60 |  | Elaboration Done | Build IT Service |  |  | Architecture management♦Perform software selection♦Elaboration♦L3♦CP
Architecture management | Perform software selection | Implementation LIS | L3 | CP | 0% |  |  |  | 2026-02-16 | 2026-04-30 | 54 |  | Implementation LIS | Build IT Service |  |  | Architecture management♦Perform software selection♦Implementation LIS♦L3♦CP
Architecture management | Perform software selection | Implementation COT | L3 | CP | 0% |  |  |  | 2025-10-16 | 2025-12-31 | 55 |  | Implementation COT Done | Build IT Service |  |  | Architecture management♦Perform software selection♦Implementation COT♦L3♦CP
Architecture management | Perform software selection | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Perform software selection♦Implementation LUS♦L3♦CP
Architecture management | Record and plan functional requirements | Total | L4 | CP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  | Build IT Service |  |  | Architecture management♦Record and plan functional requirements♦Total♦L4♦CP
Architecture management | Record and plan functional requirements | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Build IT Service |  |  | Architecture management♦Record and plan functional requirements♦Elaboration♦L4♦CP
Architecture management | Record and plan functional requirements | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Record and plan functional requirements♦Implementation LIS♦L4♦CP
Architecture management | Record and plan functional requirements | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Record and plan functional requirements♦Implementation COT♦L4♦CP
Architecture management | Record and plan functional requirements | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Record and plan functional requirements♦Implementation LUS♦L4♦CP
Architecture management | Conduct market analysis and compile long or short list | Total | L4 | CP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  | Build IT Service |  |  | Architecture management♦Conduct market analysis and compile long or short list♦Total♦L4♦CP
Architecture management | Conduct market analysis and compile long or short list | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Build IT Service |  |  | Architecture management♦Conduct market analysis and compile long or short list♦Elaboration♦L4♦CP
Architecture management | Conduct market analysis and compile long or short list | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Conduct market analysis and compile long or short list♦Implementation LIS♦L4♦CP
Architecture management | Conduct market analysis and compile long or short list | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Conduct market analysis and compile long or short list♦Implementation COT♦L4♦CP
Architecture management | Conduct market analysis and compile long or short list | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Conduct market analysis and compile long or short list♦Implementation LUS♦L4♦CP
Architecture management | Perform vendor use case pitch and usability test | Total | L4 | CP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  | Build IT Service |  |  | Architecture management♦Perform vendor use case pitch and usability test♦Total♦L4♦CP
Architecture management | Perform vendor use case pitch and usability test | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Build IT Service |  |  | Architecture management♦Perform vendor use case pitch and usability test♦Elaboration♦L4♦CP
Architecture management | Perform vendor use case pitch and usability test | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Perform vendor use case pitch and usability test♦Implementation LIS♦L4♦CP
Architecture management | Perform vendor use case pitch and usability test | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Perform vendor use case pitch and usability test♦Implementation COT♦L4♦CP
Architecture management | Perform vendor use case pitch and usability test | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Perform vendor use case pitch and usability test♦Implementation LUS♦L4♦CP
Architecture management | Validate strategic fit | Total | L4 | CP | 100% |  |  |  | 2025-10-01 | 2025-10-02 | 2 | 2025-10-14 |  | Build IT Service |  |  | Architecture management♦Validate strategic fit♦Total♦L4♦CP
Architecture management | Validate strategic fit | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Build IT Service |  |  | Architecture management♦Validate strategic fit♦Elaboration♦L4♦CP
Architecture management | Validate strategic fit | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Validate strategic fit♦Implementation LIS♦L4♦CP
Architecture management | Validate strategic fit | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Validate strategic fit♦Implementation COT♦L4♦CP
Architecture management | Validate strategic fit | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Validate strategic fit♦Implementation LUS♦L4♦CP
Architecture management | Recommendation and EA approval | Total | L4 | CP | 100% |  |  |  | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  | Build IT Service |  |  | Architecture management♦Recommendation and EA approval♦Total♦L4♦CP
Architecture management | Recommendation and EA approval | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Build IT Service |  |  | Architecture management♦Recommendation and EA approval♦Elaboration♦L4♦CP
Architecture management | Recommendation and EA approval | Implementation LIS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Recommendation and EA approval♦Implementation LIS♦L4♦CP
Architecture management | Recommendation and EA approval | Implementation COT | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Recommendation and EA approval♦Implementation COT♦L4♦CP
Architecture management | Recommendation and EA approval | Implementation LUS | L4 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | Architecture management♦Recommendation and EA approval♦Implementation LUS♦L4♦CP
ITSM | Develop and customise IT service | Total | L2 | CP | 0% |  |  |  | 2025-05-26 | 2026-05-15 | 255 |  |  | Build IT Service |  |  | ITSM♦Develop and customise IT service♦Total♦L2♦CP
ITSM | Develop and customise IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-02-16 | 2026-05-15 | 65 |  | Elaboration in progress | Build IT Service | approximate date |  | ITSM♦Develop and customise IT service♦Elaboration♦L2♦CP
ITSM | Develop and customise IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2025-05-26 | 2025-08-15 | 60 |  | Implementation LIS Done | Build IT Service | approximate date |  | ITSM♦Develop and customise IT service♦Implementation LIS♦L2♦CP
ITSM | Develop and customise IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Develop and customise IT service♦Implementation COT♦L2♦CP
ITSM | Develop and customise IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Develop and customise IT service♦Implementation LUS♦L2♦CP
ITSM | Deploy IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 |  |  | Build IT Service |  |  | ITSM♦Deploy IT service♦Total♦L2♦CP
ITSM | Deploy IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-04-15 | 2026-06-15 | 44 |  | Scheduled | Build IT Service | approximate date |  | ITSM♦Deploy IT service♦Elaboration♦L2♦CP
ITSM | Deploy IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 |  | Scheduled | Build IT Service | approximate date |  | ITSM♦Deploy IT service♦Implementation LIS♦L2♦CP
ITSM | Deploy IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service | approximate date |  | ITSM♦Deploy IT service♦Implementation COT♦L2♦CP
ITSM | Deploy IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service | approximate date |  | ITSM♦Deploy IT service♦Implementation LUS♦L2♦CP
| Test and validate IT service | Total | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-08-31 | 99 |  |  | Build IT Service |  |  | ♦Test and validate IT service♦Total♦L2♦CP
ITSM | Test and validate IT service | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-04-15 | 2026-06-15 | 44 |  | Scheduled | Build IT Service | approximate date |  | ITSM♦Test and validate IT service♦Elaboration♦L2♦CP
ITSM | Test and validate IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-07-15 | 2026-08-31 | 34 |  | Scheduled | Build IT Service | approximate date |  | ITSM♦Test and validate IT service♦Implementation LIS♦L2♦CP
ITSM | Test and validate IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service | approximate date |  | ITSM♦Test and validate IT service♦Implementation COT♦L2♦CP
ITSM | Test and validate IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service | approximate date |  | ITSM♦Test and validate IT service♦Implementation LUS♦L2♦CP
ITSM | Evaluate success of IT service rollout | Total | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Evaluate success of IT service rollout♦Total♦L2♦CP
ITSM | Evaluate success of IT service rollout | Elaboration | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) |  |  | 0 |  |  | Build IT Service |  |  | ITSM♦Evaluate success of IT service rollout♦Elaboration♦L2♦CP
ITSM | Evaluate success of IT service rollout | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Evaluate success of IT service rollout♦Implementation LIS♦L2♦CP
ITSM | Evaluate success of IT service rollout | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Evaluate success of IT service rollout♦Implementation COT♦L2♦CP
ITSM | Evaluate success of IT service rollout | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Evaluate success of IT service rollout♦Implementation LUS♦L2♦CP
ITSM | Manage IT service change | Total | L2 | CP | 100% |  |  |  | 2026-01-12 | 2026-06-30 | 122 | 2026-04-15 |  | Build IT Service |  |  | ITSM♦Manage IT service change♦Total♦L2♦CP
ITSM | Manag IT service change | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 2026-01-12 | 2026-03-18 | 48 | 2026-04-15 | Elaboration Done | Build IT Service |  |  | ITSM♦Manag IT service change♦Elaboration♦L2♦CP
ITSM | Manag IT service change | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  | Scheduled | Build IT Service |  |  | ITSM♦Manag IT service change♦Implementation LIS♦L2♦CP
ITSM | Manag IT service change | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Manag IT service change♦Implementation COT♦L2♦CP
ITSM | Manag IT service change | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Manag IT service change♦Implementation LUS♦L2♦CP
ITSM | Manage IT service release | Total | L2 | CP | 50% |  |  |  | 2026-02-20 | 2026-06-30 | 93 |  |  | Build IT Service |  |  | ITSM♦Manage IT service release♦Total♦L2♦CP
ITSM | Manage IT service release | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 2026-02-20 | 2026-05-08 | 56 |  | Elaboration in progress | Build IT Service |  |  | ITSM♦Manage IT service release♦Elaboration♦L2♦CP
ITSM | Manage IT service release | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  | Scheduled | Build IT Service |  |  | ITSM♦Manage IT service release♦Implementation LIS♦L2♦CP
ITSM | Manage IT service release | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Manage IT service release♦Implementation COT♦L2♦CP
ITSM | Manage IT service release | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Build IT Service |  |  | ITSM♦Manage IT service release♦Implementation LUS♦L2♦CP
ITSM | Deliver IT service | Total | L1 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-17 | 56 |  |  | Deliver IT service |  |  | ITSM♦Deliver IT service♦Total♦L1♦CP
ITSM | Deliver IT service | Elaboration | L1 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) |  |  | 0 |  |  | Deliver IT service |  |  | ITSM♦Deliver IT service♦Elaboration♦L1♦CP
ITSM | Deliver IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  | Deliver IT service |  |  | ITSM♦Deliver IT service♦Implementation LIS♦L1♦CP
ITSM | Deliver IT service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  | Deliver IT service |  |  | ITSM♦Deliver IT service♦Implementation COT♦L1♦CP
ITSM | Deliver IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  | Deliver IT service |  |  | ITSM♦Deliver IT service♦Implementation LUS♦L1♦CP
ITSM | Manage IT service provision request | Total | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-17 | 56 |  |  | Deliver IT service |  |  | ITSM♦Manage IT service provision request♦Total♦L2♦CP
ITSM | Manage IT service provision request | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 |  | Elaboration in progress | Deliver IT service | Resonsible unklar; Verwechslung Deliver und Run Prozesse |  | ITSM♦Manage IT service provision request♦Elaboration♦L2♦CP
ITSM | Manage IT service provision request | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  | Implementation LIS | Deliver IT service |  |  | ITSM♦Manage IT service provision request♦Implementation LIS♦L2♦CP
ITSM | Manage IT service provision request | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Deliver IT service |  |  | ITSM♦Manage IT service provision request♦Implementation COT♦L2♦CP
ITSM | Manage IT service provision request | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Deliver IT service |  |  | ITSM♦Manage IT service provision request♦Implementation LUS♦L2♦CP
ITSM | Handle IT service order | Total | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-17 | 56 |  |  | Deliver IT service |  |  | ITSM♦Handle IT service order♦Total♦L2♦CP
ITSM | Handle IT service order | Elaboration | L2 | CP | 0% | Hoermann Patrick (LLI) | Kuerschner Phillip | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 |  | Elaboration in progress | Deliver IT service | Responsible unklar; Verwechslung Deliver und Run Prozesse |  | ITSM♦Handle IT service order♦Elaboration♦L2♦CP
ITSM | Handle IT service order | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  | Implementation LIS | Deliver IT service |  |  | ITSM♦Handle IT service order♦Implementation LIS♦L2♦CP
ITSM | Handle IT service order | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Deliver IT service |  |  | ITSM♦Handle IT service order♦Implementation COT♦L2♦CP
ITSM | Handle IT service order | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Deliver IT service |  |  | ITSM♦Handle IT service order♦Implementation LUS♦L2♦CP
ITSM | Run IT service | Total | L1 | CP | 17% |  |  |  | 2025-10-15 | 2026-09-25 | 248 |  |  | Run IT service |  |  | ITSM♦Run IT service♦Total♦L1♦CP
ITSM | Run IT service | Elaboration | L1 | CP | 0% | Schroeder Michael (LIS);Böhme Matthias (ext.) | Oey Kai (LIS) | Sint Rachel (LBH) | 2025-10-16 | 2026-06-30 | 184 |  | Elaboration in progress | Run IT service |  |  | ITSM♦Run IT service♦Elaboration♦L1♦CP
ITSM | Run IT service | Implementation LIS | L1 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Run IT service♦Implementation LIS♦L1♦CP
ITSM | Run IT service | Implementation COT | L1 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Run IT service♦Implementation COT♦L1♦CP
ITSM | Run IT service | Implementation LUS | L1 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Run IT service♦Implementation LUS♦L1♦CP
ITSM | Ensure IT service continuity | Total | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Ensure IT service continuity♦Total♦L2♦CP
ITSM | Ensure IT service continuity | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Ensure IT service continuity♦Elaboration♦L2♦CP
ITSM | Ensure IT service continuity | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Ensure IT service continuity♦Implementation LIS♦L2♦CP
ITSM | Ensure IT service continuity | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Ensure IT service continuity♦Implementation COT♦L2♦CP
ITSM | Ensure IT service continuity | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Ensure IT service continuity♦Implementation LUS♦L2♦CP
ITSM | Manage IT service capacity | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service capacity♦Total♦L3♦CP
ITSM | Manage IT service capacity | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service capacity♦Elaboration♦L3♦CP
ITSM | Manage IT service capacity | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service capacity♦Implementation LIS♦L3♦CP
ITSM | Manage IT service capacity | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service capacity♦Implementation COT♦L3♦CP
ITSM | Manage IT service capacity | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service capacity♦Implementation LUS♦L3♦CP
ITSM | Review and maintain IT service continuity plan | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Review and maintain IT service continuity plan♦Total♦L3♦CP
ITSM | Review and maintain IT service continuity plan | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Review and maintain IT service continuity plan♦Elaboration♦L3♦CP
ITSM | Review and maintain IT service continuity plan | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Review and maintain IT service continuity plan♦Implementation LIS♦L3♦CP
ITSM | Review and maintain IT service continuity plan | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Review and maintain IT service continuity plan♦Implementation COT♦L3♦CP
ITSM | Review and maintain IT service continuity plan | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Review and maintain IT service continuity plan♦Implementation LUS♦L3♦CP
ITSM | Monitor and report IT service performance | Total | L2 | CP | 0% |  |  |  | 2026-04-15 |  | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service performance♦Total♦L2♦CP
ITSM | Montior and report IT service performance | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service | approximate date |  | ITSM♦Montior and report IT service performance♦Elaboration♦L2♦CP
ITSM | Montior and report IT service performance | Implementation LIS | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service | approximate date |  | ITSM♦Montior and report IT service performance♦Implementation LIS♦L2♦CP
ITSM | Montior and report IT service performance | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Montior and report IT service performance♦Implementation COT♦L2♦CP
ITSM | Montior and report IT service performance | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Montior and report IT service performance♦Implementation LUS♦L2♦CP
ITSM | Monitor and report IT service level | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service level♦Total♦L3♦CP
ITSM | Monitor and report IT service level | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service level♦Elaboration♦L3♦CP
ITSM | Monitor and report IT service level | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service level♦Implementation LIS♦L3♦CP
ITSM | Monitor and report IT service level | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service level♦Implementation COT♦L3♦CP
ITSM | Monitor and report IT service level | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service level♦Implementation LUS♦L3♦CP
ITSM | Monitor and report IT service financials | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service financials♦Total♦L3♦CP
ITSM | Monitor and report IT service financials | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service financials♦Elaboration♦L3♦CP
ITSM | Monitor and report IT service financials | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service financials♦Implementation LIS♦L3♦CP
ITSM | Monitor and report IT service financials | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service financials♦Implementation COT♦L3♦CP
ITSM | Monitor and report IT service financials | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and report IT service financials♦Implementation LUS♦L3♦CP
ITSM | Monitor and analyse events | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and analyse events♦Total♦L3♦CP
ITSM | Monitor and analyse events | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and analyse events♦Elaboration♦L3♦CP
ITSM | Monitor and analyse events | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and analyse events♦Implementation LIS♦L3♦CP
ITSM | Monitor and analyse events | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and analyse events♦Implementation COT♦L3♦CP
ITSM | Monitor and analyse events | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor and analyse events♦Implementation LUS♦L3♦CP
ITSM | Monitor IT service risk and compliance | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor IT service risk and compliance♦Total♦L3♦CP
ITSM | Monitor IT service risk and compliance | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service | Responsible from Matthias Held adjusted to Philipp Kürschner in the joint conversation |  | ITSM♦Monitor IT service risk and compliance♦Elaboration♦L3♦CP
ITSM | Monitor IT service risk and compliance | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor IT service risk and compliance♦Implementation LIS♦L3♦CP
ITSM | Monitor IT service risk and compliance | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor IT service risk and compliance♦Implementation COT♦L3♦CP
ITSM | Monitor IT service risk and compliance | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor IT service risk and compliance♦Implementation LUS♦L3♦CP
ITSM | Monitor user experience | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor user experience♦Total♦L3♦CP
ITSM | Monitor user experience | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service | Responsible from Matthias Held adjusted to Philipp Kürschner in the joint conversation |  | ITSM♦Monitor user experience♦Elaboration♦L3♦CP
ITSM | Monitor user experience | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor user experience♦Implementation LIS♦L3♦CP
ITSM | Monitor user experience | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor user experience♦Implementation COT♦L3♦CP
ITSM | Monitor user experience | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Monitor user experience♦Implementation LUS♦L3♦CP
ITSM | Operate and maintain IT service | Total | L2 | CP | 21% |  |  |  | 2025-10-15 | 2026-06-30 | 185 |  |  | Run IT service |  |  | ITSM♦Operate and maintain IT service♦Total♦L2♦CP
ITSM | Operate and maintain IT service | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-12 | 2026-06-30 | 122 |  | Elaboration in progress | Run IT service | approximate date |  | ITSM♦Operate and maintain IT service♦Elaboration♦L2♦CP
ITSM | Operate and maintain IT service | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  | Scheduled | Run IT service | approximate date |  | ITSM♦Operate and maintain IT service♦Implementation LIS♦L2♦CP
ITSM | Operate and maintain IT service | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Operate and maintain IT service♦Implementation COT♦L2♦CP
ITSM | Operate and maintain IT service | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Operate and maintain IT service♦Implementation LUS♦L2♦CP
ITSM | Maintain CMDB | Total | L3 | CP | 50% |  |  |  | 2026-01-14 | 2026-05-20 | 91 |  |  | Run IT service |  |  | ITSM♦Maintain CMDB♦Total♦L3♦CP
ITSM | Maintain CMDB | Elaboration | L3 | CP | 50% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-14 | 2026-05-20 | 91 |  | Elaboration in progress | Run IT service |  |  | ITSM♦Maintain CMDB♦Elaboration♦L3♦CP
ITSM | Maintain CMDB | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain CMDB♦Implementation LIS♦L3♦CP
ITSM | Maintain CMDB | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain CMDB♦Implementation COT♦L3♦CP
ITSM | Maintain CMDB | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain CMDB♦Implementation LUS♦L3♦CP
ITSM | Maintain IT asset database | Total | L3 | CP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Run IT service |  |  | ITSM♦Maintain IT asset database♦Total♦L3♦CP
ITSM | Maintain IT asset database | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Nissen Sönke (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Maintain IT asset database♦Elaboration♦L3♦CP
ITSM | Maintain IT asset database | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain IT asset database♦Implementation LIS♦L3♦CP
ITSM | Maintain IT asset database | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain IT asset database♦Implementation COT♦L3♦CP
ITSM | Maintain IT asset database | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain IT asset database♦Implementation LUS♦L3♦CP
ITSM | Maintain standard change catalouge for IT service | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain standard change catalouge for IT service♦Total♦L3♦CP
ITSM | Maintain standard change catalouge for IT service | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Held Matthias (LIS) ? | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service |  |  | ITSM♦Maintain standard change catalouge for IT service♦Elaboration♦L3♦CP
ITSM | Maintain standard change catalouge for IT service | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain standard change catalouge for IT service♦Implementation LIS♦L3♦CP
ITSM | Maintain standard change catalouge for IT service | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain standard change catalouge for IT service♦Implementation COT♦L3♦CP
ITSM | Maintain standard change catalouge for IT service | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Maintain standard change catalouge for IT service♦Implementation LUS♦L3♦CP
ITSM | Provide IT service support | Total | L2 | CP | 57% |  |  |  | 2025-10-16 | 2026-06-15 | 173 |  |  | Run IT service |  |  | ITSM♦Provide IT service support♦Total♦L2♦CP
ITSM | Provide IT service support | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  | Elaboration Done | Run IT service |  |  | ITSM♦Provide IT service support♦Elaboration♦L2♦CP
ITSM | Provide IT service support | Implementation LIS | L2 | CP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  | Implementation LIS | Run IT service |  |  | ITSM♦Provide IT service support♦Implementation LIS♦L2♦CP
ITSM | Provide IT service support | Implementation COT | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Provide IT service support♦Implementation COT♦L2♦CP
ITSM | Provide IT service support | Implementation LUS | L2 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Provide IT service support♦Implementation LUS♦L2♦CP
ITSM | Handle IT Incident | Total | L3 | CP | 75% |  |  |  | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 |  | Run IT service |  |  | ITSM♦Handle IT Incident♦Total♦L3♦CP
ITSM | Handle IT Incident | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 | Elaboration Done | Run IT service | Ansprechpartner Anna Rantou |  | ITSM♦Handle IT Incident♦Elaboration♦L3♦CP
ITSM | Handle IT Incident | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Handle IT Incident♦Implementation LIS♦L3♦CP
ITSM | Handle IT Incident | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Handle IT Incident♦Implementation COT♦L3♦CP
ITSM | Handle IT Incident | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Handle IT Incident♦Implementation LUS♦L3♦CP
ITSM | Handle IT problem | Total | L3 | CP | 75% |  |  |  | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 |  | Run IT service |  |  | ITSM♦Handle IT problem♦Total♦L3♦CP
ITSM | Handle IT problem | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 | Elaboration Done | Run IT service | Ansprechpartner Anna Rantou |  | ITSM♦Handle IT problem♦Elaboration♦L3♦CP
ITSM | Handle IT problem | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Handle IT problem♦Implementation LIS♦L3♦CP
ITSM | Handle IT problem | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Handle IT problem♦Implementation COT♦L3♦CP
ITSM | Handle IT problem | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Handle IT problem♦Implementation LUS♦L3♦CP
ITSM | Handle IT service request | Total | L3 | CP | 100% |  |  |  | 2026-02-02 | 2026-03-19 | 34 | 2026-03-19 |  | Run IT service |  |  | ITSM♦Handle IT service request♦Total♦L3♦CP
ITSM | Handle IT service request | Elaboration | L3 | CP | 100% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-02-02 | 2026-03-19 | 34 | 2026-03-19 | Elaboration Done | Run IT service | Ansprechpartner Eloise |  | ITSM♦Handle IT service request♦Elaboration♦L3♦CP
ITSM | Handle IT service request | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service | Mit Go Life Service Now |  | ITSM♦Handle IT service request♦Implementation LIS♦L3♦CP
ITSM | Handle IT service request | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service | Mit Go Life Service Now |  | ITSM♦Handle IT service request♦Implementation COT♦L3♦CP
ITSM | Handle IT service request | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service | Mit Go Life Service Now |  | ITSM♦Handle IT service request♦Implementation LUS♦L3♦CP
ITSM | Manage IT service desk | Total | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service desk♦Total♦L3♦CP
ITSM | Manage IT service desk | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) |  |  | 0 |  |  | Run IT service | Sönke Nissen war zuvor eingetragen. Philipp Kürschner sieht sich als verantwortlich. |  | ITSM♦Manage IT service desk♦Elaboration♦L3♦CP
ITSM | Manage IT service desk | Implementation LIS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service desk♦Implementation LIS♦L3♦CP
ITSM | Manage IT service desk | Implementation COT | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service desk♦Implementation COT♦L3♦CP
ITSM | Manage IT service desk | Implementation LUS | L3 | CP | 0% | [5 empty] | 0 |  |  | Run IT service |  |  | ITSM♦Manage IT service desk♦Implementation LUS♦L3♦CP
Information security | Ensure Information security | Total | L1 | SP | 50% |  |  |  | 2025-10-16 | 2025-10-16 | 1 |  |  | Ensure Information security |  |  | Information security♦Ensure Information security♦Total♦L1♦SP
Information security | Ensure Information security | Elaboration | L1 | SP | 50% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | 2025-10-16 |  | 0 |  |  | Ensure Information security |  |  | Information security♦Ensure Information security♦Elaboration♦L1♦SP
Information security | Ensure Information security | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  | Ensure Information security |  |  | Information security♦Ensure Information security♦Implementation LIS♦L1♦SP
Information security | Ensure Information security | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  | Ensure Information security |  |  | Information security♦Ensure Information security♦Implementation COT♦L1♦SP
Information security | Ensure Information security | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  | Ensure Information security |  |  | Information security♦Ensure Information security♦Implementation LUS♦L1♦SP
Information security | Perform SaaS Security Assessment | Total | L2 | SP | 50% |  |  |  | 2025-10-16 |  | 0 |  |  | Ensure Information security |  |  | Information security♦Perform SaaS Security Assessment♦Total♦L2♦SP
Information security | Perform SaaS Security Assessment | Elaboration | L2 | SP | 50% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-19 | 2026-04-30 | 139 |  | Elaboration in progress | Ensure Information security |  |  | Information security♦Perform SaaS Security Assessment♦Elaboration♦L2♦SP
Information security | Perform SaaS Security Assessment | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Ensure Information security |  |  | Information security♦Perform SaaS Security Assessment♦Implementation LIS♦L2♦SP
Information security | Perform SaaS Security Assessment | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Ensure Information security |  |  | Information security♦Perform SaaS Security Assessment♦Implementation COT♦L2♦SP
Information security | Perform SaaS Security Assessment | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Ensure Information security |  |  | Information security♦Perform SaaS Security Assessment♦Implementation LUS♦L2♦SP
IT project management | Manage IT project | Total | L1 | SP | 100% |  |  |  | 2025-07-14 | 2025-12-10 | 108 | 2025-09-18 |  | Manage IT project |  |  | IT project management♦Manage IT project♦Total♦L1♦SP
IT project management | Manage IT project | Elaboration | L1 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Manage IT project |  |  | IT project management♦Manage IT project♦Elaboration♦L1♦SP
IT project management | Manage IT project | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Manage IT project♦Implementation LIS♦L1♦SP
IT project management | Manage IT project | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Manage IT project♦Implementation COT♦L1♦SP
IT project management | Manage IT project | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Manage IT project♦Implementation LUS♦L1♦SP
IT project management | Initiate IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  | Manage IT project |  |  | IT project management♦Initiate IT project♦Total♦L2♦SP
IT project management | Initiate IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Manage IT project |  |  | IT project management♦Initiate IT project♦Elaboration♦L2♦SP
IT project management | Initiate IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Initiate IT project♦Implementation LIS♦L2♦SP
IT project management | Initiate IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Initiate IT project♦Implementation COT♦L2♦SP
IT project management | Initiate IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Initiate IT project♦Implementation LUS♦L2♦SP
IT project management | Plan IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  | Manage IT project |  |  | IT project management♦Plan IT project♦Total♦L2♦SP
IT project management | Plan IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Manage IT project |  |  | IT project management♦Plan IT project♦Elaboration♦L2♦SP
IT project management | Plan IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Plan IT project♦Implementation LIS♦L2♦SP
IT project management | Plan IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Plan IT project♦Implementation COT♦L2♦SP
IT project management | Plan IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Plan IT project♦Implementation LUS♦L2♦SP
IT project management | Steer and execute IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  | Manage IT project |  |  | IT project management♦Steer and execute IT project♦Total♦L2♦SP
IT project management | Steer and execute IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Manage IT project |  |  | IT project management♦Steer and execute IT project♦Elaboration♦L2♦SP
IT project management | Steer and execute IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Steer and execute IT project♦Implementation LIS♦L2♦SP
IT project management | Steer and execute IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Steer and execute IT project♦Implementation COT♦L2♦SP
IT project management | Steer and execute IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Steer and execute IT project♦Implementation LUS♦L2♦SP
IT project management | Close IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  | Manage IT project |  |  | IT project management♦Close IT project♦Total♦L2♦SP
IT project management | Close IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Manage IT project |  |  | IT project management♦Close IT project♦Elaboration♦L2♦SP
IT project management | Close IT project | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Close IT project♦Implementation LIS♦L2♦SP
IT project management | Close IT project | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Close IT project♦Implementation COT♦L2♦SP
IT project management | Close IT project | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Close IT project♦Implementation LUS♦L2♦SP
IT project management | Manage IT project change request | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  | Manage IT project |  |  | IT project management♦Manage IT project change request♦Total♦L2♦SP
IT project management | Manage IT project change request | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Manage IT project |  |  | IT project management♦Manage IT project change request♦Elaboration♦L2♦SP
IT project management | Manage IT project change request | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Manage IT project change request♦Implementation LIS♦L2♦SP
IT project management | Manage IT project change request | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Manage IT project change request♦Implementation COT♦L2♦SP
IT project management | Manage IT project change request | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Manage IT project change request♦Implementation LUS♦L2♦SP
IT project management | Assign personnel resources to IT project | Total | L2 | SP | 100% |  |  |  | 2025-07-14 | 2025-07-14 | 1 |  |  | Manage IT project |  |  | IT project management♦Assign personnel resources to IT project♦Total♦L2♦SP
IT project management | Ressourcemanagement for IT projects | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Manage IT project |  |  | IT project management♦Ressourcemanagement for IT projects♦Elaboration♦L2♦SP
IT project management | Ressourcemanagement for IT projects | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Ressourcemanagement for IT projects♦Implementation LIS♦L2♦SP
IT project management | Ressourcemanagement for IT projects | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Ressourcemanagement for IT projects♦Implementation COT♦L2♦SP
IT project management | Ressourcemanagement for IT projects | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Manage IT project | Trainings ongoing (with cPlace implementation) |  | IT project management♦Ressourcemanagement for IT projects♦Implementation LUS♦L2♦SP
ITSM | Manage IT sourcing and procurement | Total | L1 | SP | 0% |  |  |  | 2026-04-20 | 2026-09-30 | 118 |  |  | Manage IT sourcing and procurement |  |  | ITSM♦Manage IT sourcing and procurement♦Total♦L1♦SP
ITSM | Manage IT sourcing and procurement | Elaboration | L1 | SP | 0% | Rollinger Alexander (LIS);Schoeberl Lorena (LBH) | Roland Mario (LPS) | Monnier Murielle (LEC) | 2026-04-20 | 2026-06-30 | 52 |  | Scheduled | Manage IT sourcing and procurement | approximate date |  | ITSM♦Manage IT sourcing and procurement♦Elaboration♦L1♦SP
ITSM | Manage IT sourcing and procurement | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-07-13 | 2026-09-30 | 58 |  | Scheduled | Manage IT sourcing and procurement | approximate date |  | ITSM♦Manage IT sourcing and procurement♦Implementation LIS♦L1♦SP
ITSM | Manage IT sourcing and procurement | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  | Manage IT sourcing and procurement |  |  | ITSM♦Manage IT sourcing and procurement♦Implementation COT♦L1♦SP
ITSM | Manage IT sourcing and procurement | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  | Manage IT sourcing and procurement |  |  | ITSM♦Manage IT sourcing and procurement♦Implementation LUS♦L1♦SP
HR initiatives for IT | Provide and develop IT workforce | Total | L1 | SP | 15% |  |  |  | 2025-10-01 | 2027-06-30 | 456 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Provide and develop IT workforce♦Total♦L1♦SP
HR initiatives for IT | Provide and develop IT workforce | Elaboration | L1 | SP | 100% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Provide and develop IT workforce |  |  | HR initiatives for IT♦Provide and develop IT workforce♦Elaboration♦L1♦SP
HR initiatives for IT | Provide and develop IT workforce | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Provide and develop IT workforce♦Implementation LIS♦L1♦SP
HR initiatives for IT | Provide and develop IT workforce | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Provide and develop IT workforce♦Implementation COT♦L1♦SP
HR initiatives for IT | Provide and develop IT workforce | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Provide and develop IT workforce♦Implementation LUS♦L1♦SP
| Manage HR4IT strategy, governane and framework | Total | L2 | SP | 0% |  |  |  | 2025-10-01 | 2026-12-31 | 327 |  |  | Provide and develop IT workforce |  |  | ♦Manage HR4IT strategy, governane and framework♦Total♦L2♦SP
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Elaboration | L2 | SP | 100% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT strategy, governane and framework♦Elaboration♦L2♦SP
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT strategy, governane and framework♦Implementation LIS♦L2♦SP
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT strategy, governane and framework♦Implementation COT♦L2♦SP
HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT strategy, governane and framework♦Implementation LUS♦L2♦SP
HR initiatives for IT | Plan IT workforce | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2026-12-31 | 316 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Plan IT workforce♦Total♦L3♦SP
HR initiatives for IT | Plan IT workforce | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2025-12-31 | 55 |  | Elaboration Done | Provide and develop IT workforce | will be defined in CF-B (HR) |  | HR initiatives for IT♦Plan IT workforce♦Elaboration♦L3♦SP
HR initiatives for IT | Plan IT workforce | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-01-01 | 2026-12-31 | 261 |  | Implementation LIS | Provide and develop IT workforce |  |  | HR initiatives for IT♦Plan IT workforce♦Implementation LIS♦L3♦SP
HR initiatives for IT | Plan IT workforce | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Plan IT workforce♦Implementation COT♦L3♦SP
HR initiatives for IT | Plan IT workforce | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Plan IT workforce♦Implementation LUS♦L3♦SP
HR initiatives for IT | Implement and maintain IT job architecture | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2026-05-31 | 162 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Implement and maintain IT job architecture♦Total♦L3♦SP
HR initiatives for IT | Implement and maintain IT job architecture | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2026-05-31 | 162 |  | Elaboration in progress | Provide and develop IT workforce | will be defined in CF-B (HR) |  | HR initiatives for IT♦Implement and maintain IT job architecture♦Elaboration♦L3♦SP
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LIS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Implement and maintain IT job architecture♦Implementation LIS♦L3♦SP
HR initiatives for IT | Implement and maintain IT job architecture | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Implement and maintain IT job architecture♦Implementation COT♦L3♦SP
HR initiatives for IT | Implement and maintain IT job architecture | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Implement and maintain IT job architecture♦Implementation LUS♦L3♦SP
HR initiatives for IT | Manage HR4IT service demand |  | L3 | SP | 0% |  |  |  | 2025-10-01 | 2026-06-30 | 195 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT service demand♦♦L3♦SP
HR initiatives for IT | Manage HR4IT service demand | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2026-05-31 | 173 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT service demand♦Elaboration♦L3♦SP
HR initiatives for IT | Manage HR4IT service demand | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-06-01 | 2026-06-30 | 22 |  | Scheduled | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT service demand♦Implementation LIS♦L3♦SP
HR initiatives for IT | Manage HR4IT service demand | Implementation COT | L3 | SP | 0% |  |  |  | 2026-06-01 | 2026-06-30 | 22 |  | Scheduled | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT service demand♦Implementation COT♦L3♦SP
HR initiatives for IT | Manage HR4IT service demand | Implementation LUS | L3 | SP | 0% |  |  |  | 2026-06-01 | 2026-06-30 | 22 |  | Scheduled | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage HR4IT service demand♦Implementation LUS♦L3♦SP
HR initiatives for IT | Attract and hire employees | Total | L2 | SP | 18% |  |  |  | 2025-10-01 | 2026-12-31 | 327 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Attract and hire employees♦Total♦L2♦SP
HR initiatives for IT | Attract and hire employees | Elaboration | L2 | SP | 50% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  | Elaboration Done | Provide and develop IT workforce |  |  | HR initiatives for IT♦Attract and hire employees♦Elaboration♦L2♦SP
HR initiatives for IT | Attract and hire employees | Implementation LIS | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  | Implementation LIS | Provide and develop IT workforce |  |  | HR initiatives for IT♦Attract and hire employees♦Implementation LIS♦L2♦SP
HR initiatives for IT | Attract and hire employees | Implementation COT | L2 | SP | 0% |  |  |  | 2026-04-01 | 2026-06-15 | 54 |  | Implementation COT | Provide and develop IT workforce |  |  | HR initiatives for IT♦Attract and hire employees♦Implementation COT♦L2♦SP
HR initiatives for IT | Attract and hire employees | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Attract and hire employees♦Implementation LUS♦L2♦SP
HR initiatives for IT | Perform active sourcing |  | L3 | SP | 0% |  |  |  | 2025-10-01 | 2026-12-31 | 327 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform active sourcing♦♦L3♦SP
HR initiatives for IT | Perform active sourcing | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-04-30 | 152 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform active sourcing♦Elaboration♦L3♦SP
HR initiatives for IT | Perform active sourcing | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-03-01 | 2026-12-31 | 219 |  | Implementation LIS | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform active sourcing♦Implementation LIS♦L3♦SP
HR initiatives for IT | Perform active sourcing | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform active sourcing♦Implementation COT♦L3♦SP
HR initiatives for IT | Perform active sourcing | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform active sourcing♦Implementation LUS♦L3♦SP
HR initiatives for IT | Recruit employees and managers |  | L3 | SP | 25% |  |  |  | 2025-10-01 | 2026-12-31 | 327 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Recruit employees and managers♦♦L3♦SP
HR initiatives for IT | Recruit employees and managers | Elaboration | L3 | SP | 25% | Chen Leilei (ext.);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-04-30 | 152 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Recruit employees and managers♦Elaboration♦L3♦SP
HR initiatives for IT | Recruit employees and managers | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-03-01 | 2026-12-31 | 219 |  | Implementation LIS | Provide and develop IT workforce |  |  | HR initiatives for IT♦Recruit employees and managers♦Implementation LIS♦L3♦SP
HR initiatives for IT | Recruit employees and managers | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Recruit employees and managers♦Implementation COT♦L3♦SP
HR initiatives for IT | Recruit employees and managers | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Recruit employees and managers♦Implementation LUS♦L3♦SP
HR initiatives for IT | Perform onboarding | Total | L2 | SP | 33% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform onboarding♦Total♦L2♦SP
HR initiatives for IT | Perform onboarding | Elaboration | L2 | SP | 25% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform onboarding♦Elaboration♦L2♦SP
HR initiatives for IT | Perform onboarding | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform onboarding♦Implementation LIS♦L2♦SP
HR initiatives for IT | Perform onboarding | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform onboarding♦Implementation COT♦L2♦SP
HR initiatives for IT | Perform onboarding | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform onboarding♦Implementation LUS♦L2♦SP
HR initiatives for IT | Pre-board new IT employee and manager | Total | L3 | SP | 25% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Pre-board new IT employee and manager♦Total♦L3♦SP
HR initiatives for IT | Pre-board new IT employee and manager | Elaboration | L3 | SP | 25% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Pre-board new IT employee and manager♦Elaboration♦L3♦SP
HR initiatives for IT | Pre-board new IT employee and manager | Implementation LIS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Pre-board new IT employee and manager♦Implementation LIS♦L3♦SP
HR initiatives for IT | Pre-board new IT employee and manager | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Pre-board new IT employee and manager♦Implementation COT♦L3♦SP
HR initiatives for IT | Pre-board new IT employee and manager | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Pre-board new IT employee and manager♦Implementation LUS♦L3♦SP
HR initiatives for IT | Onboard new IT employee and manager | Total | L3 | SP | 50% |  |  |  | 2025-10-16 | 2026-04-30 | 141 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Onboard new IT employee and manager♦Total♦L3♦SP
HR initiatives for IT | Onboard new IT employee and manager | Elaboration | L3 | SP | 50% | Chen Leilei (ext.);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Onboard new IT employee and manager♦Elaboration♦L3♦SP
HR initiatives for IT | Onboard new IT employee and manager | Implementation LIS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Onboard new IT employee and manager♦Implementation LIS♦L3♦SP
HR initiatives for IT | Onboard new IT employee and manager | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Onboard new IT employee and manager♦Implementation COT♦L3♦SP
HR initiatives for IT | Onboard new IT employee and manager | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Onboard new IT employee and manager♦Implementation LUS♦L3♦SP
HR initiatives for IT | Perform, learn and grow | Total | L2 | SP | 11% |  |  |  | 2025-10-01 | 2027-06-30 | 456 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform, learn and grow♦Total♦L2♦SP
HR initiatives for IT | Perform, learn and grow | Elaboration | L2 | SP | 25% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-01 |  | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform, learn and grow♦Elaboration♦L2♦SP
HR initiatives for IT | Perform, learn and grow | Implementation LIS | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform, learn and grow♦Implementation LIS♦L2♦SP
HR initiatives for IT | Perform, learn and grow | Implementation COT | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform, learn and grow♦Implementation COT♦L2♦SP
HR initiatives for IT | Perform, learn and grow | Implementation LUS | L2 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Perform, learn and grow♦Implementation LUS♦L2♦SP
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue |  | L3 | SP | 50% |  |  |  | 2025-10-01 | 2026-04-30 | 152 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Create, approve and publish trainings for IT workforce within IT Training Catalogue♦♦L3♦SP
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Elaboration | L3 | SP | 50% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-04-30 | 152 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Create, approve and publish trainings for IT workforce within IT Training Catalogue♦Elaboration♦L3♦SP
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LIS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Create, approve and publish trainings for IT workforce within IT Training Catalogue♦Implementation LIS♦L3♦SP
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Create, approve and publish trainings for IT workforce within IT Training Catalogue♦Implementation COT♦L3♦SP
HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Create, approve and publish trainings for IT workforce within IT Training Catalogue♦Implementation LUS♦L3♦SP
HR initiatives for IT | Mapping and evaluate IT career level | Total | L3 | SP | 0% |  |  |  | 2026-04-01 | 2027-01-01 | 198 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Mapping and evaluate IT career level♦Total♦L3♦SP
HR initiatives for IT | Mapping and evaluate IT career level | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2027-01-01 | 198 |  | Elaboration in progress | Provide and develop IT workforce |  |  | HR initiatives for IT♦Mapping and evaluate IT career level♦Elaboration♦L3♦SP
HR initiatives for IT | Mapping and evaluate IT career level | Implementation LIS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Mapping and evaluate IT career level♦Implementation LIS♦L3♦SP
HR initiatives for IT | Mapping and evaluate IT career level | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Mapping and evaluate IT career level♦Implementation COT♦L3♦SP
HR initiatives for IT | Mapping and evaluate IT career level | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Mapping and evaluate IT career level♦Implementation LUS♦L3♦SP
HR initiatives for IT | Manage IT development programme | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT development programme♦Total♦L3♦SP
HR initiatives for IT | Manage IT development programme | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT development programme♦Elaboration♦L3♦SP
HR initiatives for IT | Manage IT development programme | Implementation LIS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT development programme♦Implementation LIS♦L3♦SP
HR initiatives for IT | Manage IT development programme | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT development programme♦Implementation COT♦L3♦SP
HR initiatives for IT | Manage IT development programme | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT development programme♦Implementation LUS♦L3♦SP
HR initiatives for IT | Manage IT skills | Total | L3 | SP | 0% |  |  |  | 2026-01-01 | 2027-06-30 | 390 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT skills♦Total♦L3♦SP
HR initiatives for IT | Manage IT skills | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-01 | 2026-12-31 | 261 |  | Elaboration in progress | Provide and develop IT workforce | will be defined in CF-B (HR) |  | HR initiatives for IT♦Manage IT skills♦Elaboration♦L3♦SP
HR initiatives for IT | Manage IT skills | Implementation LIS | L3 | SP | 0% |  |  |  | 2027-01-01 | 2027-06-30 | 129 |  | Scheduled | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT skills♦Implementation LIS♦L3♦SP
HR initiatives for IT | Manage IT skills | Implementation COT | L3 | SP | 0% |  |  |  | 2027-01-01 | 2027-06-30 | 129 |  | Scheduled | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT skills♦Implementation COT♦L3♦SP
HR initiatives for IT | Manage IT skills | Implementation LUS | L3 | SP | 0% |  |  |  | 2027-01-01 | 2027-06-30 | 129 |  | Scheduled | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT skills♦Implementation LUS♦L3♦SP
HR initiatives for IT | Manage IT talent pool and identify potential | Total | L3 | SP | 0% |  |  |  | 2025-10-16 | 2025-10-16 | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT talent pool and identify potential♦Total♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) |  |  | 0 |  |  | Provide and develop IT workforce | will be defined in CF-B (HR) |  | HR initiatives for IT♦Manage IT global orientation programme♦Elaboration♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme | Implementation LIS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme♦Implementation LIS♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme | Implementation COT | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme♦Implementation COT♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme | Implementation LUS | L3 | SP | 0% | [5 empty] | 0 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme♦Implementation LUS♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Total | L3 | SP | 0% |  |  |  | 2026-01-15 | 2026-07-01 | 120 |  |  | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme incl. job shadowing♦Total♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Elaboration | L3 | SP | 0% | Chen Leilei (ext.);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-03-31 | 54 |  | Elaboration Done | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme incl. job shadowing♦Elaboration♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LIS | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 |  | Implementation LIS | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme incl. job shadowing♦Implementation LIS♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation COT | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 |  | Implementation COT | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme incl. job shadowing♦Implementation COT♦L3♦SP
HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LUS | L3 | SP | 0% |  |  |  | 2026-04-01 | 2026-07-01 | 66 |  | Implementation LUS | Provide and develop IT workforce |  |  | HR initiatives for IT♦Manage IT global orientation programme incl. job shadowing♦Implementation LUS♦L3♦SP
ITSM | Ensure performance and conformance of IT services | Total | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  |  | Ensure performance and conformance of IT services |  |  | ITSM♦Ensure performance and conformance of IT services♦Total♦L1♦SP
ITSM | Ensure performance and conformance of IT services | Elaboration | L1 | SP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 |  | Scheduled | Ensure performance and conformance of IT services | approximate date |  | ITSM♦Ensure performance and conformance of IT services♦Elaboration♦L1♦SP
ITSM | Ensure performance and conformance of IT services | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  | Ensure performance and conformance of IT services | approximate date |  | ITSM♦Ensure performance and conformance of IT services♦Implementation LIS♦L1♦SP
ITSM | Ensure performance and conformance of IT services | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  | Ensure performance and conformance of IT services |  |  | ITSM♦Ensure performance and conformance of IT services♦Implementation COT♦L1♦SP
ITSM | Ensure performance and conformance of IT services | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  | Ensure performance and conformance of IT services |  |  | ITSM♦Ensure performance and conformance of IT services♦Implementation LUS♦L1♦SP
ITSM | Manage IT knowledge | Total | L1 | SP | 100% |  |  |  | 2026-01-20 | 2026-06-30 | 116 | 2026-03-19 |  | Manage IT knowledge |  |  | ITSM♦Manage IT knowledge♦Total♦L1♦SP
ITSM | Manage IT knowledge | Elaboration | L1 | SP | 100% | Schroeder Michael (LIS) | Kürschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-20 | 2026-02-25 | 27 |  | Elaboration Done | Manage IT knowledge | Ansprechpartner Anna Rantou |  | ITSM♦Manage IT knowledge♦Elaboration♦L1♦SP
ITSM | Manage IT knowledge | Implementation LIS | L1 | SP | 0% |  |  |  | 2026-04-15 | 2026-06-30 | 55 |  | Scheduled | Manage IT knowledge |  |  | ITSM♦Manage IT knowledge♦Implementation LIS♦L1♦SP
ITSM | Manage IT knowledge | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  | Manage IT knowledge |  |  | ITSM♦Manage IT knowledge♦Implementation COT♦L1♦SP
ITSM | Manage IT knowledge | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  | Manage IT knowledge |  |  | ITSM♦Manage IT knowledge♦Implementation LUS♦L1♦SP
ITSM | Leverage IT innovation | Total | L1 | SP | 25% |  |  |  | 2025-10-16 | 2025-12-31 | 55 |  |  | Leverage IT innovtion |  |  | ITSM♦Leverage IT innovation♦Total♦L1♦SP
ITSM | Leverage IT innovation | Elaboration | L1 | SP | 25% | Rollinger Alexander (LIS);Böhme Matthias (ext.) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | 2025-10-16 |  | 0 |  |  | Leverage IT innovtion | approximate date |  | ITSM♦Leverage IT innovation♦Elaboration♦L1♦SP
ITSM | Leverage IT innovation | Implementation LIS | L1 | SP | 0% | [5 empty] | 0 |  |  | Leverage IT innovtion | approximate date |  | ITSM♦Leverage IT innovation♦Implementation LIS♦L1♦SP
ITSM | Leverage IT innovation | Implementation COT | L1 | SP | 0% | [5 empty] | 0 |  |  | Leverage IT innovtion |  |  | ITSM♦Leverage IT innovation♦Implementation COT♦L1♦SP
ITSM | Leverage IT innovation | Implementation LUS | L1 | SP | 0% | [5 empty] | 0 |  |  | Leverage IT innovtion |  |  | ITSM♦Leverage IT innovation♦Implementation LUS♦L1♦SP

## Date_table_13_4_26 (hidden)
Datum | Elaboration | Implementation LIS | Implementation LUS | Implementation COT
2025-08-01 | 0 | 1 | 0 | 0
2025-08-02 | 1 | 1 | 0 | 0
2025-08-03 | 1 | 1 | 0 | 0
2025-08-04 | 1 | 1 | 0 | 0
2025-08-05 | 2 | 1 | 0 | 0
2025-08-06 | 2 | 1 | 0 | 0
2025-08-07 | 2 | 1 | 0 | 0
2025-08-08 | 2 | 1 | 0 | 0
2025-08-09 | 2 | 1 | 0 | 0
2025-08-10 | 2 | 1 | 0 | 0
2025-08-11 | 2 | 1 | 0 | 0
2025-08-12 | 2 | 1 | 0 | 0
2025-08-13 | 2 | 1 | 0 | 0
2025-08-14 | 2 | 1 | 0 | 0
2025-08-15 | 2 | 0 | 0 | 0
2025-08-16 | 2 | 0 | 0 | 0
2025-08-17 | 2 | 0 | 0 | 0
2025-08-18 | 2 | 0 | 0 | 0
2025-08-19 | 2 | 0 | 0 | 0
2025-08-20 | 2 | 0 | 0 | 0
2025-08-21 | 2 | 0 | 0 | 0
2025-08-22 | 2 | 0 | 0 | 0
2025-08-23 | 2 | 0 | 0 | 0
2025-08-24 | 2 | 0 | 0 | 0
2025-08-25 | 2 | 0 | 0 | 0
2025-08-26 | 2 | 0 | 0 | 0
2025-08-27 | 2 | 0 | 0 | 0
2025-08-28 | 2 | 0 | 0 | 0
2025-08-29 | 2 | 0 | 0 | 0
2025-08-30 | 1 | 0 | 0 | 0
2025-08-31 | 1 | 0 | 0 | 0
2025-09-01 | 1 | 0 | 0 | 0
2025-09-02 | 1 | 0 | 0 | 0
2025-09-03 | 1 | 0 | 0 | 0
2025-09-04 | 1 | 0 | 0 | 0
2025-09-05 | 1 | 0 | 0 | 0
2025-09-06 | 1 | 0 | 0 | 0
2025-09-07 | 1 | 0 | 0 | 0
2025-09-08 | 1 | 0 | 0 | 0
2025-09-09 | 1 | 0 | 0 | 0
2025-09-10 | 1 | 0 | 0 | 0
2025-09-11 | 1 | 0 | 0 | 0
2025-09-12 | 1 | 0 | 0 | 0
2025-09-13 | 1 | 0 | 0 | 0
2025-09-14 | 1 | 0 | 0 | 0
2025-09-15 | 1 | 0 | 0 | 0
2025-09-16 | 1 | 0 | 0 | 0
2025-09-17 | 1 | 0 | 0 | 0
2025-09-18 | 1 | 0 | 0 | 0
2025-09-19 | 1 | 0 | 0 | 0
2025-09-20 | 1 | 0 | 0 | 0
2025-09-21 | 1 | 0 | 0 | 0
2025-09-22 | 1 | 0 | 0 | 0
2025-09-23 | 1 | 0 | 0 | 0
2025-09-24 | 1 | 0 | 0 | 0
2025-09-25 | 1 | 0 | 0 | 0
2025-09-26 | 1 | 0 | 0 | 0
2025-09-27 | 1 | 0 | 0 | 0
2025-09-28 | 1 | 0 | 0 | 0
2025-09-29 | 1 | 0 | 0 | 0
2025-09-30 | 1 | 0 | 0 | 0
2025-10-01 | 1 | 0 | 0 | 0
2025-10-02 | 14 | 0 | 0 | 0
2025-10-03 | 14 | 0 | 0 | 0
2025-10-04 | 14 | 0 | 0 | 0
2025-10-05 | 14 | 0 | 0 | 0
2025-10-06 | 14 | 0 | 0 | 0
2025-10-07 | 14 | 0 | 0 | 0
2025-10-08 | 14 | 0 | 0 | 0
2025-10-09 | 14 | 0 | 0 | 0
2025-10-10 | 14 | 0 | 0 | 0
2025-10-11 | 14 | 0 | 0 | 0
2025-10-12 | 14 | 0 | 0 | 0
2025-10-13 | 14 | 0 | 0 | 0
2025-10-14 | 14 | 0 | 0 | 0
2025-10-15 | 13 | 0 | 0 | 0
2025-10-16 | 14 | 0 | 0 | 0
2025-10-17 | 21 | 0 | 0 | 2
2025-10-18 | 21 | 0 | 0 | 2
2025-10-19 | 21 | 0 | 0 | 2
2025-10-20 | 22 | 0 | 0 | 2
2025-10-21 | 22 | 0 | 0 | 2
2025-10-22 | 22 | 0 | 0 | 2
2025-10-23 | 22 | 0 | 0 | 2
2025-10-24 | 22 | 0 | 0 | 2
2025-10-25 | 22 | 0 | 0 | 2
2025-10-26 | 22 | 0 | 0 | 2
2025-10-27 | 22 | 0 | 0 | 2
2025-10-28 | 22 | 0 | 0 | 2
2025-10-29 | 22 | 0 | 0 | 2
2025-10-30 | 22 | 0 | 0 | 2
2025-10-31 | 21 | 0 | 0 | 2
2025-11-01 | 21 | 0 | 0 | 2
2025-11-02 | 21 | 4 | 0 | 2
2025-11-03 | 21 | 4 | 0 | 2
2025-11-04 | 21 | 4 | 0 | 6
2025-11-05 | 21 | 4 | 0 | 6
2025-11-06 | 21 | 4 | 0 | 6
2025-11-07 | 21 | 4 | 0 | 6
2025-11-08 | 21 | 4 | 0 | 6
2025-11-09 | 21 | 4 | 0 | 6
2025-11-10 | 21 | 4 | 0 | 6
2025-11-11 | 22 | 4 | 0 | 6
2025-11-12 | 30 | 4 | 0 | 6
2025-11-13 | 30 | 4 | 0 | 6
2025-11-14 | 30 | 4 | 0 | 6
2025-11-15 | 30 | 4 | 0 | 6
2025-11-16 | 30 | 4 | 0 | 6
2025-11-17 | 30 | 4 | 0 | 6
2025-11-18 | 30 | 4 | 0 | 6
2025-11-19 | 30 | 4 | 0 | 6
2025-11-20 | 30 | 4 | 0 | 6
2025-11-21 | 30 | 4 | 0 | 6
2025-11-22 | 30 | 4 | 0 | 6
2025-11-23 | 30 | 4 | 0 | 6
2025-11-24 | 30 | 4 | 0 | 6
2025-11-25 | 30 | 4 | 0 | 6
2025-11-26 | 30 | 4 | 0 | 6
2025-11-27 | 30 | 4 | 0 | 6
2025-11-28 | 30 | 4 | 0 | 6
2025-11-29 | 30 | 4 | 0 | 6
2025-11-30 | 30 | 4 | 0 | 6
2025-12-01 | 30 | 4 | 0 | 6
2025-12-02 | 30 | 4 | 0 | 6
2025-12-03 | 30 | 4 | 0 | 6
2025-12-04 | 30 | 4 | 0 | 6
2025-12-05 | 30 | 4 | 0 | 6
2025-12-06 | 30 | 4 | 0 | 6
2025-12-07 | 30 | 4 | 0 | 6
2025-12-08 | 30 | 4 | 0 | 6
2025-12-09 | 30 | 4 | 0 | 6
2025-12-10 | 22 | 4 | 0 | 6
2025-12-11 | 22 | 4 | 0 | 6
2025-12-12 | 22 | 4 | 0 | 6
2025-12-13 | 22 | 4 | 0 | 6
2025-12-14 | 22 | 4 | 0 | 6
2025-12-15 | 22 | 4 | 0 | 6
2025-12-16 | 22 | 4 | 0 | 6
2025-12-17 | 22 | 4 | 0 | 6
2025-12-18 | 22 | 4 | 0 | 6
2025-12-19 | 22 | 4 | 0 | 6
2025-12-20 | 22 | 4 | 0 | 6
2025-12-21 | 22 | 4 | 0 | 6
2025-12-22 | 22 | 4 | 0 | 6
2025-12-23 | 21 | 4 | 0 | 6
2025-12-24 | 21 | 4 | 0 | 6
2025-12-25 | 21 | 4 | 0 | 6
2025-12-26 | 21 | 4 | 0 | 6
2025-12-27 | 21 | 4 | 0 | 6
2025-12-28 | 21 | 4 | 0 | 6
2025-12-29 | 21 | 4 | 0 | 6
2025-12-30 | 21 | 4 | 0 | 6
2025-12-31 | 20 | 4 | 0 | 5
2026-01-01 | 20 | 4 | 0 | 5
2026-01-02 | 21 | 5 | 0 | 5
2026-01-03 | 21 | 5 | 0 | 5
2026-01-04 | 21 | 5 | 0 | 5
2026-01-05 | 21 | 5 | 0 | 5
2026-01-06 | 21 | 5 | 0 | 5
2026-01-07 | 21 | 5 | 0 | 5
2026-01-08 | 22 | 6 | 0 | 5
2026-01-09 | 22 | 6 | 0 | 5
2026-01-10 | 22 | 6 | 0 | 5
2026-01-11 | 22 | 6 | 0 | 5
2026-01-12 | 22 | 6 | 0 | 5
2026-01-13 | 30 | 6 | 0 | 5
2026-01-14 | 32 | 6 | 0 | 5
2026-01-15 | 33 | 6 | 0 | 5
2026-01-16 | 34 | 6 | 0 | 5
2026-01-17 | 34 | 5 | 0 | 5
2026-01-18 | 34 | 5 | 0 | 5
2026-01-19 | 34 | 5 | 0 | 5
2026-01-20 | 34 | 5 | 0 | 5
2026-01-21 | 34 | 5 | 0 | 5
2026-01-22 | 34 | 5 | 0 | 5
2026-01-23 | 34 | 5 | 0 | 5
2026-01-24 | 34 | 5 | 0 | 5
2026-01-25 | 34 | 5 | 0 | 5
2026-01-26 | 34 | 5 | 0 | 5
2026-01-27 | 34 | 5 | 0 | 5
2026-01-28 | 34 | 5 | 0 | 5
2026-01-29 | 33 | 5 | 0 | 5
2026-01-30 | 32 | 5 | 0 | 5
2026-01-31 | 32 | 5 | 0 | 5
2026-02-01 | 32 | 5 | 0 | 5
2026-02-02 | 32 | 6 | 0 | 5
2026-02-03 | 34 | 6 | 0 | 5
2026-02-04 | 34 | 6 | 0 | 5
2026-02-05 | 34 | 6 | 0 | 5
2026-02-06 | 35 | 6 | 0 | 5
2026-02-07 | 35 | 6 | 0 | 5
2026-02-08 | 35 | 6 | 0 | 5
2026-02-09 | 35 | 6 | 0 | 5
2026-02-10 | 35 | 6 | 0 | 5
2026-02-11 | 35 | 6 | 0 | 5
2026-02-12 | 35 | 6 | 0 | 5
2026-02-13 | 35 | 6 | 0 | 5
2026-02-14 | 35 | 6 | 0 | 5
2026-02-15 | 35 | 6 | 0 | 5
2026-02-16 | 35 | 6 | 0 | 5
2026-02-17 | 37 | 7 | 0 | 5
2026-02-18 | 37 | 7 | 0 | 5
2026-02-19 | 37 | 7 | 0 | 5
2026-02-20 | 37 | 7 | 0 | 5
2026-02-21 | 38 | 7 | 0 | 5
2026-02-22 | 38 | 7 | 0 | 5
2026-02-23 | 38 | 7 | 0 | 5
2026-02-24 | 38 | 7 | 0 | 5
2026-02-25 | 38 | 7 | 0 | 5
2026-02-26 | 38 | 7 | 0 | 5
2026-02-27 | 38 | 7 | 0 | 5
2026-02-28 | 38 | 3 | 0 | 5
2026-03-01 | 38 | 3 | 0 | 5
2026-03-02 | 38 | 5 | 0 | 5
2026-03-03 | 38 | 5 | 0 | 5
2026-03-04 | 38 | 5 | 0 | 5
2026-03-05 | 38 | 5 | 0 | 5
2026-03-06 | 38 | 5 | 0 | 5
2026-03-07 | 38 | 5 | 0 | 5
2026-03-08 | 38 | 5 | 0 | 5
2026-03-09 | 38 | 5 | 0 | 5
2026-03-10 | 38 | 5 | 0 | 5
2026-03-11 | 38 | 5 | 0 | 5
2026-03-12 | 38 | 5 | 0 | 5
2026-03-13 | 38 | 5 | 0 | 5
2026-03-14 | 38 | 5 | 0 | 5
2026-03-15 | 38 | 5 | 0 | 5
2026-03-16 | 37 | 5 | 0 | 5
2026-03-17 | 38 | 5 | 0 | 5
2026-03-18 | 37 | 5 | 0 | 5
2026-03-19 | 34 | 5 | 0 | 5
2026-03-20 | 34 | 5 | 0 | 5
2026-03-21 | 34 | 5 | 0 | 5
2026-03-22 | 34 | 5 | 0 | 5
2026-03-23 | 34 | 5 | 0 | 5
2026-03-24 | 34 | 5 | 0 | 5
2026-03-25 | 34 | 5 | 0 | 5
2026-03-26 | 34 | 5 | 0 | 5
2026-03-27 | 34 | 5 | 0 | 5
2026-03-28 | 34 | 5 | 0 | 5
2026-03-29 | 34 | 5 | 0 | 5
2026-03-30 | 33 | 5 | 0 | 5
2026-03-31 | 32 | 5 | 0 | 1
2026-04-01 | 32 | 5 | 0 | 1
2026-04-02 | 37 | 10 | 0 | 3
2026-04-03 | 37 | 10 | 0 | 3
2026-04-04 | 37 | 10 | 0 | 3
2026-04-05 | 37 | 10 | 0 | 3
2026-04-06 | 37 | 10 | 0 | 3
2026-04-07 | 37 | 10 | 0 | 3
2026-04-08 | 37 | 10 | 0 | 3
2026-04-09 | 37 | 10 | 0 | 3
2026-04-10 | 37 | 10 | 0 | 3
2026-04-11 | 37 | 10 | 0 | 3
2026-04-12 | 37 | 10 | 0 | 3
2026-04-13 | 37 | 10 | 0 | 3
2026-04-14 | 37 | 10 | 0 | 3
2026-04-15 | 37 | 10 | 0 | 3
2026-04-16 | 39 | 13 | 0 | 3
2026-04-17 | 39 | 13 | 0 | 3
2026-04-18 | 39 | 13 | 0 | 3
2026-04-19 | 39 | 13 | 0 | 3
2026-04-20 | 39 | 13 | 0 | 3
2026-04-21 | 39 | 13 | 0 | 3
2026-04-22 | 39 | 13 | 0 | 3
2026-04-23 | 39 | 14 | 0 | 3
2026-04-24 | 39 | 14 | 0 | 3
2026-04-25 | 39 | 14 | 0 | 3
2026-04-26 | 39 | 14 | 0 | 3
2026-04-27 | 39 | 14 | 0 | 3
2026-04-28 | 39 | 14 | 0 | 3
2026-04-29 | 39 | 14 | 0 | 3
2026-04-30 | 30 | 13 | 0 | 2
2026-05-01 | 30 | 13 | 0 | 2
2026-05-02 | 30 | 14 | 0 | 2
2026-05-03 | 30 | 14 | 0 | 2
2026-05-04 | 30 | 14 | 0 | 2
2026-05-05 | 30 | 14 | 0 | 2
2026-05-06 | 30 | 14 | 0 | 2
2026-05-07 | 30 | 14 | 0 | 2
2026-05-08 | 29 | 14 | 0 | 2
2026-05-09 | 29 | 14 | 0 | 2
2026-05-10 | 29 | 14 | 0 | 2
2026-05-11 | 29 | 14 | 0 | 2
2026-05-12 | 29 | 14 | 0 | 2
2026-05-13 | 29 | 14 | 0 | 2
2026-05-14 | 29 | 14 | 0 | 2
2026-05-15 | 27 | 15 | 0 | 2
2026-05-16 | 27 | 15 | 0 | 2
2026-05-17 | 27 | 15 | 0 | 2
2026-05-18 | 27 | 15 | 0 | 2
2026-05-19 | 27 | 16 | 0 | 2
2026-05-20 | 26 | 16 | 0 | 2
2026-05-21 | 25 | 16 | 0 | 2
2026-05-22 | 25 | 16 | 0 | 2
2026-05-23 | 25 | 16 | 0 | 2
2026-05-24 | 25 | 16 | 0 | 2
2026-05-25 | 25 | 16 | 0 | 2
2026-05-26 | 25 | 17 | 0 | 2
2026-05-27 | 25 | 17 | 0 | 2
2026-05-28 | 25 | 17 | 0 | 2
2026-05-29 | 25 | 17 | 0 | 2
2026-05-30 | 25 | 17 | 0 | 2
2026-05-31 | 18 | 16 | 0 | 2
2026-06-01 | 18 | 16 | 0 | 2
2026-06-02 | 18 | 17 | 1 | 3
2026-06-03 | 18 | 17 | 1 | 3
2026-06-04 | 18 | 17 | 1 | 3
2026-06-05 | 18 | 17 | 1 | 3
2026-06-06 | 18 | 17 | 1 | 3
2026-06-07 | 18 | 17 | 1 | 3
2026-06-08 | 18 | 17 | 1 | 3
2026-06-09 | 18 | 17 | 1 | 3
2026-06-10 | 18 | 17 | 1 | 3
2026-06-11 | 18 | 17 | 1 | 3
2026-06-12 | 18 | 17 | 1 | 3
2026-06-13 | 18 | 17 | 1 | 3
2026-06-14 | 18 | 17 | 1 | 3
2026-06-15 | 14 | 13 | 1 | 2
2026-06-16 | 14 | 14 | 1 | 2
2026-06-17 | 12 | 14 | 1 | 2
2026-06-18 | 12 | 14 | 1 | 2
2026-06-19 | 12 | 14 | 1 | 2
2026-06-20 | 12 | 14 | 1 | 2
2026-06-21 | 12 | 14 | 1 | 2
2026-06-22 | 12 | 13 | 1 | 2
2026-06-23 | 12 | 13 | 1 | 2
2026-06-24 | 12 | 13 | 1 | 2
2026-06-25 | 12 | 13 | 1 | 2
2026-06-26 | 12 | 13 | 1 | 2
2026-06-27 | 12 | 13 | 1 | 2
2026-06-28 | 12 | 13 | 1 | 2
2026-06-29 | 12 | 13 | 1 | 2
2026-06-30 | 9 | 9 | 0 | 1
2026-07-01 | 9 | 8 | 0 | 0
2026-07-02 | 9 | 8 | 0 | 0
2026-07-03 | 9 | 8 | 0 | 0
2026-07-04 | 9 | 8 | 0 | 0
2026-07-05 | 9 | 8 | 0 | 0
2026-07-06 | 9 | 8 | 0 | 0
2026-07-07 | 9 | 8 | 0 | 0
2026-07-08 | 9 | 8 | 0 | 0
2026-07-09 | 9 | 8 | 0 | 0
2026-07-10 | 9 | 8 | 0 | 0
2026-07-11 | 9 | 8 | 0 | 0
2026-07-12 | 9 | 8 | 0 | 0
2026-07-13 | 9 | 8 | 0 | 0
2026-07-14 | 9 | 9 | 0 | 0
2026-07-15 | 9 | 9 | 0 | 0
2026-07-16 | 9 | 11 | 0 | 0
2026-07-17 | 9 | 11 | 0 | 0
2026-07-18 | 9 | 11 | 0 | 0
2026-07-19 | 9 | 11 | 0 | 0
2026-07-20 | 9 | 11 | 0 | 0
2026-07-21 | 9 | 11 | 0 | 0
2026-07-22 | 9 | 11 | 0 | 0
2026-07-23 | 9 | 11 | 0 | 0
2026-07-24 | 9 | 11 | 0 | 0
2026-07-25 | 9 | 11 | 0 | 0
2026-07-26 | 9 | 11 | 0 | 0
2026-07-27 | 9 | 11 | 0 | 0
2026-07-28 | 9 | 11 | 0 | 0
2026-07-29 | 9 | 10 | 0 | 0
2026-07-30 | 9 | 10 | 0 | 0
2026-07-31 | 9 | 9 | 0 | 0
2026-08-01 | 9 | 9 | 0 | 0
2026-08-02 | 9 | 9 | 0 | 0
2026-08-03 | 9 | 9 | 0 | 0
2026-08-04 | 9 | 9 | 0 | 0
2026-08-05 | 9 | 9 | 0 | 0
2026-08-06 | 9 | 9 | 0 | 0
2026-08-07 | 9 | 9 | 0 | 0
2026-08-08 | 9 | 9 | 0 | 0
2026-08-09 | 9 | 9 | 0 | 0
2026-08-10 | 9 | 9 | 0 | 0
2026-08-11 | 9 | 9 | 0 | 0
2026-08-12 | 9 | 9 | 0 | 0
2026-08-13 | 9 | 9 | 0 | 0
2026-08-14 | 9 | 8 | 0 | 0
2026-08-15 | 9 | 8 | 0 | 0
2026-08-16 | 9 | 8 | 0 | 0
2026-08-17 | 9 | 8 | 0 | 0
2026-08-18 | 9 | 8 | 0 | 0
2026-08-19 | 9 | 8 | 0 | 0
2026-08-20 | 9 | 8 | 0 | 0
2026-08-21 | 9 | 8 | 0 | 0
2026-08-22 | 9 | 8 | 0 | 0
2026-08-23 | 9 | 8 | 0 | 0
2026-08-24 | 9 | 8 | 0 | 0
2026-08-25 | 9 | 8 | 0 | 0
2026-08-26 | 9 | 8 | 0 | 0
2026-08-27 | 9 | 8 | 0 | 0
2026-08-28 | 9 | 8 | 0 | 0
2026-08-29 | 9 | 8 | 0 | 0
2026-08-30 | 9 | 8 | 0 | 0
2026-08-31 | 9 | 5 | 0 | 0
2026-09-01 | 9 | 5 | 0 | 0
2026-09-02 | 9 | 5 | 0 | 0
2026-09-03 | 9 | 5 | 0 | 0
2026-09-04 | 9 | 5 | 0 | 0
2026-09-05 | 9 | 5 | 0 | 0
2026-09-06 | 9 | 5 | 0 | 0
2026-09-07 | 9 | 5 | 0 | 0
2026-09-08 | 9 | 4 | 0 | 0
2026-09-09 | 9 | 4 | 0 | 0
2026-09-10 | 9 | 4 | 0 | 0
2026-09-11 | 9 | 4 | 0 | 0
2026-09-12 | 9 | 4 | 0 | 0
2026-09-13 | 9 | 4 | 0 | 0
2026-09-14 | 9 | 4 | 0 | 0
2026-09-15 | 9 | 4 | 0 | 0
2026-09-16 | 9 | 4 | 0 | 0
2026-09-17 | 9 | 4 | 0 | 0
2026-09-18 | 9 | 4 | 0 | 0
2026-09-19 | 9 | 4 | 0 | 0
2026-09-20 | 9 | 4 | 0 | 0
2026-09-21 | 9 | 4 | 0 | 0
2026-09-22 | 9 | 4 | 0 | 0
2026-09-23 | 9 | 4 | 0 | 0
2026-09-24 | 9 | 4 | 0 | 0
2026-09-25 | 9 | 4 | 0 | 0
2026-09-26 | 9 | 4 | 0 | 0
2026-09-27 | 9 | 4 | 0 | 0
2026-09-28 | 9 | 4 | 0 | 0
2026-09-29 | 9 | 4 | 0 | 0
2026-09-30 | 2 | 3 | 0 | 0
2026-10-01 | 2 | 3 | 0 | 0
2026-10-02 | 2 | 3 | 0 | 0
2026-10-03 | 2 | 3 | 0 | 0
2026-10-04 | 2 | 3 | 0 | 0
2026-10-05 | 2 | 3 | 0 | 0
2026-10-06 | 2 | 3 | 0 | 0
2026-10-07 | 2 | 3 | 0 | 0
2026-10-08 | 2 | 3 | 0 | 0
2026-10-09 | 2 | 3 | 0 | 0
2026-10-10 | 2 | 3 | 0 | 0
2026-10-11 | 2 | 3 | 0 | 0
2026-10-12 | 2 | 3 | 0 | 0
2026-10-13 | 2 | 3 | 0 | 0
2026-10-14 | 2 | 3 | 0 | 0
2026-10-15 | 2 | 3 | 0 | 0
2026-10-16 | 2 | 4 | 0 | 0
2026-10-17 | 2 | 4 | 0 | 0
2026-10-18 | 2 | 4 | 0 | 0
2026-10-19 | 2 | 4 | 0 | 0
2026-10-20 | 2 | 4 | 0 | 0
2026-10-21 | 2 | 4 | 0 | 0
2026-10-22 | 2 | 4 | 0 | 0
2026-10-23 | 2 | 4 | 0 | 0
2026-10-24 | 2 | 4 | 0 | 0
2026-10-25 | 2 | 4 | 0 | 0
2026-10-26 | 2 | 4 | 0 | 0
2026-10-27 | 2 | 4 | 0 | 0
2026-10-28 | 2 | 4 | 0 | 0
2026-10-29 | 2 | 4 | 0 | 0
2026-10-30 | 2 | 4 | 0 | 0
2026-10-31 | 2 | 4 | 0 | 0
2026-11-01 | 2 | 4 | 0 | 0
2026-11-02 | 2 | 4 | 0 | 0
2026-11-03 | 2 | 4 | 0 | 0
2026-11-04 | 2 | 4 | 0 | 0
2026-11-05 | 2 | 4 | 0 | 0
2026-11-06 | 2 | 4 | 0 | 0
2026-11-07 | 2 | 4 | 0 | 0
2026-11-08 | 2 | 4 | 0 | 0
2026-11-09 | 2 | 4 | 0 | 0
2026-11-10 | 2 | 4 | 0 | 0
2026-11-11 | 2 | 4 | 0 | 0
2026-11-12 | 2 | 4 | 0 | 0
2026-11-13 | 2 | 4 | 0 | 0
2026-11-14 | 2 | 4 | 0 | 0
2026-11-15 | 2 | 4 | 0 | 0
2026-11-16 | 2 | 4 | 0 | 0
2026-11-17 | 2 | 4 | 0 | 0
2026-11-18 | 2 | 4 | 0 | 0
2026-11-19 | 2 | 4 | 0 | 0
2026-11-20 | 2 | 4 | 0 | 0
2026-11-21 | 2 | 4 | 0 | 0
2026-11-22 | 2 | 4 | 0 | 0
2026-11-23 | 2 | 4 | 0 | 0
2026-11-24 | 2 | 4 | 0 | 0
2026-11-25 | 2 | 4 | 0 | 0
2026-11-26 | 2 | 4 | 0 | 0
2026-11-27 | 2 | 4 | 0 | 0
2026-11-28 | 2 | 4 | 0 | 0
2026-11-29 | 2 | 4 | 0 | 0
2026-11-30 | 2 | 4 | 0 | 0
2026-12-01 | 2 | 4 | 0 | 0
2026-12-02 | 2 | 4 | 0 | 0
2026-12-03 | 2 | 4 | 0 | 0
2026-12-04 | 2 | 4 | 0 | 0
2026-12-05 | 2 | 4 | 0 | 0
2026-12-06 | 2 | 4 | 0 | 0
2026-12-07 | 2 | 4 | 0 | 0
2026-12-08 | 2 | 4 | 0 | 0
2026-12-09 | 2 | 4 | 0 | 0
2026-12-10 | 2 | 4 | 0 | 0
2026-12-11 | 2 | 4 | 0 | 0
2026-12-12 | 2 | 4 | 0 | 0
2026-12-13 | 2 | 4 | 0 | 0
2026-12-14 | 2 | 4 | 0 | 0
2026-12-15 | 2 | 4 | 0 | 0
2026-12-16 | 2 | 4 | 0 | 0
2026-12-17 | 2 | 4 | 0 | 0
2026-12-18 | 2 | 4 | 0 | 0
2026-12-19 | 2 | 4 | 0 | 0
2026-12-20 | 2 | 4 | 0 | 0
2026-12-21 | 2 | 4 | 0 | 0
2026-12-22 | 2 | 4 | 0 | 0
2026-12-23 | 2 | 3 | 0 | 0
2026-12-24 | 2 | 3 | 0 | 0
2026-12-25 | 2 | 3 | 0 | 0
2026-12-26 | 2 | 3 | 0 | 0
2026-12-27 | 2 | 3 | 0 | 0
2026-12-28 | 2 | 3 | 0 | 0
2026-12-29 | 2 | 3 | 0 | 0
2026-12-30 | 2 | 3 | 0 | 0
2026-12-31 | 1 | 0 | 0 | 0
2027-01-01 | 0 | 0 | 0 | 0

## data Draft-april26
Vorgangsmodus | Initiative | Process | Phase | Process level | Process Group | % Work done | IT Process Consultant | IT Process Initiative Lead | IT Process Manager | Start | End | Duration in days | Process Approval Date | Actual Phase | Planned phase | Associated Process on L1 | Comment | Parent Process
Manuell geplant |  | Management Processes |  | L1 | MP | 31% |  |  |  | 2025-10-01 | [5 empty] | Management Processes
Automatisch geplant | Corporate IT body | Manage IT strategy | Total | L1 | MP | 50% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-02-02 | 2026-07-29 | 128 | 2026-05-06 |  | 1 | Manage IT strategy
Manuell geplant | Corporate IT body | Manage IT strategy | Elaboration | L1 | MP | 50% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-02-02 | 2026-04-30 | 64 |  | Elaboration in progress | Elaboration in progress | Manage IT strategy
Manuell geplant | Corporate IT body | Manage IT strategy | Implementation LIS | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-05-14 | 2026-07-29 | 55 |  |  | Scheduled | Manage IT strategy
Manuell geplant | Corporate IT body | Manage IT strategy | Implementation COT | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | [6 empty] | Manage IT strategy
Manuell geplant | Corporate IT body | Manage IT strategy | Implementation LUS | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | [6 empty] | Manage IT strategy
Automatisch geplant | Corporate IT body | Manage IT governance framework | Total | L1 | MP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-08-31 | 169 |  |  |  | Manage IT governance framework
Manuell geplant | Corporate IT body | Manage IT governance framework | Elaboration | L1 | MP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-03-16 | 2026-05-21 | 49 |  | Elaboration in progress | Elaboration in progress | Manage IT governance framework
Manuell geplant | Corporate IT body | Manage IT governance framework | Implementation LIS | L1 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-05-25 | 2026-08-31 | 71 |  |  | Scheduled | Manage IT governance framework
Manuell geplant | Corporate IT body | Manage IT governance framework | Implementation COT | L1 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | [6 empty] | Manage IT governance framework
Manuell geplant | Corporate IT body | Manage IT governance framework | Implementation LUS | L1 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | [6 empty] | Manage IT governance framework
Automatisch geplant | Corporate IT body | Maintain IT glossary | Total | L2 | MP | 25% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-01-17 | 8 |  |  |  | Manage IT governance framework |  | Manage IT governance framework
Manuell geplant | Corporate IT body | Maintain IT glossary | Elaboration | L2 | MP | 25% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | [5 empty] | Manage IT governance framework |  | Manage IT governance framework
Manuell geplant | Corporate IT body | Maintain IT glossary | Implementation LIS | L2 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-01-17 | 7 |  | Delayed | Implementation LIS Done | Manage IT governance framework |  | Manage IT governance framework
Manuell geplant | Corporate IT body | Maintain IT glossary | Implementation COT | L2 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-01-07 | [5 empty] | Manage IT governance framework |  | Manage IT governance framework
Manuell geplant | Corporate IT body | Maintain IT glossary | Implementation LUS | L2 | MP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Felder Max (LLI) | Mielenz Thomas (LMT) | [6 empty] | Manage IT governance framework |  | Manage IT governance framework
Automatisch geplant | Corporate IT body | Manage enterprise architecture | Total | L1 | MP | 0% |  |  |  | 2025-10-16 | 2026-07-16 | 195.85 |  |  |  | Manage enterprise architecture
Manuell geplant | Corporate IT body | Manage enterprise architecture | Elaboration | L1 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 2026-02-23 | 2026-05-08 |  |  | Delayed | Elaboration in progress | Manage enterprise architecture
Automatisch geplant | Corporate IT body | Manage enterprise architecture | Implementation LIS | L1 | MP | 0% |  |  |  | 2026-05-08 | 2026-07-16 |  |  |  | Scheduled | Manage enterprise architecture
Manuell geplant | Corporate IT body | Manage enterprise architecture | Implementation COT | L1 | MP | 0% |  |  |  | 2026-05-08 | 2026-05-11 |  |  |  | Scheduled | Manage enterprise architecture
Manuell geplant | Corporate IT body | Manage enterprise architecture | Implementation LUS | L1 | MP | 0% |  |  |  | 2026-05-08 | 2026-05-11 |  |  |  | Scheduled | Manage enterprise architecture
Automatisch geplant | Corporate IT body | Strategic architecture process | Total | L2 | MP | 0% |  |  |  | 2025-10-16 | 2026-04-30 |  |  |  |  | Manage enterprise architecture
Manuell geplant | Corporate IT body | Strategic architecture process | Elaboration | L2 | MP | 0% | Hoermann Patrick (LLI) | Gujral Parth (COB-COT-IT) | Nussbaumer Florian (LBC) | 2026-02-23 | 2026-04-30 |  |  | Delayed | Elaboration in progress | Manage enterprise architecture
Manuell geplant | Corporate IT body | Strategic architecture process | Implementation LIS | L2 | MP | 0% | [9 empty] | Manage enterprise architecture
Manuell geplant | Corporate IT body | Strategic architecture process | Implementation COT | L2 | MP | 0% | [9 empty] | Manage enterprise architecture
Manuell geplant | Corporate IT body | Strategic architecture process | Implementation LUS | L2 | MP | 0% | [9 empty] | Manage enterprise architecture
Manuell geplant | ITSM | Manage IT portfolio | Total | L1 | MP | 78% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | ? |  | 2025-11-10 | 2026-05-15 | 135 |  |  |  | Manage IT portfolio
Manuell geplant | ITSM | Manage IT portfolio | Elaboration | L1 | MP | 100% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | ? |  | 2025-11-11 | 2026-01-29 | 58 |  | Elaboration Done | Elaboration Done | Manage IT portfolio
Manuell geplant | ITSM | Manage IT portfolio | Implementation LIS | L1 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | ? | [7 empty] | Manage IT portfolio
Manuell geplant | ITSM | Manage IT portfolio | Implementation COT | L1 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | ? | [7 empty] | Manage IT portfolio
Manuell geplant | ITSM | Manage IT portfolio | Implementation LUS | L1 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | ? | [7 empty] | Manage IT portfolio
Automatisch geplant | IT project management | Manage IT project portfolio | Total | L2 | MP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-10 | 2026-05-31 | 145 |  |  |  | Manage IT portfolio |  | Manage IT portfolio
Manuell geplant | IT project management | Manage IT project portfolio | Elaboration | L2 | MP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-10 | 2025-12-10 | 23 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT portfolio |  | Manage IT portfolio
Manuell geplant | IT project management | Manage IT project portfolio | Implementation LIS | L2 | MP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2026-02-01 | 2026-05-31 | 85 |  | Delayed | Implementation LIS | Manage IT portfolio | No actual status | Manage IT portfolio
Manuell geplant | IT project management | Manage IT project portfolio | Implementation COT | L2 | MP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT portfolio |  | Manage IT portfolio
Manuell geplant | IT project management | Manage IT project portfolio | Implementation LUS | L2 | MP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT portfolio |  | Manage IT portfolio
Automatisch geplant | ITSM | Manage IT service portfolio | Total | L2 | MP | 50% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Birgit Gerathewohl (LIS) | Reiner Heiko (HAU-ITSA) | 2026-04-01 | 2026-09-08 | 115 |  |  |  | Manage IT portfolio |  | Manage IT portfolio
Manuell geplant | ITSM | Manage IT service portfolio | Elaboration | L2 | MP | 50% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Birgit Gerathewohl (LIS) | Reiner Heiko (HAU-ITSA) | 2026-04-01 | 2026-07-15 | 54 |  | Elaboration in progress | Elaboration in progress | Manage IT portfolio |  | Manage IT portfolio
Manuell geplant | ITSM | Manage IT service portfolio | Implementation LIS | L2 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Birgit Gerathewohl (LIS) | Reiner Heiko (HAU-ITSA) |  |  |  |  | Not planned yet |  | Manage IT portfolio |  | Manage IT portfolio
Manuell geplant | ITSM | Manage IT service portfolio | Implementation COT | L2 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Birgit Gerathewohl (LIS) | Reiner Heiko (HAU-ITSA) |  |  |  |  | Not planned yet |  | Manage IT portfolio |  | Manage IT portfolio
Manuell geplant | ITSM | Manage IT service portfolio | Implementation LUS | L2 | MP | 0% | Frank Maren (LIS);Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Birgit Gerathewohl (LIS) | Reiner Heiko (HAU-ITSA) |  |  |  |  | Not planned yet |  | Manage IT portfolio |  | Manage IT portfolio
Automatisch geplant | IT planning and steering | Manage and control IT financials | Total | L1 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | 2026-07-31 | 208 |  |  |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage and control IT financials | Elaboration | L1 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | 2026-04-30 | 142 |  | Elaboration in progress | Elaboration in progress | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage and control IT financials | Implementation LIS | L1 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2026-05-01 | 2026-07-31 | 66 |  |  | Scheduled | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage and control IT financials | Implementation COT | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage and control IT financials | Implementation LUS | L1 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials
Manuell geplant | IT planning and steering | Create and maintain IT budgets | Total | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Create and maintain IT budgets | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Create and maintain IT budgets | Implementation LIS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Create and maintain IT budgets | Implementation COT | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Create and maintain IT budgets | Implementation LUS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Approve and communicate budget plan | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Approve and communicate budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Approve and communicate budget plan | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Approve and communicate budget plan | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Approve and communicate budget plan | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Collect and consolidate budget from stakeholders | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Collect and consolidate budget from stakeholders | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Collect and consolidate budget from stakeholders | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Collect and consolidate budget from stakeholders | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Develop preliminary budget plan | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Develop preliminary budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Develop preliminary budget plan | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Develop preliminary budget plan | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Develop preliminary budget plan | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Maintan and adjust budget | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Maintan and adjust budget | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Maintan and adjust budget | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Maintan and adjust budget | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Maintan and adjust budget | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Review budget plan | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 |  |  |  |  | 18 | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Review budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Review budget plan | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Review budget plan | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Review budget plan | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Revise and optimize budget plan | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Revise and optimize budget plan | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Revise and optimize budget plan | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Revise and optimize budget plan | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Revise and optimize budget plan | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | [6 empty] | Manage and control IT financials |  | Create and maintain IT budgets
Manuell geplant | IT planning and steering | Manage finance and accounting | Total | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Mielenz Thomas (LMT) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage finance and accounting | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage finance and accounting | Implementation LIS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage finance and accounting | Implementation COT | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage finance and accounting | Implementation LUS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Define financial management framework | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Define financial management framework | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Define financial management framework | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Define financial management framework | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Define financial management framework | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Establish financial accounting structure | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Establish financial accounting structure | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Establish financial accounting structure | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Establish financial accounting structure | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Establish financial accounting structure | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage finance and accounting
Manuell geplant | IT planning and steering | Manage IT costs | Total | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage IT costs | Implementation LIS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage IT costs | Implementation COT |  | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Manage IT costs | Implementation LUS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Compare actual cost to budget forecast | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Compare actual cost to budget forecast | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Compare actual cost to budget forecast | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Compare actual cost to budget forecast | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Compare actual cost to budget forecast | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Initiate corrective or preventive actions | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Initiate corrective or preventive actions | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Initiate corrective or preventive actions | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Initiate corrective or preventive actions | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Initiate corrective or preventive actions | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Report actual IT costs | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Report actual IT costs | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Report actual IT costs | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Report actual IT costs | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Report actual IT costs | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage IT costs
Manuell geplant | IT planning and steering | Model and allocate IT costs | Total | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Model and allocate IT costs | Elaboration | L2 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Model and allocate IT costs | Implementation LIS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Model and allocate IT costs | Implementation COT | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Model and allocate IT costs | Implementation LUS | L2 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Manage and control IT financials
Manuell geplant | IT planning and steering | Apply cost model to calculate service cost per unit | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Apply cost model to calculate service cost per unit | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Apply cost model to calculate service cost per unit | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Apply cost model to calculate service cost per unit | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Implement cost allocation to stakeholders or companies | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Implement cost allocation to stakeholders or companies | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Implement cost allocation to stakeholders or companies | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Define cost allocation principles | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Define cost allocation principles | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Define cost allocation principles | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Define cost allocation principles | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Define cost allocation principles | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Establish cost allocation model | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Establish cost allocation model | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Establish cost allocation model | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Establish cost allocation model | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Establish cost allocation model | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Gather relevant cost and consumption data | Total | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Gather relevant cost and consumption data | Elaboration | L3 | MP | 50% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | 2025-10-15 | [5 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Gather relevant cost and consumption data | Implementation LIS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Gather relevant cost and consumption data | Implementation COT | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Manuell geplant | IT planning and steering | Gather relevant cost and consumption data | Implementation LUS | L3 | MP | 0% | Hynek Tobias (LIS);Kreis Andreas (LLI) | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | [6 empty] | Manage and control IT financials |  | Model and allocate IT costs
Automatisch geplant | Corporate IT body | Manage IT stakeholder relationships | Total | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-12-23 | 191 |  |  |  | Manage IT stakeholder relationships
Manuell geplant | Corporate IT body | Manage IT stakeholder relationships | Elaboration | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-06-15 | 54 |  | Delayed | Elaboration in progress | Manage IT stakeholder relationships
Manuell geplant | Corporate IT body | Manage IT stakeholder relationships | Implementation LIS | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | 2026-10-15 | 2026-12-23 | 50 |  |  | Scheduled | Manage IT stakeholder relationships
Manuell geplant | Corporate IT body | Manage IT stakeholder relationships | Implementation COT | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | [6 empty] | Manage IT stakeholder relationships
Manuell geplant | Corporate IT body | Manage IT stakeholder relationships | Implementation LUS | L1 | MP | 0% | Kreis Andreas (LLI) | Felder Max (LLI) | Mielenz Thomas (LMT) | [6 empty] | Manage IT stakeholder relationships
Automatisch geplant | ITSM | Manage IT processes and continuous improvement | Total | L1 | MP | 21% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-05-31 | 173 |  |  |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage IT processes and continuous improvement | Elaboration | L1 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage IT processes and continuous improvement | Implementation LIS | L1 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage IT processes and continuous improvement | Implementation COT | L1 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage IT processes and continuous improvement | Implementation LUS | L1 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Develop and maintain IT BPM framework | Total | L2 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-15 | 2025-10-16 | 1 | 2025-09-18 |  |  | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Develop and maintain IT BPM framework | Elaboration | L2 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-08-04 | 2025-08-30 | 20 |  | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Develop and maintain IT BPM framework | Implementation LIS | L2 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Develop and maintain IT BPM framework | Implementation COT | L2 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Develop and maintain IT BPM framework | Implementation LUS | L2 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Automatisch geplant | ITSM | Manage continuous improvement | Total | L2 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-01-30 | 88 |  |  |  | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage continuous improvement | Elaboration | L2 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-01-30 | 88 |  | Delayed | Elaboration Done | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage continuous improvement | Implementation LIS | L2 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage continuous improvement | Implementation COT | L2 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage continuous improvement | Implementation LUS | L2 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Manage a common approach to contiual improvement | Total | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) |  | 2025-10-16 |  |  |  |  | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage a common approach to contiual improvement | Elaboration | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage a common approach to contiual improvement | Implementation LIS | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage a common approach to contiual improvement | Implementation COT | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage a common approach to contiual improvement | Implementation LUS | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage continual improvement initiative | Total | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) |  | 2025-10-16 |  |  |  |  | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage continual improvement initiative | Elaboration | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage continual improvement initiative | Implementation LIS | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage continual improvement initiative | Implementation COT | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Manuell geplant | ITSM | Manage continual improvement initiative | Implementation LUS | L3 | MP | 0% | Boehme Matthias (LIS-BPMO);Rollinger Alexander (LIS) | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage continuous improvement
Automatisch geplant | ITSM | Perform operational process management | Total | L2 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-05-31 | 173 | 2025-09-18 |  |  | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | Corporate IT body | Perform operational process management (V 2.0) | Elaboration | L2 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement | approximate date | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Perform operational process management | Implementation LIS | L2 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Perform operational process management | Implementation COT | L2 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Manuell geplant | ITSM | Perform operational process management | Implementation LUS | L2 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Manage IT processes and continuous improvement
Automatisch geplant | ITSM | Identify process and determine goals | Total | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | 2025-09-18 |  |  | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | Corporate IT body | Identify process and determine goals (V 2.0) | Elaboration | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement | approximate date | Perform operational process management (V 2.0)
Manuell geplant | ITSM | Identify process and determine goals | Implementation LIS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Identify process and determine goals | Implementation COT | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Identify process and determine goals | Implementation LUS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Automatisch geplant | ITSM | Elaborate to-be process | Total | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | 2025-09-18 |  |  | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | Corporate IT body | Elaborate to-be process (V 2.0) | Elaboration | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement | approximate date | Perform operational process management (V 2.0)
Manuell geplant | ITSM | Elaborate to-be process | Implementation LIS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Elaborate to-be process | Implementation COT | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Elaborate to-be process | Implementation LUS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Automatisch geplant | ITSM | Plan process execution | Total | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | 2025-09-18 |  |  | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | Corporate IT body | Plan process execution (V 2.0) | Elaboration | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement | approximate date | Perform operational process management (V 2.0)
Manuell geplant | ITSM | Plan process execution | Implementation LIS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Plan process execution | Implementation COT | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Plan process execution | Implementation LUS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Automatisch geplant | ITSM | Implement process | Total | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 | 2025-09-19 |  |  | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | Corporate IT body | Implement process (V 2.0) | Elaboration | L3 | MP | 25% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2026-01-12 | 2026-05-31 | 100 |  | Elaboration in progress | Elaboration in progress | Manage IT processes and continuous improvement |  | Perform operational process management (V 2.0)
Manuell geplant | ITSM | Implement process | Implementation LIS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Implement process | Implementation COT | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Implement process | Implementation LUS | L3 | MP | 0% | Rollinger Alexander (LIS) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Automatisch geplant | ITSM | Perform and measure process | Total | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | 2025-09-18 |  |  | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | Corporate IT body | Perform and measure process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement | approximate date | Perform operational process management (V 2.0)
Manuell geplant | ITSM | Perform and measure process | Implementation LIS | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Perform and measure process | Implementation COT | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Perform and measure process | Implementation LUS | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Automatisch geplant | ITSM | Analyse process | Total | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | 2025-09-18 |  |  | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | Corporate IT body | Analyse process | Elaboration | L3 | MP | 100% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Elaboration Done | Manage IT processes and continuous improvement | approximate date | Perform operational process management (V 2.0)
Manuell geplant | ITSM | Analyse process | Implementation LIS | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Analyse process | Implementation COT | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Manuell geplant | ITSM | Analyse process | Implementation LUS | L3 | MP | 0% | Hoermann Patrick (LLI) | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Manage IT processes and continuous improvement |  | Perform operational process management
Automatisch geplant | n/a | Manage IT risks and compliance | Total | L1 | MP | 22% | Hoermann Patrick (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 |  |  |  |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT risks and compliance | Elaboration | L1 | MP | 100% | Hoermann Patrick (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Elaboration Done | Manage IT risks and compliance | date to be reviewed
Manuell geplant | Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LIS | L1 | MP | 0% | Hoermann Patrick (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT risks and compliance | Implementation COT | L1 | MP | 0% | Hoermann Patrick (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT risks and compliance | Implementation LUS | L1 | MP | 0% | Hoermann Patrick (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance
Automatisch geplant | Central area (Jan Müskens) | Manage IT risks | Total | L2 | MP | 0% | tbd | ? | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT risks | Elaboration | L2 | MP | 0% | tbd | ? | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT risks | Implementation LIS | L2 | MP | 0% | tbd | ? | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT risks | Implementation COT | L2 | MP | 0% | tbd | ? | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT risks | Implementation LUS | L2 | MP | 0% | tbd | ? | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT risks and compliance
Automatisch geplant | Central area (Jan Müskens) | Manage IT compliance | Total | L2 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT compliance | Elaboration | L2 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance | date to be reviewed | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT compliance | Implementation LIS | L2 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT compliance | Implementation COT | L2 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT risks and compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT compliance | Implementation LUS | L2 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT risks and compliance
Automatisch geplant | Central area (Jan Müskens) | Monitor to delegate | Total | L3 | MP | 25% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Monitor to delegate | Elaboration | L3 | MP | 25% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance | date to be reviewed | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Monitor to delegate | Implementation LIS | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Monitor to delegate | Implementation COT | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Monitor to delegate | Implementation LUS | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Automatisch geplant | Central area (Jan Müskens) | Requirements to measures | Total | L3 | MP | 25% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Requirements to measures | Elaboration | L3 | MP | 25% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance | date to be reviewed | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Requirements to measures | Implementation LIS | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Requirements to measures | Implementation COT | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Requirements to measures | Implementation LUS | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Automatisch geplant | Central area (Jan Müskens) | Implement to improve | Total | L3 | MP | 25% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Implement to improve | Elaboration | L3 | MP | 25% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance | date to be reviewed | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Implement to improve | Implementation LIS | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Implement to improve | Implementation COT | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Implement to improve | Implementation LUS | L3 | MP | 0% | tbd | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Automatisch geplant | Central area (Jan Müskens) | Manage IT-C strategy | Total | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C strategy | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance | date to be reviewed | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C strategy | Implementation LIS | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C strategy | Implementation COT | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C strategy | Implementation LUS | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Automatisch geplant | Central area (Jan Müskens) | Manage IT-C framework | Total | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C framework | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance | date to be reviewed | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C framework | Implementation LIS | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C framework | Implementation COT | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | Manage IT-C framework | Implementation LUS | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Automatisch geplant | Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Total | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  |  |  | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Elaboration | L3 | MP | 25% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | 2025-10-01 | 2026-09-30 | 261 |  | Elaboration in progress | Elaboration in progress | Manage IT risks and compliance | date to be reviewed | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LIS | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation COT | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Manuell geplant | Central area (Jan Müskens) | DC/DCC/MSC IT-compliance | Implementation LUS | L3 | MP | 0% | Kreis Andreas (LLI) | Mueskens Jan (LHO) | Monnier Murielle (LEC) | [6 empty] | Manage IT risks and compliance |  | Manage IT compliance
Automatisch geplant |  | Core Processes |  | L1 | CP | 28% |  |  |  | 2025-04-01 | 2026-09-25 |  |  |  |  | Core Processes
Automatisch geplant | Corporate IT body | Plan IT service | Total | L1 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2026-04-30 | 195 |  |  |  | Plan IT service
Manuell geplant | Corporate IT body | Plan IT service | Elaboration | L1 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-10-16 | 2025-10-31 | 12 | 2025-12-10 | Elaboration Done | Elaboration Done | Plan IT service
Manuell geplant | Corporate IT body | Plan IT service | Implementation LIS | L1 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-01 | 2026-02-28 | 85 |  | Delayed | Implementation LIS Done | Plan IT service
Manuell geplant | Corporate IT body | Plan IT service | Implementation COT | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-03 | 2026-03-31 | 107 |  | Delayed | Implementation COT Done | Plan IT service
Manuell geplant | Corporate IT body | Plan IT service | Implementation LUS | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | [6 empty] | Plan IT service
Manuell geplant | Corporate IT body | Perform initial assessment of customer need | Total | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-05 | 3 | 2025-08-19 |  |  | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Perform initial assessment of customer need | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 |  | Elaboration Done | Elaboration Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Perform initial assessment of customer need | Implementation LIS | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-01 | 2026-02-28 | 85 |  | Delayed | Implementation LIS Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Perform initial assessment of customer need | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-03 | 2026-03-31 | 107 |  | Delayed | Implementation COT Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Perform initial assessment of customer need | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | [6 empty] | Plan IT service |  | Plan IT service
Automatisch geplant | Corporate IT body | Evaluate and qualify IT demand | Total | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2026-04-30 | 195 | 2025-12-10 |  |  | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Evaluate and qualify IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 |  | Elaboration Done | Elaboration Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Evaluate and qualify IT demand | Implementation LIS | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-01 | 2026-02-28 | 85 |  | Delayed | Implementation LIS Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Evaluate and qualify IT demand | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-03 | 2026-03-31 | 107 |  | Delayed | Implementation COT Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Evaluate and qualify IT demand | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | [6 empty] | Plan IT service |  | Plan IT service
Automatisch geplant | Corporate IT body | Analyse architecture impact | Total | L3 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2025-08-01 | 2026-04-30 | 195 |  |  |  | Plan IT service |  | Evaluate and qualify IT demand
Manuell geplant | Corporate IT body | Analyse architecture impact | Elaboration | L3 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-10-15 | 54 |  | Elaboration Done | Elaboration Done | Plan IT service |  | Evaluate and qualify IT demand
Manuell geplant | Corporate IT body | Analyse architecture impact | Implementation LIS | L3 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2026-11-01 | 2026-02-28 | 0 |  |  |  | Plan IT service |  | Evaluate and qualify IT demand
Manuell geplant | Corporate IT body | Analyse architecture impact | Implementation COT | L3 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  | Delayed | Implementation COT | Plan IT service |  | Evaluate and qualify IT demand
Manuell geplant | Corporate IT body | Analyse architecture impact | Implementation LUS | L3 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Pernet Benoit (LEC) (MIN) | Mielenz Thomas (LMT) | [6 empty] | Plan IT service |  | Evaluate and qualify IT demand
Manuell geplant | Corporate IT body | Approve IT demand | Total | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 | 2025-08-19 |  |  | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Approve IT demand | Elaboration | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-08-01 | 2025-08-01 | 1 |  | Elaboration Done | Elaboration Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Approve IT demand | Implementation LIS | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-01 | 2026-02-28 | 85 |  | Delayed | Implementation LIS Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Approve IT demand | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | 2025-11-03 | 2026-03-31 | 107 |  | Delayed | Implementation COT Done | Plan IT service |  | Plan IT service
Manuell geplant | Corporate IT body | Approve IT demand | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Spieth Tina (LIS) | Mielenz Thomas (LMT) | [6 empty] | Plan IT service |  | Plan IT service
Automatisch geplant | ITSM | Build IT Service | Total | L1 | CP | 41% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service
Manuell geplant | ITSM | Build IT Service | Elaboration | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service
Manuell geplant | ITSM | Build IT Service | Implementation LIS | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service
Manuell geplant | ITSM | Build IT Service | Implementation COT | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service
Manuell geplant | ITSM | Build IT Service | Implementation LUS | L1 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service
Automatisch geplant | ITSM | Design IT service | Total | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Design IT service | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-05-04 | 2026-07-31 | 65 |  | Elaboration in progress | Elaboration done | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Design IT service | Implementation LIS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Design IT service | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Design IT service | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Automatisch geplant | Architecture management | Define solution target architecture | Total | L3 | CP | 50% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) | 2026-01-14 | 2026-06-22 | 114 |  |  |  | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Define solution target architecture | Elaboration | L3 | CP | 50% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) | 2026-02-05 | 2026-06-15 | 54 |  | Elaboration in progress | Elaboration Done | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Define solution target architecture | Implementation LIS | L3 | CP | 0% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) |  |  |  |  | Delayed | Implementation LIS | Build IT Service |  | Design IT service
Automatisch geplant | Architecture management | Define solution target architecture | Implementation COT | L3 | CP | 0% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) |  |  |  |  | Delayed | Implementation COT Done | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Define solution target architecture | Implementation LUS | L3 | CP | 0% | Hoermann Patrick (LLI) | Hammer Marco (AER) | Nussbaumer Florian (LBC) |  |  |  |  | Delayed | Implementation LUS Done | Build IT Service |  | Design IT service
Automatisch geplant | Architecture management | Perform software selection | Total | L3 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2026-04-30 | 152 | 2025-10-14 |  |  | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Perform software selection | Elaboration | L3 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 60 |  | Elaboration Done | Elaboration Done | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Perform software selection | Implementation LIS | L3 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2026-02-16 | 2026-04-30 | 54 |  | Delayed | Implementation LIS | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Perform software selection | Implementation COT | L3 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Implementation COT Done | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Perform software selection | Implementation LUS | L3 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Design IT service
Manuell geplant | Architecture management | Record and plan functional requirements | Total | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Record and plan functional requirements | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 1 |  | Elaboration Done | Elaboration Done | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Record and plan functional requirements | Implementation LIS | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2026-02-16 | 2026-04-30 | 0 |  |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Record and plan functional requirements | Implementation COT | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Record and plan functional requirements | Implementation LUS | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Conduct market analysis and compile long or short list | Total | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Conduct market analysis and compile long or short list | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 1 |  | Elaboration Done | Elaboration Done | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Conduct market analysis and compile long or short list | Implementation LIS | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2026-02-16 | 2026-04-30 | 0 |  |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Conduct market analysis and compile long or short list | Implementation COT | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Conduct market analysis and compile long or short list | Implementation LUS | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Perform vendor use case pitch and usability test | Total | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Perform vendor use case pitch and usability test | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 1 |  | Elaboration Done | Elaboration Done | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Perform vendor use case pitch and usability test | Implementation LIS | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2026-02-16 | 2026-04-30 | 0 |  |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Perform vendor use case pitch and usability test | Implementation COT | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Perform vendor use case pitch and usability test | Implementation LUS | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Validate strategic fit | Total | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-02 | 2 | 2025-10-14 |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Validate strategic fit | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 1 |  | Elaboration Done | Elaboration Done | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Validate strategic fit | Implementation LIS | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2026-02-16 | 2026-04-30 | 0 |  |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Validate strategic fit | Implementation COT | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Validate strategic fit | Implementation LUS | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Recommendation and EA approval | Total | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-10-01 | 1 | 2025-10-14 |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Recommendation and EA approval | Elaboration | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2025-10-01 | 2025-12-23 | 1 |  | Elaboration Done | Elaboration Done | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Recommendation and EA approval | Implementation LIS | L4 | CP | 100% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | 2026-02-16 | 2026-04-30 | 0 |  |  |  | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Recommendation and EA approval | Implementation COT | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Manuell geplant | Architecture management | Recommendation and EA approval | Implementation LUS | L4 | CP | 0% | Hoermann Patrick (LLI) | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | [6 empty] | Build IT Service |  | Perform software selection
Automatisch geplant | ITSM | Develop and customise IT service | Total | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Develop and customise IT service | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-05-04 | 2026-07-31 | 65 |  | Elaboration in progress | Elaboration done | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Develop and customise IT service | Implementation LIS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Develop and customise IT service | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Develop and customise IT service | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Automatisch geplant | ITSM | Deploy IT service | Total | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Deploy IT service | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-05-04 | 2026-07-31 | 44 |  | Elaboration in progress | Elaboration done | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Deploy IT service | Implementation LIS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Deploy IT service | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Deploy IT service | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Automatisch geplant | ITSM | Test and validate IT service | Total | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Test and validate IT service | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-05-04 | 2026-07-31 | 44 |  | Elaboration in progress | Elaboration done | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Test and validate IT service | Implementation LIS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Test and validate IT service | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Test and validate IT service | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Evaluate success of IT service rollout | Total | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Evaluate success of IT service rollout | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | 2026-05-04 | 2026-07-31 | 0 |  | Elaboration in progress | Elaboration done | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Evaluate success of IT service rollout | Implementation LIS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Evaluate success of IT service rollout | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Manuell geplant | ITSM | Evaluate success of IT service rollout | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH) | Dalek Martin (LIS) | Wiehe Alexander (COB) | [6 empty] | Build IT Service | not planned yet | Build IT Service
Automatisch geplant | ITSM | Manage IT service change | Total | L2 | CP | 100% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 2026-01-12 | 2026-06-30 | 122 | 2026-04-15 |  |  | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Manag IT service change | Elaboration | L2 | CP | 75% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) | 2026-01-12 | 2026-03-18 | 48 |  | Elaboration Done | Elaboration Done | Build IT Service | Presented in IT Process Committee - still open points and not approved yet | Build IT Service
Manuell geplant | ITSM | Manag IT service change | Implementation LIS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) |  |  |  |  | not planned yet |  | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Manag IT service change | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) |  |  |  |  | not planned yet |  | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Manag IT service change | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Sint Rachel (LBH) | Wiehe Alexander (COB) |  |  |  |  | not planned yet |  | Build IT Service |  | Build IT Service
Automatisch geplant | ITSM | Manage IT service release | Total | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Hoeller Martin (LBH) | Wiehe Alexander (COB) | 2026-02-20 | 2026-06-30 | 93 |  |  |  | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Manage IT service release | Elaboration | L2 | CP | 50% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Hoeller Martin (LBH) | Wiehe Alexander (COB) | 2026-02-20 | 2026-05-08 | 56 |  | Elaboration in progress | Elaboration in progress | Build IT Service | In review cycle | Build IT Service
Manuell geplant | ITSM | Manage IT service release | Implementation LIS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Hoeller Martin (LBH) | Wiehe Alexander (COB) |  |  |  |  | not planned yet |  | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Manage IT service release | Implementation COT | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Hoeller Martin (LBH) | Wiehe Alexander (COB) |  |  |  |  | not planned yet |  | Build IT Service |  | Build IT Service
Manuell geplant | ITSM | Manage IT service release | Implementation LUS | L2 | CP | 0% | Kunz Christina (LIS-MHP Management- und IT Beratung GmbH);Frank Maren (LIS) | Hoeller Martin (LBH) | Wiehe Alexander (COB) |  |  |  |  | not planned yet |  | Build IT Service |  | Build IT Service
Automatisch geplant | ITSM | Deliver IT service | Total | L1 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 |  |  |  | Deliver IT service
Manuell geplant | ITSM | Deliver IT service | Elaboration | L1 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service
Manuell geplant | ITSM | Deliver IT service | Implementation LIS | L1 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service
Manuell geplant | ITSM | Deliver IT service | Implementation COT | L1 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service
Manuell geplant | ITSM | Deliver IT service | Implementation LUS | L1 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service
Automatisch geplant | ITSM | Manage IT service provision request | Total | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 |  |  |  | Deliver IT service |  | Deliver IT service
Manuell geplant | ITSM | Manage IT service provision request | Elaboration | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 |  | Delayed | Elaboration in progress | Deliver IT service | Resonsible unklar; Verwechslung Deliver und Run Prozesse | Deliver IT service
Manuell geplant | ITSM | Manage IT service provision request | Implementation LIS | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-15 | 54 |  | Delayed | Implementation LIS | Deliver IT service |  | Deliver IT service
Manuell geplant | ITSM | Manage IT service provision request | Implementation COT | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service |  | Deliver IT service
Manuell geplant | ITSM | Manage IT service provision request | Implementation LUS | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service |  | Deliver IT service
Automatisch geplant | ITSM | Handle IT service order | Total | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 |  |  |  | Deliver IT service |  | Deliver IT service
Manuell geplant | ITSM | Handle IT service order | Elaboration | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-17 | 56 |  | Delayed | Elaboration in progress | Deliver IT service | Responsible unklar; Verwechslung Deliver und Run Prozesse | Deliver IT service
Manuell geplant | ITSM | Handle IT service order | Implementation LIS | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | 2026-04-01 | 2026-06-15 | 54 |  | Delayed | Implementation LIS | Deliver IT service |  | Deliver IT service
Manuell geplant | ITSM | Handle IT service order | Implementation COT | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service |  | Deliver IT service
Manuell geplant | ITSM | Handle IT service order | Implementation LUS | L2 | CP | 0% | tbd | ? | Schnurrenberger Christoph (LIS-LIN) | [6 empty] | Deliver IT service |  | Deliver IT service
Automatisch geplant | ITSM | Run IT service | Total | L1 | CP | 17% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | Oey Kai (LIS)? | Sint Rachel (LBH) | 2025-10-15 | 2026-09-25 | 248 |  |  |  | Run IT service
Manuell geplant | ITSM | Run IT service | Elaboration | L1 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | Oey Kai (LIS)? | Sint Rachel (LBH) | 2025-10-16 | 2026-06-30 | 184 |  | Delayed | Elaboration in progress | Run IT service
Manuell geplant | ITSM | Run IT service | Implementation LIS | L1 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | Oey Kai (LIS)? | Sint Rachel (LBH) | [6 empty] | Run IT service
Manuell geplant | ITSM | Run IT service | Implementation COT | L1 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | Oey Kai (LIS)? | Sint Rachel (LBH) | [6 empty] | Run IT service
Manuell geplant | ITSM | Run IT service | Implementation LUS | L1 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | Oey Kai (LIS)? | Sint Rachel (LBH) | [6 empty] | Run IT service
Manuell geplant | ITSM | Ensure IT service continuity | Total | L2 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Ensure IT service continuity | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Ensure IT service continuity | Implementation LIS | L2 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Ensure IT service continuity | Implementation COT | L2 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Ensure IT service continuity | Implementation LUS | L2 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Manage IT service capacity | Total | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Manage IT service capacity | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Manage IT service capacity | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Manage IT service capacity | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Manage IT service capacity | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Review and maintain IT service continuity plan | Total | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Review and maintain IT service continuity plan | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Review and maintain IT service continuity plan | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Review and maintain IT service continuity plan | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Review and maintain IT service continuity plan | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS);Boehme Matthias (LIS-BPMO) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Ensure IT service continuity
Manuell geplant | ITSM | Monitor and report IT service performance | Total | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-04-15 | [5 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Montior and report IT service performance | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service | approximate date | Run IT service
Manuell geplant | ITSM | Montior and report IT service performance | Implementation LIS | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service | approximate date | Run IT service
Manuell geplant | ITSM | Montior and report IT service performance | Implementation COT | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Montior and report IT service performance | Implementation LUS | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Monitor and report IT service level | Total | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-04-15 | 2026-07-31 | 0 |  |  |  | Run IT service | Norbert Schwarz (MHP) wird für Philipp Kürschner den Prozess mit erarbeiten; Philipp ist weiterhin PO | Monitor and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service level | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service level | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service level | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service level | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service financials | Total | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Monitor and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service financials | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service financials | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service financials | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and report IT service financials | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and analyse events | Total | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Monitor and report IT service performance
Manuell geplant | ITSM | Monitor and analyse events | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and analyse events | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and analyse events | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor and analyse events | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor IT service risk and compliance | Total | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Monitor and report IT service performance
Manuell geplant | ITSM | Monitor IT service risk and compliance | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service | Responsible from Matthias Held adjusted to Philipp Kürschner in the joint conversation | Montior and report IT service performance
Manuell geplant | ITSM | Monitor IT service risk and compliance | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor IT service risk and compliance | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor IT service risk and compliance | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor user experience | Total | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Monitor and report IT service performance
Manuell geplant | ITSM | Monitor user experience | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service | Responsible from Matthias Held adjusted to Philipp Kürschner in the joint conversation | Montior and report IT service performance
Manuell geplant | ITSM | Monitor user experience | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor user experience | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Manuell geplant | ITSM | Monitor user experience | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Montior and report IT service performance
Automatisch geplant | ITSM | Operate and maintain IT service | Total | L2 | CP | 21% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2025-10-15 | 2026-06-30 | 185 |  |  |  | Run IT service |  | Run IT service
Manuell geplant | ITSM | Operate and maintain IT service | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-12 | 2026-06-30 | 122 |  | Delayed | Elaboration in progress | Run IT service | approximate date | Run IT service
Manuell geplant | ITSM | Operate and maintain IT service | Implementation LIS | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 |  | Delayed | Implementation LIS | Run IT service | approximate date | Run IT service
Manuell geplant | ITSM | Operate and maintain IT service | Implementation COT | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Operate and maintain IT service | Implementation LUS | L2 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Automatisch geplant | ITSM | Maintain CMDB | Total | L3 | CP | 50% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-14 | 2026-06-16 | 91 |  |  |  | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain CMDB | Elaboration | L3 | CP | 50% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | 2026-01-14 | 2026-06-16 | 91 |  | Elaboration in progress | Elaboration in progress | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain CMDB | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain CMDB | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain CMDB | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain IT asset database | Total | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain IT asset database | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain IT asset database | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain IT asset database | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain IT asset database | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain standard change catalogue for IT service | Total | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain standard change catalogue for IT service | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain standard change catalogue for IT service | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain standard change catalogue for IT service | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Manuell geplant | ITSM | Maintain standard change catalogue for IT service | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Operate and maintain IT service
Automatisch geplant | ITSM | Provide IT service support | Total | L2 | CP | 57% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2025-10-16 | 2026-06-15 | 173 |  |  |  | Run IT service |  | Run IT service
Manuell geplant | ITSM | Provide IT service support | Elaboration | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-12 | 2026-03-30 | 56 |  | Delayed | Elaboration Done | Run IT service |  | Run IT service
Manuell geplant | ITSM | Provide IT service support | Implementation LIS | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-04-01 | 2026-06-15 | 54 |  | Delayed | Implementation LIS | Run IT service |  | Run IT service
Manuell geplant | ITSM | Provide IT service support | Implementation COT | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Manuell geplant | ITSM | Provide IT service support | Implementation LUS | L2 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Run IT service
Automatisch geplant | ITSM | Handle IT Incident | Total | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 |  |  | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Handle IT Incident | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 | Elaboration in progress | Elaboration Done | Run IT service | Ansprechpartner Anna Rantou | Provide IT service support
Manuell geplant | ITSM | Handle IT Incident | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Handle IT Incident | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Handle IT Incident | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Automatisch geplant | ITSM | Handle IT problem | Total | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 |  |  | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Handle IT problem | Elaboration | L3 | CP | 75% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-13 | 2026-03-19 | 48 | 2026-03-19 | Elaboration in progress | Elaboration Done | Run IT service | Ansprechpartner Anna Rantou | Provide IT service support
Manuell geplant | ITSM | Handle IT problem | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Handle IT problem | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Handle IT problem | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Automatisch geplant | ITSM | Handle IT service request | Total | L3 | CP | 100% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Handle IT service request | Elaboration | L3 | CP | 100% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-02-02 | 2026-03-19 | 34 | 2026-03-19 | Elaboration Done | Elaboration Done | Run IT service | Ansprechpartner Eloise | Provide IT service support
Manuell geplant | ITSM | Handle IT service request | Implementation LIS | L3 | CP | 0% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service | Mit Go Life Service Now | Provide IT service support
Manuell geplant | ITSM | Handle IT service request | Implementation COT | L3 | CP | 0% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service | Mit Go Life Service Now | Provide IT service support
Manuell geplant | ITSM | Handle IT service request | Implementation LUS | L3 | CP | 0% | Frank Maren (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Run IT service | Mit Go Life Service Now | Provide IT service support
Manuell geplant | ITSM | Manage IT service desk | Total | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Manage IT service desk | Elaboration | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service | Sönke Nissen war zuvor eingetragen. Philipp Kürschner sieht sich als verantwortlich. | Provide IT service support
Manuell geplant | ITSM | Manage IT service desk | Implementation LIS | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Manage IT service desk | Implementation COT | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Manuell geplant | ITSM | Manage IT service desk | Implementation LUS | L3 | CP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Run IT service |  | Provide IT service support
Automatisch geplant |  | Support processes |  | L1 | SP | 20% |  |  |  | 2025-07-14 | 2027-06-30 |  |  |  |  | Support processes
Automatisch geplant | Information security | Ensure Information security | Total | L1 | SP | 50% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | 2025-10-16 | 2025-10-16 | 1 |  |  |  | Ensure Information security
Manuell geplant | Information security | Ensure Information security | Elaboration | L1 | SP | 50% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | 2025-10-16 | [5 empty] | Ensure Information security
Manuell geplant | Information security | Ensure Information security | Implementation LIS | L1 | SP | 0% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | [6 empty] | Ensure Information security
Manuell geplant | Information security | Ensure Information security | Implementation COT | L1 | SP | 0% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | [6 empty] | Ensure Information security
Manuell geplant | Information security | Ensure Information security | Implementation LUS | L1 | SP | 0% | Rollinger Alexander (LIS) | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | [6 empty] | Ensure Information security
Manuell geplant | Information security | Perform SaaS Security Assessment | Total | L2 | SP | 50% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Ensure Information security |  | Ensure Information security
Manuell geplant | Information security | Perform SaaS Security Assessment | Elaboration | L2 | SP | 50% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | 2025-10-19 | 2025-11-30 | 139 |  | Elaboration in progress | Elaboration in progress | Ensure Information security |  | Ensure Information security
Manuell geplant | Information security | Perform SaaS Security Assessment | Implementation LIS | L2 | SP | 0% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Ensure Information security |  | Ensure Information security
Manuell geplant | Information security | Perform SaaS Security Assessment | Implementation COT | L2 | SP | 0% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Ensure Information security |  | Ensure Information security
Manuell geplant | Information security | Perform SaaS Security Assessment | Implementation LUS | L2 | SP | 0% | Hoermann Patrick (LLI);Rollinger Alexander (LIS) | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | [6 empty] | Ensure Information security |  | Ensure Information security
Automatisch geplant | IT project management | Manage IT project | Total | L1 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-12-10 | 108 | 2025-09-18 |  |  | Manage IT project
Manuell geplant | IT project management | Manage IT project | Elaboration | L1 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project
Manuell geplant | IT project management | Manage IT project | Implementation LIS | L1 | SP | 50% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation)
Manuell geplant | IT project management | Manage IT project | Implementation COT | L1 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation)
Manuell geplant | IT project management | Manage IT project | Implementation LUS | L1 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation)
Manuell geplant | IT project management | Initiate IT project | Total | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Initiate IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Initiate IT project | Implementation LIS | L2 | SP | 50% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Initiate IT project | Implementation COT | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Initiate IT project | Implementation LUS | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Plan IT project | Total | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Plan IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Plan IT project | Implementation LIS | L2 | SP | 50% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Plan IT project | Implementation COT | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Plan IT project | Implementation LUS | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Steer and execute IT project | Total | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Steer and execute IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Steer and execute IT project | Implementation LIS | L2 | SP | 50% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Steer and execute IT project | Implementation COT | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Steer and execute IT project | Implementation LUS | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Close IT project | Total | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Close IT project | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Close IT project | Implementation LIS | L2 | SP | 50% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Close IT project | Implementation COT | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Close IT project | Implementation LUS | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Manage IT project change request | Total | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-07-14 | 1 | 2025-09-18 |  |  | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Manage IT project change request | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Manage IT project change request | Implementation LIS | L2 | SP | 50% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Manage IT project change request | Implementation COT | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Manage IT project change request | Implementation LUS | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Assign personnel resources to IT project | Total | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-07-14 | 2025-07-14 | 1 |  |  |  | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Ressourcemanagement for IT projects | Elaboration | L2 | SP | 100% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | 2025-11-11 | 2025-12-10 | 22 | 2026-01-28 | Elaboration Done | Elaboration Done | Manage IT project |  | Manage IT project
Manuell geplant | IT project management | Ressourcemanagement for IT projects | Implementation LIS | L2 | SP | 50% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Ressourcemanagement for IT projects | Implementation COT | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Manuell geplant | IT project management | Ressourcemanagement for IT projects | Implementation LUS | L2 | SP | 0% | Frank Maren (LIS) | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | [6 empty] | Manage IT project | Trainings ongoing (with cPlace implementation) | Manage IT project
Automatisch geplant | ITSM | Manage IT sourcing and procurement | Total | L1 | SP | 25% | Schoeberl Lorena (LBH) | Dolderer Wolfgang (LIS) | Monnier Murielle (LEC) | 2026-04-20 | 2026-07-08 | 118 |  |  |  | Manage IT sourcing and procurement
Manuell geplant | ITSM | Manage IT sourcing and procurement | Elaboration | L1 | SP | 25% | Schoeberl Lorena (LBH) | Dolderer Wolfgang (LIS) | Monnier Murielle (LEC) | 2026-04-20 | 2026-04-22 | 52 |  | Elaboration in progress | Elaboration Done | Manage IT sourcing and procurement | approximate date
Manuell geplant | ITSM | Manage IT sourcing and procurement | Implementation LIS | L1 | SP | 50% | Schoeberl Lorena (LBH) | Dolderer Wolfgang (LIS) | Monnier Murielle (LEC) | [6 empty] | Manage IT sourcing and procurement | approximate date
Manuell geplant | ITSM | Manage IT sourcing and procurement | Implementation COT | L1 | SP | 0% | Schoeberl Lorena (LBH) | Dolderer Wolfgang (LIS) | Monnier Murielle (LEC) | [6 empty] | Manage IT sourcing and procurement
Manuell geplant | ITSM | Manage IT sourcing and procurement | Implementation LUS | L1 | SP | 0% | Schoeberl Lorena (LBH) | Dolderer Wolfgang (LIS) | Monnier Murielle (LEC) | [6 empty] | Manage IT sourcing and procurement
Automatisch geplant | HR initiatives for IT | Provide and develop IT workforce | Total | L1 | SP | 15% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2027-06-30 | 456 |  |  |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Provide and develop IT workforce | Elaboration | L1 | SP | 100% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Elaboration Done | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Provide and develop IT workforce | Implementation LIS | L1 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Provide and develop IT workforce | Implementation COT | L1 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Provide and develop IT workforce | Implementation LUS | L1 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce
Automatisch geplant | HR initiatives for IT | Manage HR4IT strategy, governane and framework | Total | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2026-12-31 |  |  |  |  | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Manage HR4IT strategy, governane and framework | Elaboration | L2 | SP | 100% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2025-10-01 | 1 |  | Elaboration Done | Elaboration Done | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LIS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation COT | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Manage HR4IT strategy, governane and framework | Implementation LUS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Automatisch geplant | HR initiatives for IT | Plan IT workforce | Total | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2026-12-31 | 316 |  |  |  | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Plan IT workforce | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2025-12-31 | 55 |  | Delayed | Elaboration Done | Provide and develop IT workforce | will be defined in CF-B (HR) | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Plan IT workforce | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2026-01-01 | 2026-12-31 | 261 |  | Delayed | Implementation LIS | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Plan IT workforce | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Plan IT workforce | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Automatisch geplant | HR initiatives for IT | Implement and maintain IT job architecture | Total | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2026-05-31 | 162 |  |  |  | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Implement and maintain IT job architecture | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-16 | 2026-05-31 | 162 |  | Delayed | Elaboration in progress | Provide and develop IT workforce | will be defined in CF-B (HR) | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Implement and maintain IT job architecture | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Implement and maintain IT job architecture | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Implement and maintain IT job architecture | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | [6 empty] | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Automatisch geplant | HR initiatives for IT | Manage HR4IT service demand |  | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2026-06-30 | 195 |  |  |  | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Manage HR4IT service demand | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2025-10-01 | 2026-05-31 | 173 |  | Delayed | Elaboration in progress | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Manage HR4IT service demand | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2026-06-01 | 2026-06-30 | 22 |  |  | Scheduled | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Manage HR4IT service demand | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2026-06-01 | 2026-06-30 | 22 |  |  | Scheduled | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Manuell geplant | HR initiatives for IT | Manage HR4IT service demand | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | 2026-06-01 | 2026-06-30 | 22 |  |  | Scheduled | Provide and develop IT workforce |  | Manage HR4IT strategy, governane and framework
Automatisch geplant | HR initiatives for IT | Attract and hire employees | Total | L2 | SP | 18% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-12-31 | 327 |  |  |  | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Attract and hire employees | Elaboration | L2 | SP | 50% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2026-01-07 | 2026-03-16 | 49 |  | Elaboration in progress | Elaboration Done | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Attract and hire employees | Implementation LIS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-06-15 | 54 |  | Delayed | Implementation LIS | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Attract and hire employees | Implementation COT | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-06-15 | 54 |  | Delayed | Implementation COT | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Attract and hire employees | Implementation LUS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Automatisch geplant | HR initiatives for IT | Perform active sourcing |  | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-12-31 | 327 |  |  |  | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Perform active sourcing | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-04-30 | 152 |  | Delayed | Elaboration in progress | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Perform active sourcing | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2026-03-01 | 2026-12-31 | 219 |  | Delayed | Implementation LIS | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Perform active sourcing | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Perform active sourcing | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Attract and hire employees
Automatisch geplant | HR initiatives for IT | Recruit employees and managers |  | L3 | SP | 25% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-12-31 | 327 |  |  |  | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Recruit employees and managers | Elaboration | L3 | SP | 25% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-04-30 | 152 |  | Elaboration in progress | Elaboration in progress | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Recruit employees and managers | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | 2026-03-01 | 2026-12-31 | 219 |  | Delayed | Implementation LIS | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Recruit employees and managers | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Attract and hire employees
Manuell geplant | HR initiatives for IT | Recruit employees and managers | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Attract and hire employees
Automatisch geplant | HR initiatives for IT | Perform onboarding | Total | L2 | SP | 33% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  |  |  | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform onboarding | Elaboration | L2 | SP | 25% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  | Elaboration in progress | Elaboration in progress | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform onboarding | Implementation LIS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform onboarding | Implementation COT | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform onboarding | Implementation LUS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Automatisch geplant | HR initiatives for IT | Pre-board new IT employee and manager | Total | L3 | SP | 25% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  |  |  | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Pre-board new IT employee and manager | Elaboration | L3 | SP | 25% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  | Elaboration in progress | Elaboration in progress | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Pre-board new IT employee and manager | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Pre-board new IT employee and manager | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Pre-board new IT employee and manager | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform onboarding
Automatisch geplant | HR initiatives for IT | Onboard new IT employee and manager | Total | L3 | SP | 50% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  |  |  | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Onboard new IT employee and manager | Elaboration | L3 | SP | 50% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | 2025-10-16 | 2026-04-30 | 141 |  | Elaboration in progress | Elaboration in progress | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Onboard new IT employee and manager | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Onboard new IT employee and manager | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform onboarding
Manuell geplant | HR initiatives for IT | Onboard new IT employee and manager | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) |  | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform onboarding
Automatisch geplant | HR initiatives for IT | Perform, learn and grow | Total | L2 | SP | 11% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2027-06-30 | 456 |  |  |  | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform, learn and grow | Elaboration | L2 | SP | 25% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | [5 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform, learn and grow | Implementation LIS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform, learn and grow | Implementation COT | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Manuell geplant | HR initiatives for IT | Perform, learn and grow | Implementation LUS | L2 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Provide and develop IT workforce
Automatisch geplant | HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue |  | L3 | SP | 50% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-04-30 | 152 |  |  |  | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Elaboration | L3 | SP | 50% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-01 | 2026-04-30 | 152 |  | Elaboration in progress | Elaboration in progress | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Automatisch geplant | HR initiatives for IT | Mapping and evaluate IT career level | Total | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2027-01-01 | 198 |  |  |  | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Mapping and evaluate IT career level | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2027-01-01 | 198 |  | Delayed | Elaboration in progress | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Mapping and evaluate IT career level | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Mapping and evaluate IT career level | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Mapping and evaluate IT career level | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Automatisch geplant | HR initiatives for IT | Manage IT development programme | Total | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-16 | 2025-10-16 | 0 |  |  |  | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT development programme | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT development programme | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT development programme | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT development programme | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Automatisch geplant | HR initiatives for IT | Manage IT skills | Total | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-01 | 2027-06-30 | 390 |  |  |  | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT skills | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-01 | 2026-12-31 | 261 |  | Delayed | Elaboration in progress | Provide and develop IT workforce | will be defined in CF-B (HR) | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT skills | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2027-01-01 | 2027-06-30 | 129 |  |  | Scheduled | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT skills | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2027-01-01 | 2027-06-30 | 129 |  |  | Scheduled | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT skills | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2027-01-01 | 2027-06-30 | 129 |  |  | Scheduled | Provide and develop IT workforce |  | Perform, learn and grow
Automatisch geplant | HR initiatives for IT | Manage IT talent pool and identify potential | Total | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2025-10-16 | 2025-10-16 | 0 |  |  |  | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce | will be defined in CF-B (HR) | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | [6 empty] | Provide and develop IT workforce |  | Perform, learn and grow
Automatisch geplant | HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Total | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-07-01 | 120 |  |  |  | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Elaboration | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-01-15 | 2026-03-31 | 54 |  | Delayed | Elaboration Done | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LIS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-07-01 | 66 |  | Delayed | Implementation LIS | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation COT | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-07-01 | 66 |  | Delayed | Implementation COT | Provide and develop IT workforce |  | Perform, learn and grow
Manuell geplant | HR initiatives for IT | Manage IT global orientation programme incl. job shadowing | Implementation LUS | L3 | SP | 0% | Chen Leilei (LIS-BPMO);Hynek Tobias (LIS) | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | 2026-04-01 | 2026-07-01 | 66 |  | Delayed | Implementation LUS | Provide and develop IT workforce |  | Perform, learn and grow
Automatisch geplant | ITSM | Ensure performance and conformance of IT services | Total | L1 | SP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Ensure performance and conformance of IT services
Manuell geplant | ITSM | Ensure performance and conformance of IT services | Elaboration | L1 | SP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) |  |  |  |  | Delayed | Elaboration in progress | Ensure performance and conformance of IT services | approximate date
Manuell geplant | ITSM | Ensure performance and conformance of IT services | Implementation LIS | L1 | SP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Ensure performance and conformance of IT services | approximate date
Manuell geplant | ITSM | Ensure performance and conformance of IT services | Implementation COT | L1 | SP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Ensure performance and conformance of IT services
Manuell geplant | ITSM | Ensure performance and conformance of IT services | Implementation LUS | L1 | SP | 0% | Schroeder Michael (LIS) | ? | Sint Rachel (LBH) | [6 empty] | Ensure performance and conformance of IT services
Automatisch geplant | ITSM | Manage IT knowledge | Total | L1 | SP | 100% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-20 | 2026-06-30 | 116 | 2026-03-19 |  |  | Manage IT knowledge
Manuell geplant | ITSM | Manage IT knowledge | Elaboration | L1 | SP | 100% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-01-20 | 2026-02-25 | 27 |  | Elaboration Done | Elaboration Done | Manage IT knowledge | Ansprechpartner Anna Rantou
Manuell geplant | ITSM | Manage IT knowledge | Implementation LIS | L1 | SP | 25% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | 2026-04-15 | 2026-06-30 | 55 |  | Delayed | Implementation LIS | Manage IT knowledge
Manuell geplant | ITSM | Manage IT knowledge | Implementation COT | L1 | SP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Manage IT knowledge
Manuell geplant | ITSM | Manage IT knowledge | Implementation LUS | L1 | SP | 0% | Schroeder Michael (LIS) | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | [6 empty] | Manage IT knowledge
Automatisch geplant | ITSM | Leverage IT innovation | Total | L1 | SP | 25% | Chen Leilei (LIS-BPMO) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | 2026-05-01 | 2026-10-31 | 55 |  |  |  | Leverage IT innovation
Manuell geplant | ITSM | Leverage IT innovation | Elaboration | L1 | SP | 25% | Chen Leilei (LIS-BPMO) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | 2026-05-01 | 2026-10-31 | 0 |  |  |  | Leverage IT innovation | approximate date
Manuell geplant | ITSM | Leverage IT innovation | Implementation LIS | L1 | SP | 0% | Chen Leilei (LIS-BPMO) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | [6 empty] | Leverage IT innovation
Manuell geplant | ITSM | Leverage IT innovation | Implementation COT | L1 | SP | 0% | Chen Leilei (LIS-BPMO) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | [6 empty] | Leverage IT innovation
Manuell geplant | ITSM | Leverage IT innovation | Implementation LUS | L1 | SP | 0% | Chen Leilei (LIS-BPMO) | Abbondio Viviana (LIS) | Sint Rachel (LBH) | [6 empty] | Leverage IT innovation
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: keine % Werte mehr, sondern Status aus Initiative Record: 25%: Erster Termin oder Kickoff wurde durchgeführt, Lead-Verantwortung ist geklärt 50%: Elaboration ist im Gange 75%: Prozess wurde beim IT Process Committee zur Freigabe eingereicht 100%: IT Process Committee hat den Prozess freigegeben
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: spalte kann vermutlich raus
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: für dashboard nicht mehr relevant

## calc Draft-april26 (hidden)
Datum | Elaboration | Implementation LIS | Implementation LUS | Implementation COT
2025-08-01 | 0 | 0 | 0 | 0
2025-08-02 | 1 | 0 | 0 | 0
2025-08-03 | 1 | 0 | 0 | 0
2025-08-04 | 1 | 0 | 0 | 0
2025-08-05 | 2 | 0 | 0 | 0
2025-08-06 | 2 | 0 | 0 | 0
2025-08-07 | 2 | 0 | 0 | 0
2025-08-08 | 2 | 0 | 0 | 0
2025-08-09 | 2 | 0 | 0 | 0
2025-08-10 | 2 | 0 | 0 | 0
2025-08-11 | 2 | 0 | 0 | 0
2025-08-12 | 2 | 0 | 0 | 0
2025-08-13 | 2 | 0 | 0 | 0
2025-08-14 | 2 | 0 | 0 | 0
2025-08-15 | 2 | 0 | 0 | 0
2025-08-16 | 2 | 0 | 0 | 0
2025-08-17 | 2 | 0 | 0 | 0
2025-08-18 | 2 | 0 | 0 | 0
2025-08-19 | 2 | 0 | 0 | 0
2025-08-20 | 2 | 0 | 0 | 0
2025-08-21 | 2 | 0 | 0 | 0
2025-08-22 | 2 | 0 | 0 | 0
2025-08-23 | 2 | 0 | 0 | 0
2025-08-24 | 2 | 0 | 0 | 0
2025-08-25 | 2 | 0 | 0 | 0
2025-08-26 | 2 | 0 | 0 | 0
2025-08-27 | 2 | 0 | 0 | 0
2025-08-28 | 2 | 0 | 0 | 0
2025-08-29 | 2 | 0 | 0 | 0
2025-08-30 | 1 | 0 | 0 | 0
2025-08-31 | 1 | 0 | 0 | 0
2025-09-01 | 1 | 0 | 0 | 0
2025-09-02 | 1 | 0 | 0 | 0
2025-09-03 | 1 | 0 | 0 | 0
2025-09-04 | 1 | 0 | 0 | 0
2025-09-05 | 1 | 0 | 0 | 0
2025-09-06 | 1 | 0 | 0 | 0
2025-09-07 | 1 | 0 | 0 | 0
2025-09-08 | 1 | 0 | 0 | 0
2025-09-09 | 1 | 0 | 0 | 0
2025-09-10 | 1 | 0 | 0 | 0
2025-09-11 | 1 | 0 | 0 | 0
2025-09-12 | 1 | 0 | 0 | 0
2025-09-13 | 1 | 0 | 0 | 0
2025-09-14 | 1 | 0 | 0 | 0
2025-09-15 | 1 | 0 | 0 | 0
2025-09-16 | 1 | 0 | 0 | 0
2025-09-17 | 1 | 0 | 0 | 0
2025-09-18 | 1 | 0 | 0 | 0
2025-09-19 | 1 | 0 | 0 | 0
2025-09-20 | 1 | 0 | 0 | 0
2025-09-21 | 1 | 0 | 0 | 0
2025-09-22 | 1 | 0 | 0 | 0
2025-09-23 | 1 | 0 | 0 | 0
2025-09-24 | 1 | 0 | 0 | 0
2025-09-25 | 1 | 0 | 0 | 0
2025-09-26 | 1 | 0 | 0 | 0
2025-09-27 | 1 | 0 | 0 | 0
2025-09-28 | 1 | 0 | 0 | 0
2025-09-29 | 1 | 0 | 0 | 0
2025-09-30 | 1 | 0 | 0 | 0
2025-10-01 | 1 | 0 | 0 | 0
2025-10-02 | 19 | 0 | 0 | 0
2025-10-03 | 19 | 0 | 0 | 0
2025-10-04 | 19 | 0 | 0 | 0
2025-10-05 | 19 | 0 | 0 | 0
2025-10-06 | 19 | 0 | 0 | 0
2025-10-07 | 19 | 0 | 0 | 0
2025-10-08 | 19 | 0 | 0 | 0
2025-10-09 | 19 | 0 | 0 | 0
2025-10-10 | 19 | 0 | 0 | 0
2025-10-11 | 19 | 0 | 0 | 0
2025-10-12 | 19 | 0 | 0 | 0
2025-10-13 | 19 | 0 | 0 | 0
2025-10-14 | 19 | 0 | 0 | 0
2025-10-15 | 18 | 0 | 0 | 0
2025-10-16 | 19 | 0 | 0 | 0
2025-10-17 | 26 | 0 | 0 | 2
2025-10-18 | 26 | 0 | 0 | 2
2025-10-19 | 26 | 0 | 0 | 2
2025-10-20 | 27 | 0 | 0 | 2
2025-10-21 | 27 | 0 | 0 | 2
2025-10-22 | 27 | 0 | 0 | 2
2025-10-23 | 27 | 0 | 0 | 2
2025-10-24 | 27 | 0 | 0 | 2
2025-10-25 | 27 | 0 | 0 | 2
2025-10-26 | 27 | 0 | 0 | 2
2025-10-27 | 27 | 0 | 0 | 2
2025-10-28 | 27 | 0 | 0 | 2
2025-10-29 | 27 | 0 | 0 | 2
2025-10-30 | 27 | 0 | 0 | 2
2025-10-31 | 26 | 0 | 0 | 2
2025-11-01 | 26 | 0 | 0 | 2
2025-11-02 | 26 | 4 | 0 | 2
2025-11-03 | 26 | 4 | 0 | 2
2025-11-04 | 26 | 4 | 0 | 6
2025-11-05 | 26 | 4 | 0 | 6
2025-11-06 | 26 | 4 | 0 | 6
2025-11-07 | 26 | 4 | 0 | 6
2025-11-08 | 26 | 4 | 0 | 6
2025-11-09 | 26 | 4 | 0 | 6
2025-11-10 | 26 | 4 | 0 | 6
2025-11-11 | 27 | 4 | 0 | 6
2025-11-12 | 35 | 4 | 0 | 6
2025-11-13 | 35 | 4 | 0 | 6
2025-11-14 | 35 | 4 | 0 | 6
2025-11-15 | 35 | 4 | 0 | 6
2025-11-16 | 35 | 4 | 0 | 6
2025-11-17 | 35 | 4 | 0 | 6
2025-11-18 | 35 | 4 | 0 | 6
2025-11-19 | 35 | 4 | 0 | 6
2025-11-20 | 35 | 4 | 0 | 6
2025-11-21 | 35 | 4 | 0 | 6
2025-11-22 | 35 | 4 | 0 | 6
2025-11-23 | 35 | 4 | 0 | 6
2025-11-24 | 35 | 4 | 0 | 6
2025-11-25 | 35 | 4 | 0 | 6
2025-11-26 | 35 | 4 | 0 | 6
2025-11-27 | 35 | 4 | 0 | 6
2025-11-28 | 35 | 4 | 0 | 6
2025-11-29 | 35 | 4 | 0 | 6
2025-11-30 | 34 | 4 | 0 | 6
2025-12-01 | 34 | 4 | 0 | 6
2025-12-02 | 34 | 4 | 0 | 6
2025-12-03 | 34 | 4 | 0 | 6
2025-12-04 | 34 | 4 | 0 | 6
2025-12-05 | 34 | 4 | 0 | 6
2025-12-06 | 34 | 4 | 0 | 6
2025-12-07 | 34 | 4 | 0 | 6
2025-12-08 | 34 | 4 | 0 | 6
2025-12-09 | 34 | 4 | 0 | 6
2025-12-10 | 26 | 4 | 0 | 6
2025-12-11 | 26 | 4 | 0 | 6
2025-12-12 | 26 | 4 | 0 | 6
2025-12-13 | 26 | 4 | 0 | 6
2025-12-14 | 26 | 4 | 0 | 6
2025-12-15 | 26 | 4 | 0 | 6
2025-12-16 | 26 | 4 | 0 | 6
2025-12-17 | 26 | 4 | 0 | 6
2025-12-18 | 26 | 4 | 0 | 6
2025-12-19 | 26 | 4 | 0 | 6
2025-12-20 | 26 | 4 | 0 | 6
2025-12-21 | 26 | 4 | 0 | 6
2025-12-22 | 26 | 4 | 0 | 6
2025-12-23 | 20 | 4 | 0 | 6
2025-12-24 | 20 | 4 | 0 | 6
2025-12-25 | 20 | 4 | 0 | 6
2025-12-26 | 20 | 4 | 0 | 6
2025-12-27 | 20 | 4 | 0 | 6
2025-12-28 | 20 | 4 | 0 | 6
2025-12-29 | 20 | 4 | 0 | 6
2025-12-30 | 20 | 4 | 0 | 6
2025-12-31 | 19 | 4 | 0 | 5
2026-01-01 | 19 | 4 | 0 | 5
2026-01-02 | 20 | 5 | 0 | 5
2026-01-03 | 20 | 5 | 0 | 5
2026-01-04 | 20 | 5 | 0 | 5
2026-01-05 | 20 | 5 | 0 | 5
2026-01-06 | 20 | 5 | 0 | 5
2026-01-07 | 20 | 5 | 0 | 5
2026-01-08 | 21 | 6 | 0 | 5
2026-01-09 | 21 | 6 | 0 | 5
2026-01-10 | 21 | 6 | 0 | 5
2026-01-11 | 21 | 6 | 0 | 5
2026-01-12 | 21 | 6 | 0 | 5
2026-01-13 | 29 | 6 | 0 | 5
2026-01-14 | 31 | 6 | 0 | 5
2026-01-15 | 32 | 6 | 0 | 5
2026-01-16 | 33 | 6 | 0 | 5
2026-01-17 | 33 | 5 | 0 | 5
2026-01-18 | 33 | 5 | 0 | 5
2026-01-19 | 33 | 5 | 0 | 5
2026-01-20 | 33 | 5 | 0 | 5
2026-01-21 | 34 | 5 | 0 | 5
2026-01-22 | 34 | 5 | 0 | 5
2026-01-23 | 34 | 5 | 0 | 5
2026-01-24 | 34 | 5 | 0 | 5
2026-01-25 | 34 | 5 | 0 | 5
2026-01-26 | 34 | 5 | 0 | 5
2026-01-27 | 34 | 5 | 0 | 5
2026-01-28 | 34 | 5 | 0 | 5
2026-01-29 | 33 | 5 | 0 | 5
2026-01-30 | 32 | 5 | 0 | 5
2026-01-31 | 32 | 5 | 0 | 5
2026-02-01 | 32 | 5 | 0 | 5
2026-02-02 | 32 | 6 | 0 | 5
2026-02-03 | 34 | 6 | 0 | 5
2026-02-04 | 34 | 6 | 0 | 5
2026-02-05 | 34 | 6 | 0 | 5
2026-02-06 | 35 | 6 | 0 | 5
2026-02-07 | 35 | 6 | 0 | 5
2026-02-08 | 35 | 6 | 0 | 5
2026-02-09 | 35 | 6 | 0 | 5
2026-02-10 | 35 | 6 | 0 | 5
2026-02-11 | 35 | 6 | 0 | 5
2026-02-12 | 35 | 6 | 0 | 5
2026-02-13 | 35 | 6 | 0 | 5
2026-02-14 | 35 | 6 | 0 | 5
2026-02-15 | 35 | 6 | 0 | 5
2026-02-16 | 35 | 6 | 0 | 5
2026-02-17 | 35 | 12 | 0 | 5
2026-02-18 | 35 | 12 | 0 | 5
2026-02-19 | 35 | 12 | 0 | 5
2026-02-20 | 35 | 12 | 0 | 5
2026-02-21 | 36 | 12 | 0 | 5
2026-02-22 | 36 | 12 | 0 | 5
2026-02-23 | 36 | 12 | 0 | 5
2026-02-24 | 38 | 12 | 0 | 5
2026-02-25 | 37 | 12 | 0 | 5
2026-02-26 | 37 | 12 | 0 | 5
2026-02-27 | 37 | 12 | 0 | 5
2026-02-28 | 37 | 8 | 0 | 5
2026-03-01 | 37 | 8 | 0 | 5
2026-03-02 | 37 | 10 | 0 | 5
2026-03-03 | 37 | 10 | 0 | 5
2026-03-04 | 37 | 10 | 0 | 5
2026-03-05 | 37 | 10 | 0 | 5
2026-03-06 | 37 | 10 | 0 | 5
2026-03-07 | 37 | 10 | 0 | 5
2026-03-08 | 37 | 10 | 0 | 5
2026-03-09 | 37 | 10 | 0 | 5
2026-03-10 | 37 | 10 | 0 | 5
2026-03-11 | 37 | 10 | 0 | 5
2026-03-12 | 37 | 10 | 0 | 5
2026-03-13 | 37 | 10 | 0 | 5
2026-03-14 | 37 | 10 | 0 | 5
2026-03-15 | 37 | 10 | 0 | 5
2026-03-16 | 36 | 10 | 0 | 5
2026-03-17 | 37 | 10 | 0 | 5
2026-03-18 | 36 | 10 | 0 | 5
2026-03-19 | 33 | 10 | 0 | 5
2026-03-20 | 33 | 10 | 0 | 5
2026-03-21 | 33 | 10 | 0 | 5
2026-03-22 | 33 | 10 | 0 | 5
2026-03-23 | 33 | 10 | 0 | 5
2026-03-24 | 33 | 10 | 0 | 5
2026-03-25 | 33 | 10 | 0 | 5
2026-03-26 | 33 | 10 | 0 | 5
2026-03-27 | 33 | 10 | 0 | 5
2026-03-28 | 33 | 10 | 0 | 5
2026-03-29 | 33 | 10 | 0 | 5
2026-03-30 | 32 | 10 | 0 | 5
2026-03-31 | 31 | 10 | 0 | 1
2026-04-01 | 31 | 10 | 0 | 1
2026-04-02 | 36 | 15 | 1 | 3
2026-04-03 | 36 | 15 | 1 | 3
2026-04-04 | 36 | 15 | 1 | 3
2026-04-05 | 36 | 15 | 1 | 3
2026-04-06 | 36 | 15 | 1 | 3
2026-04-07 | 36 | 15 | 1 | 3
2026-04-08 | 36 | 15 | 1 | 3
2026-04-09 | 36 | 15 | 1 | 3
2026-04-10 | 36 | 15 | 1 | 3
2026-04-11 | 36 | 15 | 1 | 3
2026-04-12 | 36 | 15 | 1 | 3
2026-04-13 | 36 | 15 | 1 | 3
2026-04-14 | 36 | 15 | 1 | 3
2026-04-15 | 36 | 15 | 1 | 3
2026-04-16 | 36 | 17 | 1 | 3
2026-04-17 | 36 | 17 | 1 | 3
2026-04-18 | 36 | 17 | 1 | 3
2026-04-19 | 36 | 17 | 1 | 3
2026-04-20 | 36 | 17 | 1 | 3
2026-04-21 | 37 | 17 | 1 | 3
2026-04-22 | 36 | 17 | 1 | 3
2026-04-23 | 36 | 17 | 1 | 3
2026-04-24 | 36 | 17 | 1 | 3
2026-04-25 | 36 | 17 | 1 | 3
2026-04-26 | 36 | 17 | 1 | 3
2026-04-27 | 36 | 17 | 1 | 3
2026-04-28 | 36 | 17 | 1 | 3
2026-04-29 | 36 | 17 | 1 | 3
2026-04-30 | 27 | 11 | 1 | 2
2026-05-01 | 27 | 11 | 1 | 2
2026-05-02 | 28 | 12 | 1 | 2
2026-05-03 | 28 | 12 | 1 | 2
2026-05-04 | 28 | 12 | 1 | 2
2026-05-05 | 33 | 12 | 1 | 2
2026-05-06 | 33 | 12 | 1 | 2
2026-05-07 | 33 | 12 | 1 | 2
2026-05-08 | 31 | 12 | 1 | 2
2026-05-09 | 31 | 13 | 2 | 3
2026-05-10 | 31 | 13 | 2 | 3
2026-05-11 | 31 | 13 | 1 | 2
2026-05-12 | 31 | 13 | 1 | 2
2026-05-13 | 31 | 13 | 1 | 2
2026-05-14 | 31 | 13 | 1 | 2
2026-05-15 | 31 | 14 | 1 | 2
2026-05-16 | 31 | 14 | 1 | 2
2026-05-17 | 31 | 14 | 1 | 2
2026-05-18 | 31 | 14 | 1 | 2
2026-05-19 | 31 | 14 | 1 | 2
2026-05-20 | 31 | 14 | 1 | 2
2026-05-21 | 30 | 14 | 1 | 2
2026-05-22 | 30 | 14 | 1 | 2
2026-05-23 | 30 | 14 | 1 | 2
2026-05-24 | 30 | 14 | 1 | 2
2026-05-25 | 30 | 14 | 1 | 2
2026-05-26 | 30 | 15 | 1 | 2
2026-05-27 | 30 | 15 | 1 | 2
2026-05-28 | 30 | 15 | 1 | 2
2026-05-29 | 30 | 15 | 1 | 2
2026-05-30 | 30 | 15 | 1 | 2
2026-05-31 | 23 | 14 | 1 | 2
2026-06-01 | 23 | 14 | 1 | 2
2026-06-02 | 23 | 15 | 2 | 3
2026-06-03 | 23 | 15 | 2 | 3
2026-06-04 | 23 | 15 | 2 | 3
2026-06-05 | 23 | 15 | 2 | 3
2026-06-06 | 23 | 15 | 2 | 3
2026-06-07 | 23 | 15 | 2 | 3
2026-06-08 | 23 | 15 | 2 | 3
2026-06-09 | 23 | 15 | 2 | 3
2026-06-10 | 23 | 15 | 2 | 3
2026-06-11 | 23 | 15 | 2 | 3
2026-06-12 | 23 | 15 | 2 | 3
2026-06-13 | 23 | 15 | 2 | 3
2026-06-14 | 23 | 15 | 2 | 3
2026-06-15 | 21 | 11 | 2 | 2
2026-06-16 | 20 | 11 | 2 | 2
2026-06-17 | 18 | 11 | 2 | 2
2026-06-18 | 18 | 11 | 2 | 2
2026-06-19 | 18 | 11 | 2 | 2
2026-06-20 | 18 | 11 | 2 | 2
2026-06-21 | 18 | 11 | 2 | 2
2026-06-22 | 18 | 11 | 2 | 2
2026-06-23 | 18 | 11 | 2 | 2
2026-06-24 | 18 | 11 | 2 | 2
2026-06-25 | 18 | 11 | 2 | 2
2026-06-26 | 18 | 11 | 2 | 2
2026-06-27 | 18 | 11 | 2 | 2
2026-06-28 | 18 | 11 | 2 | 2
2026-06-29 | 18 | 11 | 2 | 2
2026-06-30 | 16 | 8 | 1 | 1
2026-07-01 | 16 | 7 | 0 | 0
2026-07-02 | 16 | 7 | 0 | 0
2026-07-03 | 16 | 7 | 0 | 0
2026-07-04 | 16 | 7 | 0 | 0
2026-07-05 | 16 | 7 | 0 | 0
2026-07-06 | 16 | 7 | 0 | 0
2026-07-07 | 16 | 7 | 0 | 0
2026-07-08 | 16 | 7 | 0 | 0
2026-07-09 | 16 | 7 | 0 | 0
2026-07-10 | 16 | 7 | 0 | 0
2026-07-11 | 16 | 7 | 0 | 0
2026-07-12 | 16 | 7 | 0 | 0
2026-07-13 | 16 | 7 | 0 | 0
2026-07-14 | 16 | 7 | 0 | 0
2026-07-15 | 15 | 7 | 0 | 0
2026-07-16 | 15 | 6 | 0 | 0
2026-07-17 | 15 | 6 | 0 | 0
2026-07-18 | 15 | 6 | 0 | 0
2026-07-19 | 15 | 6 | 0 | 0
2026-07-20 | 15 | 6 | 0 | 0
2026-07-21 | 15 | 6 | 0 | 0
2026-07-22 | 15 | 6 | 0 | 0
2026-07-23 | 15 | 6 | 0 | 0
2026-07-24 | 15 | 6 | 0 | 0
2026-07-25 | 15 | 6 | 0 | 0
2026-07-26 | 15 | 6 | 0 | 0
2026-07-27 | 15 | 6 | 0 | 0
2026-07-28 | 15 | 6 | 0 | 0
2026-07-29 | 15 | 5 | 0 | 0
2026-07-30 | 15 | 5 | 0 | 0
2026-07-31 | 10 | 4 | 0 | 0
2026-08-01 | 10 | 4 | 0 | 0
2026-08-02 | 10 | 4 | 0 | 0
2026-08-03 | 10 | 4 | 0 | 0
2026-08-04 | 10 | 4 | 0 | 0
2026-08-05 | 10 | 4 | 0 | 0
2026-08-06 | 10 | 4 | 0 | 0
2026-08-07 | 10 | 4 | 0 | 0
2026-08-08 | 10 | 4 | 0 | 0
2026-08-09 | 10 | 4 | 0 | 0
2026-08-10 | 10 | 4 | 0 | 0
2026-08-11 | 10 | 4 | 0 | 0
2026-08-12 | 10 | 4 | 0 | 0
2026-08-13 | 10 | 4 | 0 | 0
2026-08-14 | 10 | 4 | 0 | 0
2026-08-15 | 10 | 4 | 0 | 0
2026-08-16 | 10 | 4 | 0 | 0
2026-08-17 | 10 | 4 | 0 | 0
2026-08-18 | 10 | 4 | 0 | 0
2026-08-19 | 10 | 4 | 0 | 0
2026-08-20 | 10 | 4 | 0 | 0
2026-08-21 | 10 | 4 | 0 | 0
2026-08-22 | 10 | 4 | 0 | 0
2026-08-23 | 10 | 4 | 0 | 0
2026-08-24 | 10 | 4 | 0 | 0
2026-08-25 | 10 | 4 | 0 | 0
2026-08-26 | 10 | 4 | 0 | 0
2026-08-27 | 10 | 4 | 0 | 0
2026-08-28 | 10 | 4 | 0 | 0
2026-08-29 | 10 | 4 | 0 | 0
2026-08-30 | 10 | 4 | 0 | 0
2026-08-31 | 10 | 3 | 0 | 0
2026-09-01 | 10 | 3 | 0 | 0
2026-09-02 | 10 | 3 | 0 | 0
2026-09-03 | 10 | 3 | 0 | 0
2026-09-04 | 10 | 3 | 0 | 0
2026-09-05 | 10 | 3 | 0 | 0
2026-09-06 | 10 | 3 | 0 | 0
2026-09-07 | 10 | 3 | 0 | 0
2026-09-08 | 10 | 3 | 0 | 0
2026-09-09 | 10 | 3 | 0 | 0
2026-09-10 | 10 | 3 | 0 | 0
2026-09-11 | 10 | 3 | 0 | 0
2026-09-12 | 10 | 3 | 0 | 0
2026-09-13 | 10 | 3 | 0 | 0
2026-09-14 | 10 | 3 | 0 | 0
2026-09-15 | 10 | 3 | 0 | 0
2026-09-16 | 10 | 3 | 0 | 0
2026-09-17 | 10 | 3 | 0 | 0
2026-09-18 | 10 | 3 | 0 | 0
2026-09-19 | 10 | 3 | 0 | 0
2026-09-20 | 10 | 3 | 0 | 0
2026-09-21 | 10 | 3 | 0 | 0
2026-09-22 | 10 | 3 | 0 | 0
2026-09-23 | 10 | 3 | 0 | 0
2026-09-24 | 10 | 3 | 0 | 0
2026-09-25 | 10 | 3 | 0 | 0
2026-09-26 | 10 | 3 | 0 | 0
2026-09-27 | 10 | 3 | 0 | 0
2026-09-28 | 10 | 3 | 0 | 0
2026-09-29 | 10 | 3 | 0 | 0
2026-09-30 | 3 | 3 | 0 | 0
2026-10-01 | 3 | 3 | 0 | 0
2026-10-02 | 3 | 3 | 0 | 0
2026-10-03 | 3 | 3 | 0 | 0
2026-10-04 | 3 | 3 | 0 | 0
2026-10-05 | 3 | 3 | 0 | 0
2026-10-06 | 3 | 3 | 0 | 0
2026-10-07 | 3 | 3 | 0 | 0
2026-10-08 | 3 | 3 | 0 | 0
2026-10-09 | 3 | 3 | 0 | 0
2026-10-10 | 3 | 3 | 0 | 0
2026-10-11 | 3 | 3 | 0 | 0
2026-10-12 | 3 | 3 | 0 | 0
2026-10-13 | 3 | 3 | 0 | 0
2026-10-14 | 3 | 3 | 0 | 0
2026-10-15 | 3 | 3 | 0 | 0
2026-10-16 | 3 | 4 | 0 | 0
2026-10-17 | 3 | 4 | 0 | 0
2026-10-18 | 3 | 4 | 0 | 0
2026-10-19 | 3 | 4 | 0 | 0
2026-10-20 | 3 | 4 | 0 | 0
2026-10-21 | 3 | 4 | 0 | 0
2026-10-22 | 3 | 4 | 0 | 0
2026-10-23 | 3 | 4 | 0 | 0
2026-10-24 | 3 | 4 | 0 | 0
2026-10-25 | 3 | 4 | 0 | 0
2026-10-26 | 3 | 4 | 0 | 0
2026-10-27 | 3 | 4 | 0 | 0
2026-10-28 | 3 | 4 | 0 | 0
2026-10-29 | 3 | 4 | 0 | 0
2026-10-30 | 3 | 4 | 0 | 0
2026-10-31 | 2 | 4 | 0 | 0
2026-11-01 | 2 | 4 | 0 | 0
2026-11-02 | 2 | 4 | 0 | 0
2026-11-03 | 2 | 4 | 0 | 0
2026-11-04 | 2 | 4 | 0 | 0
2026-11-05 | 2 | 4 | 0 | 0
2026-11-06 | 2 | 4 | 0 | 0
2026-11-07 | 2 | 4 | 0 | 0
2026-11-08 | 2 | 4 | 0 | 0
2026-11-09 | 2 | 4 | 0 | 0
2026-11-10 | 2 | 4 | 0 | 0
2026-11-11 | 2 | 4 | 0 | 0
2026-11-12 | 2 | 4 | 0 | 0
2026-11-13 | 2 | 4 | 0 | 0
2026-11-14 | 2 | 4 | 0 | 0
2026-11-15 | 2 | 4 | 0 | 0
2026-11-16 | 2 | 4 | 0 | 0
2026-11-17 | 2 | 4 | 0 | 0
2026-11-18 | 2 | 4 | 0 | 0
2026-11-19 | 2 | 4 | 0 | 0
2026-11-20 | 2 | 4 | 0 | 0
2026-11-21 | 2 | 4 | 0 | 0
2026-11-22 | 2 | 4 | 0 | 0
2026-11-23 | 2 | 4 | 0 | 0
2026-11-24 | 2 | 4 | 0 | 0
2026-11-25 | 2 | 4 | 0 | 0
2026-11-26 | 2 | 4 | 0 | 0
2026-11-27 | 2 | 4 | 0 | 0
2026-11-28 | 2 | 4 | 0 | 0
2026-11-29 | 2 | 4 | 0 | 0
2026-11-30 | 2 | 4 | 0 | 0
2026-12-01 | 2 | 4 | 0 | 0
2026-12-02 | 2 | 4 | 0 | 0
2026-12-03 | 2 | 4 | 0 | 0
2026-12-04 | 2 | 4 | 0 | 0
2026-12-05 | 2 | 4 | 0 | 0
2026-12-06 | 2 | 4 | 0 | 0
2026-12-07 | 2 | 4 | 0 | 0
2026-12-08 | 2 | 4 | 0 | 0
2026-12-09 | 2 | 4 | 0 | 0
2026-12-10 | 2 | 4 | 0 | 0
2026-12-11 | 2 | 4 | 0 | 0
2026-12-12 | 2 | 4 | 0 | 0
2026-12-13 | 2 | 4 | 0 | 0
2026-12-14 | 2 | 4 | 0 | 0
2026-12-15 | 2 | 4 | 0 | 0
2026-12-16 | 2 | 4 | 0 | 0
2026-12-17 | 2 | 4 | 0 | 0
2026-12-18 | 2 | 4 | 0 | 0
2026-12-19 | 2 | 4 | 0 | 0
2026-12-20 | 2 | 4 | 0 | 0
2026-12-21 | 2 | 4 | 0 | 0
2026-12-22 | 2 | 4 | 0 | 0
2026-12-23 | 2 | 3 | 0 | 0
2026-12-24 | 2 | 3 | 0 | 0
2026-12-25 | 2 | 3 | 0 | 0
2026-12-26 | 2 | 3 | 0 | 0
2026-12-27 | 2 | 3 | 0 | 0
2026-12-28 | 2 | 3 | 0 | 0
2026-12-29 | 2 | 3 | 0 | 0
2026-12-30 | 2 | 3 | 0 | 0
2026-12-31 | 1 | 0 | 0 | 0
2027-01-01 | 0 | 0 | 0 | 0

## PBI_Source (hidden)
KeyNorm | Process Group | Associated Process on L1 | ProcessGroupOrder | L1OrderInGroup | SortKey | Start_Total | End_Total | Start_PBI | End_PBI | DummyDatesFlag | % Work done | Actual Phase | Planned phase | IT Process Initiative Lead | IT Process Manager | IT Process Consultant | Contact summary | StatusCategory | StatusOrder | KeyNorm | Process Group | Associated Process on L1 | Phase | PhaseOrder | Start | End | Duration in days | Planned phase | Actual Phase
mp¦manage it strategy | MP | Manage IT strategy | 1 | 1 | 1001 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it strategy | MP | Manage IT strategy | Elaboration | 1 | 2026-02-02 | 2026-04-30 | 64 | Elaboration in progress | Elaboration in progress
mp¦manage it governance framework | MP | Manage IT governance framework | 1 | 2 | 1002 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it strategy | MP | Manage IT strategy | Implementation LIS | 2 | 2026-05-14 | 2026-07-29 | 55 | Scheduled
mp¦manage enterprise architecture | MP | Manage enterprise architecture | 1 | 3 | 1003 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it strategy | MP | Manage IT strategy | Implementation COT | 4 |  |  | 0
mp¦manage it portfolio | MP | Manage IT portfolio | 1 | 4 | 1004 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it strategy | MP | Manage IT strategy | Implementation LUS | 3 |  |  | 0
mp¦manage and control it financials | MP | Manage and control IT financials | 1 | 5 | 1005 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it governance framework | MP | Manage IT governance framework | Elaboration | 1 | 2026-03-16 | 2026-05-21 | 49 | Elaboration in progress | Elaboration in progress
mp¦manage it stakeholder relationships | MP | Manage IT stakeholder relationships | 1 | 6 | 1006 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it governance framework | MP | Manage IT governance framework | Implementation LIS | 2 | 2026-05-25 | 2026-08-31 | 71 | Scheduled
mp¦manage it processes and continuous improvement | MP | Manage IT processes and continuous improvement | 1 | 7 | 1007 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it governance framework | MP | Manage IT governance framework | Implementation COT | 4 |  |  | 0
mp¦manage it risks and compliance | MP | Manage IT risks and compliance | 1 | 8 | 1008 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it governance framework | MP | Manage IT governance framework | Implementation LUS | 3 |  |  | 0
cp¦plan it service | CP | Plan IT service | 2 | 1 | 2001 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage enterprise architecture | MP | Manage enterprise architecture | Elaboration | 1 | 2026-02-23 | 2026-05-08 | 54.85 | Elaboration in progress | Delayed
cp¦build it service | CP | Build IT Service | 2 | 2 | 2002 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage enterprise architecture | MP | Manage enterprise architecture | Implementation LIS | 2 | 2026-05-08 | 2026-07-16 | 49 | Scheduled
cp¦deliver it service | CP | Deliver IT service | 2 | 3 | 2003 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage enterprise architecture | MP | Manage enterprise architecture | Implementation COT | 4 | 2026-05-08 | 2026-05-11 | 1 | Scheduled
cp¦run it service | CP | Run IT service | 2 | 4 | 2004 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage enterprise architecture | MP | Manage enterprise architecture | Implementation LUS | 3 | 2026-05-08 | 2026-05-11 | 1 | Scheduled
sp¦ensure information security | SP | Ensure Information security | 3 | 1 | 3001 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it portfolio | MP | Manage IT portfolio | Elaboration | 1 | 2025-11-11 | 2026-01-29 | 58 | Elaboration Done | Elaboration Done
sp¦manage it project | SP | Manage IT project | 3 | 2 | 3002 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it portfolio | MP | Manage IT portfolio | Implementation LIS | 2 |  |  | 0
sp¦manage it sourcing and procurement | SP | Manage IT sourcing and procurement | 3 | 3 | 3003 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it portfolio | MP | Manage IT portfolio | Implementation COT | 4 |  |  | 0
sp¦provide and develop it workforce | SP | Provide and develop IT workforce | 3 | 4 | 3004 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage it portfolio | MP | Manage IT portfolio | Implementation LUS | 3 |  |  | 0
sp¦ensure performance and conformance of it services | SP | Ensure performance and conformance of IT services | 3 | 5 | 3005 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage and control it financials | MP | Manage and control IT financials | Elaboration | 1 | 2025-10-15 | 2026-04-30 | 142 | Elaboration in progress | Elaboration in progress
sp¦manage it knowledge | SP | Manage IT knowledge | 3 | 6 | 3006 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage and control it financials | MP | Manage and control IT financials | Implementation LIS | 2 | 2026-05-01 | 2026-07-31 | 66 | Scheduled
sp¦leverage it innovtion | SP | Leverage IT innovtion | 3 | 7 | 3007 |  |  | 1899-12-31 | 1900-01-01 | 1 | [9 empty] | mp¦manage and control it financials | MP | Manage and control IT financials | Implementation LUS | 3 |  |  | 0
[20 empty] | mp¦manage it stakeholder relationships | MP | Manage IT stakeholder relationships | Elaboration | 1 | 2026-04-01 | 2026-06-15 | 54 | Elaboration in progress | Delayed
[20 empty] | mp¦manage it stakeholder relationships | MP | Manage IT stakeholder relationships | Implementation LIS | 2 | 2026-10-15 | 2026-12-23 | 50 | Scheduled
[20 empty] | mp¦manage it stakeholder relationships | MP | Manage IT stakeholder relationships | Implementation COT | 4 |  |  | 0
[20 empty] | mp¦manage it stakeholder relationships | MP | Manage IT stakeholder relationships | Implementation LUS | 3 |  |  | 0
[20 empty] | mp¦manage it processes and continuous improvement | MP | Manage IT processes and continuous improvement | Elaboration | 1 | 2025-10-01 | 2025-10-01 | 1 | Elaboration Done | Elaboration Done
[20 empty] | mp¦manage it processes and continuous improvement | MP | Manage IT processes and continuous improvement | Implementation LIS | 2 |  |  | 0
[20 empty] | mp¦manage it processes and continuous improvement | MP | Manage IT processes and continuous improvement | Implementation COT | 4 |  |  | 0
[20 empty] | mp¦manage it processes and continuous improvement | MP | Manage IT processes and continuous improvement | Implementation LUS | 3 |  |  | 0
[20 empty] | mp¦manage it risks and compliance | MP | Manage IT risks and compliance | Elaboration | 1 | 2025-10-01 | 2025-10-01 | 1 | Elaboration Done | Elaboration Done
[20 empty] | mp¦manage it risks and compliance | MP | Manage IT risks and compliance | Implementation LIS | 2 |  |  | 0
[20 empty] | mp¦manage it risks and compliance | MP | Manage IT risks and compliance | Implementation COT | 4 |  |  | 0
[20 empty] | mp¦manage it risks and compliance | MP | Manage IT risks and compliance | Implementation LUS | 3 |  |  | 0
[20 empty] | cp¦plan it service | CP | Plan IT service | Elaboration | 1 | 2025-10-16 | 2025-10-31 | 12 | Elaboration Done | Elaboration Done
[20 empty] | cp¦plan it service | CP | Plan IT service | Implementation LIS | 2 | 2025-11-01 | 2026-02-28 | 85 | Implementation LIS Done | Delayed
[20 empty] | cp¦plan it service | CP | Plan IT service | Implementation COT | 4 | 2025-11-03 | 2026-03-31 | 107 | Implementation COT Done | Delayed
[20 empty] | cp¦plan it service | CP | Plan IT service | Implementation LUS | 3 |  |  | 0
[20 empty] | cp¦build it service | CP | Build IT Service | Elaboration | 1 |  |  | 0
[20 empty] | cp¦build it service | CP | Build IT Service | Implementation LIS | 2 |  |  | 0
[20 empty] | cp¦build it service | CP | Build IT Service | Implementation COT | 4 |  |  | 0
[20 empty] | cp¦build it service | CP | Build IT Service | Implementation LUS | 3 |  |  | 0
[20 empty] | cp¦deliver it service | CP | Deliver IT service | Elaboration | 1 |  |  | 0
[20 empty] | cp¦deliver it service | CP | Deliver IT service | Implementation LIS | 2 |  |  | 0
[20 empty] | cp¦deliver it service | CP | Deliver IT service | Implementation COT | 4 |  |  | 0
[20 empty] | cp¦deliver it service | CP | Deliver IT service | Implementation LUS | 3 |  |  | 0
[20 empty] | cp¦run it service | CP | Run IT service | Elaboration | 1 | 2025-10-16 | 2026-06-30 | 184 | Elaboration in progress | Delayed
[20 empty] | cp¦run it service | CP | Run IT service | Implementation LIS | 2 |  |  | 0
[20 empty] | cp¦run it service | CP | Run IT service | Implementation COT | 4 |  |  | 0
[20 empty] | cp¦run it service | CP | Run IT service | Implementation LUS | 3 |  |  | 0
[20 empty] | sp¦ensure information security | SP | Ensure Information security | Elaboration | 1 | 2025-10-16 |  | 0
[20 empty] | sp¦ensure information security | SP | Ensure Information security | Implementation LIS | 2 |  |  | 0
[20 empty] | sp¦ensure information security | SP | Ensure Information security | Implementation COT | 4 |  |  | 0
[20 empty] | sp¦ensure information security | SP | Ensure Information security | Implementation LUS | 3 |  |  | 0
[20 empty] | sp¦manage it project | SP | Manage IT project | Elaboration | 1 | 2025-11-11 | 2025-12-10 | 22 | Elaboration Done | Elaboration Done
[20 empty] | sp¦manage it project | SP | Manage IT project | Implementation LIS | 2 |  |  | 0
[20 empty] | sp¦manage it project | SP | Manage IT project | Implementation COT | 4 |  |  | 0
[20 empty] | sp¦manage it project | SP | Manage IT project | Implementation LUS | 3 |  |  | 0
[20 empty] | sp¦manage it sourcing and procurement | SP | Manage IT sourcing and procurement | Elaboration | 1 | 2026-04-20 | 2026-04-22 | 3 | Elaboration Done | Elaboration in progress
[20 empty] | sp¦manage it sourcing and procurement | SP | Manage IT sourcing and procurement | Implementation LIS | 2 |  |  | 0
[20 empty] | sp¦manage it sourcing and procurement | SP | Manage IT sourcing and procurement | Implementation COT | 4 |  |  | 0
[20 empty] | sp¦manage it sourcing and procurement | SP | Manage IT sourcing and procurement | Implementation LUS | 3 |  |  | 0
[20 empty] | sp¦provide and develop it workforce | SP | Provide and develop IT workforce | Elaboration | 1 | 2025-10-01 | 2025-10-01 | 1 | Elaboration Done | Elaboration Done
[20 empty] | sp¦provide and develop it workforce | SP | Provide and develop IT workforce | Implementation LIS | 2 |  |  | 0
[20 empty] | sp¦provide and develop it workforce | SP | Provide and develop IT workforce | Implementation COT | 4 |  |  | 0
[20 empty] | sp¦provide and develop it workforce | SP | Provide and develop IT workforce | Implementation LUS | 3 |  |  | 0
[20 empty] | sp¦ensure performance and conformance of it services | SP | Ensure performance and conformance of IT services | Elaboration | 1 | 2026-04-15 | 2026-06-30 | 55 | Elaboration in progress | Delayed
[20 empty] | sp¦ensure performance and conformance of it services | SP | Ensure performance and conformance of IT services | Implementation LIS | 2 |  |  | 0
[20 empty] | sp¦ensure performance and conformance of it services | SP | Ensure performance and conformance of IT services | Implementation COT | 4 |  |  | 0
[20 empty] | sp¦ensure performance and conformance of it services | SP | Ensure performance and conformance of IT services | Implementation LUS | 3 |  |  | 0
[20 empty] | sp¦manage it knowledge | SP | Manage IT knowledge | Elaboration | 1 | 2026-01-20 | 2026-02-25 | 27 | Elaboration Done | Elaboration Done
[20 empty] | sp¦manage it knowledge | SP | Manage IT knowledge | Implementation LIS | 2 | 2026-04-15 | 2026-06-30 | 55 | Implementation LIS | Delayed
[20 empty] | sp¦manage it knowledge | SP | Manage IT knowledge | Implementation COT | 4 |  |  | 0
[20 empty] | sp¦manage it knowledge | SP | Manage IT knowledge | Implementation LUS | 3 |  |  | 0
[20 empty] | sp¦leverage it innovtion | SP | Leverage IT innovtion | Elaboration | 1 | 2025-10-16 |  | 0
[20 empty] | sp¦leverage it innovtion | SP | Leverage IT innovtion | Implementation LIS | 2 |  |  | 0
[20 empty] | sp¦leverage it innovtion | SP | Leverage IT innovtion | Implementation COT | 4 |  |  | 0
[20 empty] | sp¦leverage it innovtion | SP | Leverage IT innovtion | Implementation LUS | 3 |  |  | 0

## HTML_Dashboard (hidden)
Chunk# | HTML (alle Chunks aus Spalte B ab Zeile 2 kopieren, zusammenfügen, als dashboard.html speichern)
1 | <!doctype html> <html lang="en"> <head> <meta charset="utf-8" /> <meta name="viewport" content="width=device-width, initial-scale=1" /> <meta name="color-scheme" content="light" /> <title>Corporate IT Processes timeline</title> <style> :root{color-scheme:light;--bg:#f8fafc;--panel:#ffffff;--muted:#475569;--text:#0f172a;--line:#e2e8f0;--accent:#2563eb;--pg-mp:#BDC4CA;--pg-cp:#FFCC00;--pg-sp:#8BB2C2;} *{box-sizing:border-box;font-family:Segoe UI,system-ui,-apple-system,Arial,sans-serif;} html,body{height:100%;margin:0;background:var(--bg);color:var(--text);} .header{display:flex;align-items:center;justify-content:space-between;padding:14px 18px;border-bottom:1px solid var(--line);background:var(--panel);position:sticky;top:0;z-index:10;} .hTitle{font-size:18px;font-weight:700;letter-spacing:.2px;} .wrap{display:grid;grid-template-columns:320px 1fr;min-height:calc(100vh - 56px);} .sidebar{border-right:1px solid var(--line);background:var(--panel);padding:14px;} .main{padding:12px 14px;} .btn{border:1px solid #cbd5e1;background:#ffffff;color:#0f172a;border-radius:8px;padding:8px 10px;font-size:12px;cursor:pointer;} .btn:hover{border-color:#94a3b8;} .btnRow{display:flex;gap:8px;flex-wrap:wrap;align-items:center;justify-content:flex-end;} .grid{display:grid;grid-template-columns:320px 1fr;gap:0;border:1px solid var(--line);border-radius:12px;overflow:hidden;background:var(--panel);} .labels{background:var(--panel);border-right:1px solid var(--line);} .timeline{position:relative;background:#ffffff;overflow:auto;height:520px;} .axis{position:sticky;top:0;background:var(--panel);border-bottom:1px solid var(--line);height:32px;z-index:5;} .tick{position:absolute;top:0;height:32px;border-left:1px solid rgba(148,163,184,.45);} .tick span{position:absolute;left:4px;top:7px;font-size:11px;color:#334155;white-space:nowrap;} .labelRow{height:28px;display:flex;align-items:center;gap:8px;padding:0 10px;border-bottom:1px solid rgba(148,163,184,.25);white-space:nowrap;overflow:hidden;text-overflow:ellipsis;} .labelRow .toggle{width:18px;height:18px;border:1px solid #94a3b8;border-radius:4px;display:flex;align-items:center;justify-content:center;font-size:12px;color:#334155;flex:0 0 auto;cursor:pointer;background:#fff;} .labelRow .toggle.hidden{visibility:hidden;} .labelRow .name{overflow:hidden;text-overflow:ellipsis;} .labelRow.pg{font-weight:700;color:#0b1220;} .labelRow.pg.pg-mp{background:var(--pg-mp);} .labelRow.pg.pg-cp{background:var(--pg-cp);} .labelRow.pg.pg-sp{background:var(--pg-sp);} .labelRow.l1{font-weight:700;background:rgba(148,163,184,.18);} .indent-0{padding-left:10px;} .indent-1{padding-left:22px;} .indent-2{padding-left:36px;} .indent-3{padding-left:52px;} .indent-4{padding-left:70px;} .timeRow{height:28px;border-bottom:1px solid rgba(148,163,184,.25);position:relative;} .bar{position:absolute;top:7px;height:14px;border-radius:6px;opacity:.95;} .bar.delayed{outline:2px dashed rgba(239,68,68,.9);outline-offset:2px;} .bar.rollup{top:9px;height:10px;border-radius:999px;opacity:.9;} .todayLine{position:absolute;top:0;bottom:0;width:2px;background:rgba(239,68,68,.7);box-shadow:0 0 0 2px rgba(239,68,68,.18);z-index:4;pointer-events:none;} .legend{display:flex;gap:10px;align-items:center;flex-wrap:wrap;margin:10px 0 8px;} .legItem{display:flex;align-items:center;gap:6px;font-size:12px;color:#334155;cursor:pointer;user-select:none;} .sw{width:12px;height:12px;border-radius:3px;} .legItem.off{opacity:.35;} .tableWrap{margin-top:12px;border:1px solid var(--line);border-radius:12px;overflow:hidden;background:var(--panel);} table{width:100%;border-collapse:collapse;background:var(--panel);} th,td{padding:9px 10px;border-bottom:1px solid rgba(148,163,184,.25);font-size:12px;} th{position:sticky;top:0;background:var(--panel);text-align:left;color:#0f172a;font-weight:700;} .small{font-size:12px;color:#475569;} .hint{color:#475569;} </style> </head> <body> <div class="header"><div class="hTitle">Corporate IT Processes timeline</div> <div class="btnRow"><button class="btn" id="btnExpand">Expand all</button><button class="btn" id="btnCollapse">Collapse all</button><button class="btn" id="chipReset">Reset filters</button></div></div> <div class="wrap"><div class="sidebar"> <div class="small" style="margin-bottom:8px;">Filters</div> <div style="display:grid;gap:8px;"> <select id="fGroup" class="btn" style="width:100%"><option value="">All Process Groups</option></select> <select id="fL1" class="btn" style="width:100%"><option value="">All L1 Processes</option></select> <select id="fConsultant" class="btn" style="width:100%"><option value="">IT Process Consultant</option></select> <select id="fManager" class="btn" style="width:100%"><option value="">IT Process Manager</option></select> <select id="fLead" class="btn" style="width:100%"><option value="">IT Process Initiative Lead</option></select> <button class="btn" id="chipDelayed" style="text-align:left;">Delayed only</button> </div><div id="countInfo" class="small" style="margin-top:10px;"></div></div> <div class="main"><div class="legend" id="legend"></div> <div class="grid"><div class="labels" id="labels"></div> <div class="timeline" id="timeline"><div class="axis" id="axis"></div><div class="rows" id="bars"></div></div></div> <div class="tableWrap"><table><thead><tr> <th>Process</th><th>Level</th><th>Phase</th><th>Start</th><th>End</th><th>% Done</th><th>IT Process Initiative Lead</th><th>IT Process Manager</th><th>IT Process Consultant</th><th>Status</th> </tr></thead><tbody id="detailBody"></tbody></table></div></div></div> <textarea id="dataB64" style="display:none">eyJkYXRhIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgc3RyYXRlZ3kiLCJwcm9jIjoiTWFuYWdlIElUIHN0cmF0ZWd5IiwibHZsIjoiTDEiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAyLTAyIiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiS3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJGZWxkZXIgTWF4IChMTEkpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgc3RyYXRlZ3l8TDF8TWFuYWdlIElUIHN0cmF0ZWd5In0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgc3RyYXRlZ3kiLCJwcm9jIjoiTWFuYWdlIElUIHN0cmF0ZWd5IiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNS0xNCIsImVuZCI6IjIwMjYtMDctMjkiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLcmVpcyBBbmRyZWFzIChMTEkpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkZlbGRlciBNYXggKExMSSkiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBzdHJhdGVneXxMMXxNYW5hZ2UgSVQgc3RyYXRlZ3kifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29yayIsInByb2MiOiJNYWludGFpbiBJVCBnbG9zc2FyeSIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDEtMDciLCJlbmQiOiIyMDI2LTAxLTE3IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMgRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkZlbGRlciBNYXggKExMSSkiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29ya3xMMnxNYWludGFpbiBJVCBnbG9zc2FyeSJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIGdvdmVybmFuY2UgZnJhbWV3b3JrIiwicHJvYyI6Ik1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29yayIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMy0xNiIsImVuZCI6IjIwMjYtMDUtMjEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDA1IiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKTtLcmVpcyBBbmRyZWFzIChMTEkpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkZlbGRlciBNYXggKExMSSkiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29ya3xMMXxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29yayIsInByb2MiOiJNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA1LTI1IiwiZW5kIjoiMjAyNi0wOC0zMSIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKTtLcmVpcyBBbmRyZWFzIChMTEkpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkZlbGRlciBNYXggKExMSSkiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29ya3xMMXxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsInByb2MiOiJNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDItMjMiLCJlbmQiOiIyMDI2LTA1LTA4IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJOdXNzYmF1bWVyIEZsb3JpYW4gKExCQykiLCJsZWFkIjoiR3VqcmFsIFBhcnRoIChDT0ItQ09ULUlUKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlfEwxfE1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwicHJvYyI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsImx2bCI6IkwxIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjYtMDUtMDgiLCJlbmQiOiIyMDI2LTA1LTExIiwiYWN0dWFsIjoiIiwicGxhbm5lZCI6IlNjaGVkdWxlZCIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiIiwibWFuYWdlciI6IiIsImxlYWQiOiIiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZXxMMXxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsInByb2MiOiJNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA1LTA4IiwiZW5kIjoiMjAyNi0wNy0xNiIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IiIsIm1hbmFnZXIiOiIiLCJsZWFkIjoiIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmV8TDF8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUiLCJwcm9jIjoiTWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExVUyIsInN0YXJ0IjoiMjAyNi0wNS0wOCIsImVuZCI6IjIwMjYtMDUtMTEiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiIiLCJtYW5hZ2VyIjoiIiwibGVhZCI6IiIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlfEwxfE1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwicHJvYyI6IlN0cmF0ZWdpYyBhcmNoaXRlY3R1cmUgcHJvY2VzcyIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMi0yMyIsImVuZCI6IjIwMjYtMDQtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik51c3NiYXVtZXIgRmxvcmlhbiAoTEJDKSIsImxlYWQiOiJHdWpyYWwgUGFydGggKENPQi1DT1QtSVQpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmV8TDJ8U3RyYXRlZ2ljIGFyY2hpdGVjdHVyZSBwcm9jZXNzIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcG9ydGZvbGlvIiwicHJvYyI6Ik1hbmFnZSBJVCBwb3J0Zm9saW8iLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTEiLCJlbmQiOiIyMDI2LTAxLTI5IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKTtLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiIiwibGVhZCI6IiIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMXxNYW5hZ2UgSVQgcG9ydGZvbGlvIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcG9ydGZvbGlvIiwicHJvYyI6Ik1hbmFnZSBJVCBwcm9qZWN0IHBvcnRmb2xpbyIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMS0xMCIsImVuZCI6IjIwMjUtMTItMTAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkZyYW5rIE1hcmVuIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiTcO8aGxiYWNoZXIgQ2hyaXN0aWFuIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcG9ydGZvbGlvfEwyfE1hbmFnZSBJVCBwcm9qZWN0IHBvcnRmb2xpbyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHBvcnRmb2xpbyIsInByb2MiOiJNYW5hZ2UgSVQgcHJvamVjdCBwb3J0Zm9saW8iLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTAyLTAxIiwiZW5kIjoiMjAyNi0wNS0zMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6Ik3DvGhsYmFjaGVyIENocmlzdGlhbiAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMnxNYW5hZ2UgSVQgcHJvamVjdCBwb3J0Zm9saW8ifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwb3J0Zm9saW8iLCJwcm9jIjoiTWFuYWdlIElUIHNlcnZpY2UgcG9ydGZvbGlvIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNi0xNSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUyk7S3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IkNlaWxpYSBSb3NlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMnxNYW5hZ2UgSVQgc2VydmljZSBwb3J0Zm9saW8ifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwb3J0Zm9saW8iLCJwcm9jIjoiTWFuYWdlIElUIHNlcnZpY2UgcG9ydGZvbGlvIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNi0xNSIsImVuZCI6IjIwMjYtMDktMDgiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKTtLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiQ2VpbGlhIFJvc2VyIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcG9ydGZvbGlvfEwyfE1hbmFnZSBJVCBzZXJ2aWNlIHBvcnRmb2xpbyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJwcm9jIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMTUiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJIeW5layBUb2JpYXMgKExJUyk7S3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNb3NlciBNYXJpbyAoTElTLUxBSCkiLCJsZWFkIjoiRnJhbmsgTmljb2xlIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgYW5kIGNvbnRyb2wgSVQgZmluYW5jaWFsc3xMMXxNYW5hZ2UgYW5kIGNvbnRyb2wgSVQgZmluYW5jaWFscyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJwcm9jIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA1LTAxIiwiZW5kIjoiMjAyNi0wNy0zMSIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikh5bmVrIFRvYmlhcyAoTElTKTtLcmVpcyBBbmRyZWFzIChMTEkpIiwibWFuYWdlciI6Ik1vc2VyIE1hcmlvIChMSVMtTEFIKSIsImxlYWQiOiJGcmFuayBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzfEwxfE1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyIsInByb2MiOiJNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjYtMDYtMTUiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLcmVpcyBBbmRyZWFzIChMTEkpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkZlbGRlciBNYXggKExMSSkiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBzdGFrZWhvbGRlciByZWxhdGlvbnNoaXBzfEwxfE1hbmFnZSBJVCBzdGFrZWhvbGRlciByZWxhdGlvbnNoaXBzIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyIsInByb2MiOiJNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyIsImx2bCI6IkwxIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMTAtMTUiLCJlbmQiOiIyMDI2LTEyLTIzIiwiYWN0dWFsIjoiIiwicGxhbm5lZCI6IlNjaGVkdWxlZCIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJGZWxkZXIgTWF4IChMTEkpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwc3xMMXxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsInByb2MiOiJBbmFseXNlIHByb2Nlc3MiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI1LTEwLTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8QW5hbHlzZSBwcm9jZXNzIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6IkRldmVsb3AgYW5kIG1haW50YWluIElUIEJQTSBmcmFtZXdvcmsiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMDgtMDQiLCJlbmQiOiIyMDI1LTA4LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8RGV2ZWxvcCBhbmQgbWFpbnRhaW4gSVQgQlBNIGZyYW1ld29yayJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsInByb2MiOiJFbGFib3JhdGUgdG8tYmUgcHJvY2VzcyAoViAyLjApIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEyIiwiZW5kIjoiMjAyNi0wNS0zMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xFbGFib3JhdGUgdG8tYmUgcHJvY2VzcyAoViAyLjApIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6IklkZW50aWZ5IHByb2Nlc3MgYW5kIGRldGVybWluZSBnb2FscyAoViAyLjApIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEyIiwiZW5kIjoiMjAyNi0wNS0zMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xJZGVudGlmeSBwcm9jZXNzIGFuZCBkZXRlcm1pbmUgZ29hbHMgKFYgMi4wKSJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsInByb2MiOiJJbXBsZW1lbnQgcHJvY2VzcyAoViAyLjApIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEyIiwiZW5kIjoiMjAyNi0wNS0zMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xJbXBsZW1lbnQgcHJvY2VzcyAoViAyLjApIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6Ik1hbmFnZSBjb250aW51b3VzIGltcHJvdmVtZW50IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wMS0zMCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKTtCw7ZobWUgTWF0dGhpYXMgKGV4dC4pIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMnxNYW5hZ2UgY29udGludW91cyBpbXByb3ZlbWVudCJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsInByb2MiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwibHZsIjoiTDEiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwxfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJwcm9jIjoiUGVyZm9ybSBhbmQgbWVhc3VyZSBwcm9jZXNzIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwzfFBlcmZvcm0gYW5kIG1lYXN1cmUgcHJvY2VzcyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsInByb2MiOiJQZXJmb3JtIG9wZXJhdGlvbmFsIHByb2Nlc3MgbWFuYWdlbWVudCAoViAyLjApIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEyIiwiZW5kIjoiMjAyNi0wNS0zMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMnxQZXJmb3JtIG9wZXJhdGlvbmFsIHByb2Nlc3MgbWFuYWdlbWVudCAoViAyLjApIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6IlBsYW4gcHJvY2VzcyBleGVjdXRpb24gKFYgMi4wKSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMiIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8UGxhbiBwcm9jZXNzIGV4ZWN1dGlvbiAoViAyLjApIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJwcm9jIjoiREMvRENDL01TQyBJVC1jb21wbGlhbmNlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wOS0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTW9ubmllciBNdXJpZWxsZSAoTEVDKSIsImxlYWQiOiJNdWVza2VucyBKYW4gKExITykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xEQy9EQ0MvTVNDIElULWNvbXBsaWFuY2UifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJJbXBsZW1lbnQgdG8gaW1wcm92ZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDktMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiTXVlc2tlbnMgSmFuIChMSE8pIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8SW1wbGVtZW50IHRvIGltcHJvdmUifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNYW5hZ2UgSVQgY29tcGxpYW5jZSIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDktMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiTXVlc2tlbnMgSmFuIChMSE8pIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDJ8TWFuYWdlIElUIGNvbXBsaWFuY2UifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI1LTEwLTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiTXVlc2tlbnMgSmFuIChMSE8pIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDF8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJwcm9jIjoiTWFuYWdlIElULUMgZnJhbWV3b3JrIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wOS0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTW9ubmllciBNdXJpZWxsZSAoTEVDKSIsImxlYWQiOiJNdWVza2VucyBKYW4gKExITykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xNYW5hZ2UgSVQtQyBmcmFtZXdvcmsifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNYW5hZ2UgSVQtQyBzdHJhdGVneSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDktMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiTXVlc2tlbnMgSmFuIChMSE8pIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8TWFuYWdlIElULUMgc3RyYXRlZ3kifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNb25pdG9yIHRvIGRlbGVnYXRlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wOS0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTW9ubmllciBNdXJpZWxsZSAoTEVDKSIsImxlYWQiOiJNdWVza2VucyBKYW4gKExITykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xNb25pdG9yIHRvIGRlbGVnYXRlIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJwcm9jIjoiUmVxdWlyZW1lbnRzIHRvIG1lYXN1cmVzIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wOS0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTW9ubmllciBNdXJpZWxsZSAoTEVDKSIsImxlYWQiOiJNdWVza2VucyBKYW4gKExITykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xSZXF1aXJlbWVudHMgdG8gbWVhc3VyZXMifSx7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJBbmFseXNlIGFyY2hpdGVjdHVyZSBpbXBhY3QiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMDgtMDEiLCJlbmQiOiIyMDI1LTEwLTE1IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiUGVybmV0IEJlbm9pdCAoTEVDKSAoTUlOKSIsIm5vZGVJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwzfEFuYWx5c2UgYXJjaGl0ZWN0dXJlIGltcGFjdCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkFuYWx5c2UgYXJjaGl0ZWN0dXJlIGltcGFjdCIsImx2bCI6IkwzIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjUtMTAtMTYiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJQZXJuZXQgQmVub2l0IChMRUMpIChNSU4pIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDN8QW5hbHlzZSBhcmNoaXRlY3R1cmUgaW1wYWN0In0seyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiQXBwcm92ZSBJVCBkZW1hbmQiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMDgtMDEiLCJlbmQiOiIyMDI1LTA4LTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxBcHByb3ZlIElUIGRlbWFuZCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkFwcHJvdmUgSVQgZGVtYW5kIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNS0xMS0wMyIsImVuZCI6IjIwMjYtMDMtMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxBcHByb3ZlIElUIGRlbWFuZCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkFwcHJvdmUgSVQgZGVtYW5kIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNS0xMS0wMSIsImVuZCI6IjIwMjYtMDItMjgiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1
2 | IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxBcHByb3ZlIElUIGRlbWFuZCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0wOC0wMSIsImVuZCI6IjIwMjUtMDgtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJTcGlldGggVGluYSAoTElTKSIsIm5vZGVJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwyfEV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjUtMTEtMDMiLCJlbmQiOiIyMDI2LTAzLTMxIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBDT1QgRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8RXZhbHVhdGUgYW5kIHF1YWxpZnkgSVQgZGVtYW5kIn0seyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiRXZhbHVhdGUgYW5kIHF1YWxpZnkgSVQgZGVtYW5kIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNS0xMS0wMSIsImVuZCI6IjIwMjYtMDItMjgiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxFdmFsdWF0ZSBhbmQgcXVhbGlmeSBJVCBkZW1hbmQifSx7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJQZXJmb3JtIGluaXRpYWwgYXNzZXNzbWVudCBvZiBjdXN0b21lciBuZWVkIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTA4LTAxIiwiZW5kIjoiMjAyNS0wOC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8UGVyZm9ybSBpbml0aWFsIGFzc2Vzc21lbnQgb2YgY3VzdG9tZXIgbmVlZCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IlBlcmZvcm0gaW5pdGlhbCBhc3Nlc3NtZW50IG9mIGN1c3RvbWVyIG5lZWQiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gQ09UIiwic3RhcnQiOiIyMDI1LTExLTAzIiwiZW5kIjoiMjAyNi0wMy0zMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gQ09UIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJTcGlldGggVGluYSAoTElTKSIsIm5vZGVJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwyfFBlcmZvcm0gaW5pdGlhbCBhc3Nlc3NtZW50IG9mIGN1c3RvbWVyIG5lZWQifSx7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJQZXJmb3JtIGluaXRpYWwgYXNzZXNzbWVudCBvZiBjdXN0b21lciBuZWVkIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNS0xMS0wMSIsImVuZCI6IjIwMjYtMDItMjgiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxQZXJmb3JtIGluaXRpYWwgYXNzZXNzbWVudCBvZiBjdXN0b21lciBuZWVkIn0seyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiUGxhbiBJVCBzZXJ2aWNlIiwibHZsIjoiTDEiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTE2IiwiZW5kIjoiMjAyNS0xMC0zMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDF8UGxhbiBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiUGxhbiBJVCBzZXJ2aWNlIiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNS0xMS0wMyIsImVuZCI6IjIwMjYtMDMtMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMXxQbGFuIElUIHNlcnZpY2UifSx7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJQbGFuIElUIHNlcnZpY2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI1LTExLTAxIiwiZW5kIjoiMjAyNi0wMi0yOCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIERvbmUiLCJwY3QiOiIwLjAwNzUiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDF8UGxhbiBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkNvbmR1Y3QgbWFya2V0IGFuYWx5c2lzIGFuZCBjb21waWxlIGxvbmcgb3Igc2hvcnQgbGlzdCIsImx2bCI6Ikw0IiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTAtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUHJlaXNzIE1hdHRoaWFzIChMQkMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fENvbmR1Y3QgbWFya2V0IGFuYWx5c2lzIGFuZCBjb21waWxlIGxvbmcgb3Igc2hvcnQgbGlzdCJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJEZWZpbmUgc29sdXRpb24gdGFyZ2V0IGFyY2hpdGVjdHVyZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMi0wNSIsImVuZCI6IjIwMjYtMDQtMjEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJOdXNzYmF1bWVyIEZsb3JpYW4gKExCQykiLCJsZWFkIjoiSGFtbWVyIE1hcmNvIChBRVIpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwzfERlZmluZSBzb2x1dGlvbiB0YXJnZXQgYXJjaGl0ZWN0dXJlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkRlZmluZSBzb2x1dGlvbiB0YXJnZXQgYXJjaGl0ZWN0dXJlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNi0wNC0yMiIsImVuZCI6IjIwMjYtMDQtMjIiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik51c3NiYXVtZXIgRmxvcmlhbiAoTEJDKSIsImxlYWQiOiJIYW1tZXIgTWFyY28gKEFFUikiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8RGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTIyIiwiZW5kIjoiMjAyNi0wNi0yMiIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik51c3NiYXVtZXIgRmxvcmlhbiAoTEJDKSIsImxlYWQiOiJIYW1tZXIgTWFyY28gKEFFUikiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8RGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTFVTIiwic3RhcnQiOiIyMDI2LTAxLTE0IiwiZW5kIjoiMjAyNi0wMS0xNCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTFVTIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTnVzc2JhdW1lciBGbG9yaWFuIChMQkMpIiwibGVhZCI6IkhhbW1lciBNYXJjbyAoQUVSKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xEZWZpbmUgc29sdXRpb24gdGFyZ2V0IGFyY2hpdGVjdHVyZSJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJEZXBsb3kgSVQgc2VydmljZSIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wNC0xNSIsImVuZCI6IjIwMjYtMDYtMTUiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IkRhbGVrIE1hcnRpbiAoTElTKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxEZXBsb3kgSVQgc2VydmljZSJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJEZXBsb3kgSVQgc2VydmljZSIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDctMTUiLCJlbmQiOiIyMDI2LTA4LTMxIiwiYWN0dWFsIjoiIiwicGxhbm5lZCI6IlNjaGVkdWxlZCIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJEYWxlayBNYXJ0aW4gKExJUykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8RGVwbG95IElUIHNlcnZpY2UifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVzaWduIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDItMTYiLCJlbmQiOiIyMDI2LTA1LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJEYWxlayBNYXJ0aW4gKExJUykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8RGVzaWduIElUIHNlcnZpY2UifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVzaWduIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA1LTE4IiwiZW5kIjoiMjAyNi0wOC0xNCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJXaWVoZSBBbGV4YW5kZXIgKENPQikiLCJsZWFkIjoiRGFsZWsgTWFydGluIChMSVMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfERlc2lnbiBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkRldmVsb3AgYW5kIGN1c3RvbWlzZSBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAyLTE2IiwiZW5kIjoiMjAyNi0wNS0xNSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJXaWVoZSBBbGV4YW5kZXIgKENPQikiLCJsZWFkIjoiRGFsZWsgTWFydGluIChMSVMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfERldmVsb3AgYW5kIGN1c3RvbWlzZSBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkRldmVsb3AgYW5kIGN1c3RvbWlzZSBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNS0wNS0yNiIsImVuZCI6IjIwMjUtMDgtMTUiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IkRhbGVrIE1hcnRpbiAoTElTKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxEZXZlbG9wIGFuZCBjdXN0b21pc2UgSVQgc2VydmljZSJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJNYW5hZyBJVCBzZXJ2aWNlIGNoYW5nZSIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMiIsImVuZCI6IjIwMjYtMDMtMTgiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKTtGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJXaWVoZSBBbGV4YW5kZXIgKENPQikiLCJsZWFkIjoiU2ludCBSYWNoZWwgKExCSCkiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8TWFuYWcgSVQgc2VydmljZSBjaGFuZ2UifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiTWFuYWcgSVQgc2VydmljZSBjaGFuZ2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTE1IiwiZW5kIjoiMjAyNi0wNi0zMCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCk7RnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IlNpbnQgUmFjaGVsIChMQkgpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfE1hbmFnIElUIHNlcnZpY2UgY2hhbmdlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6Ik1hbmFnZSBJVCBzZXJ2aWNlIHJlbGVhc2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDItMjAiLCJlbmQiOiIyMDI2LTA1LTA4IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCk7RnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IlNpbnQgUmFjaGVsIChMQkgpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfE1hbmFnZSBJVCBzZXJ2aWNlIHJlbGVhc2UifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiTWFuYWdlIElUIHNlcnZpY2UgcmVsZWFzZSIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDQtMTUiLCJlbmQiOiIyMDI2LTA2LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKTtGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJXaWVoZSBBbGV4YW5kZXIgKENPQikiLCJsZWFkIjoiU2ludCBSYWNoZWwgKExCSCkiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8TWFuYWdlIElUIHNlcnZpY2UgcmVsZWFzZSJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTItMjMiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUHJlaXNzIE1hdHRoaWFzIChMQkMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwzfFBlcmZvcm0gc29mdHdhcmUgc2VsZWN0aW9uIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IlBlcmZvcm0gc29mdHdhcmUgc2VsZWN0aW9uIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjUtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlByZWlzcyBNYXR0aGlhcyAoTEJDKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImx2bCI6IkwzIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDItMTYiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUHJlaXNzIE1hdHRoaWFzIChMQkMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwzfFBlcmZvcm0gc29mdHdhcmUgc2VsZWN0aW9uIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IlBlcmZvcm0gdmVuZG9yIHVzZSBjYXNlIHBpdGNoIGFuZCB1c2FiaWxpdHkgdGVzdCIsImx2bCI6Ikw0IiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTAtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUHJlaXNzIE1hdHRoaWFzIChMQkMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fFBlcmZvcm0gdmVuZG9yIHVzZSBjYXNlIHBpdGNoIGFuZCB1c2FiaWxpdHkgdGVzdCJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJSZWNvbW1lbmRhdGlvbiBhbmQgRUEgYXBwcm92YWwiLCJsdmwiOiJMNCIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI1LTEwLTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlByZWlzcyBNYXR0aGlhcyAoTEJDKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMNHxSZWNvbW1lbmRhdGlvbiBhbmQgRUEgYXBwcm92YWwifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiUmVjb3JkIGFuZCBwbGFuIGZ1bmN0aW9uYWwgcmVxdWlyZW1lbnRzIiwibHZsIjoiTDQiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJQcmVpc3MgTWF0dGhpYXMgKExCQykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDR8UmVjb3JkIGFuZCBwbGFuIGZ1bmN0aW9uYWwgcmVxdWlyZW1lbnRzIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IlRlc3QgYW5kIHZhbGlkYXRlIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDQtMTUiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJEYWxlayBNYXJ0aW4gKExJUykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8VGVzdCBhbmQgdmFsaWRhdGUgSVQgc2VydmljZSJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJUZXN0IGFuZCB2YWxpZGF0ZSBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNy0xNSIsImVuZCI6IjIwMjYtMDgtMzEiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IkRhbGVrIE1hcnRpbiAoTElTKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxUZXN0IGFuZCB2YWxpZGF0ZSBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IlZhbGlkYXRlIHN0cmF0ZWdpYyBmaXQiLCJsdmwiOiJMNCIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI1LTEwLTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlByZWlzcyBNYXR0aGlhcyAoTEJDKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMNHxWYWxpZGF0ZSBzdHJhdGVnaWMgZml0In0seyJwZyI6IkNQIiwibDEiOiJEZWxpdmVyIElUIHNlcnZpY2UiLCJwcm9jIjoiSGFuZGxlIElUIHNlcnZpY2Ugb3JkZXIiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDQtMDEiLCJlbmQiOiIyMDI2LTA2LTE3IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJTY2hudXJyZW5iZXJnZXIgQ2hyaXN0b3BoIChMSVMtTElOKSIsImxlYWQiOiJLdWVyc2NobmVyIFBoaWxpcHAgKExJUykiLCJub2RlSWQiOiJufENQfERlbGl2ZXIgSVQgc2VydmljZXxMMnxIYW5kbGUgSVQgc2VydmljZSBvcmRlciJ9LHsicGciOiJDUCIsImwxIjoiRGVsaXZlciBJVCBzZXJ2aWNlIiwicHJvYyI6IkhhbmRsZSBJVCBzZXJ2aWNlIG9yZGVyIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjYtMDYtMTUiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJTY2hudXJyZW5iZXJnZXIgQ2hyaXN0b3BoIChMSVMtTElOKSIsImxlYWQiOiJLdWVyc2NobmVyIFBoaWxpcHAgKExJUykiLCJub2RlSWQiOiJufENQfERlbGl2ZXIgSVQgc2VydmljZXxMMnxIYW5kbGUgSVQgc2VydmljZSBvcmRlciJ9LHsicGciOiJDUCIsImwxIjoiRGVsaXZlciBJVCBzZXJ2aWNlIiwicHJvYyI6Ik1hbmFnZSBJVCBzZXJ2aWNlIHByb3Zpc2lvbiByZXF1ZXN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNi0xNyIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiU2NobnVycmVuYmVyZ2VyIENocmlzdG9waCAoTElTLUxJTikiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxEZWxpdmVyIElUIHNlcnZpY2V8TDJ8TWFuYWdlIElUIHNlcnZpY2UgcHJvdmlzaW9uIHJlcXVlc3QifSx7InBnIjoiQ1AiLCJsMSI6IkRlbGl2ZXIgSVQgc2VydmljZSIsInByb2MiOiJNYW5hZ2UgSVQgc2VydmljZSBwcm92aXNpb24gcmVxdWVzdCIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDQtMDEiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiU2NobnVycmVuYmVyZ2VyIENocmlzdG9waCAoTElTLUxJTikiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxEZWxpdmVyIElUIHNlcnZpY2V8TDJ8TWFuYWdlIElUIHNlcnZpY2UgcHJvdmlzaW9uIHJlcXVlc3QifSx7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6IkhhbmRsZSBJVCBJbmNpZGVudCIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMyIsImVuZCI6IjIwMjYtMDMtMTkiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMDc1IiwiY29uc3VsdGFudCI6IlNjaHJvZWRlciBNaWNoYWVsIChMSVMpIiwibWFuYWdlciI6IlNpbnQgUmFjaGVsIChMQkgpIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58Q1B8UnVuIElUIHNlcnZpY2V8TDN8SGFuZGxlIElUIEluY2lkZW50In0seyJwZyI6IkNQIiwibDEiOiJSdW4gSVQgc2VydmljZSIsInByb2MiOiJIYW5kbGUgSVQgcHJvYmxlbSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMyIsImVuZCI6IjIwMjYtMDMtMTkiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMDc1IiwiY29uc3VsdGFudCI6IlNjaHJvZWRlciBNaWNoYWVsIChMSVMpIiwibWFuYWdlciI6IlNpbnQgUmFjaGVsIChMQkgpIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58Q1B8UnVuIElUIHNlcnZpY2V8TDN8SGFuZGxlIElUIHByb2JsZW0ifSx7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6IkhhbmRsZSBJVCBzZXJ2aWNlIHJlcXVlc3QiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDItMDIiLCJlbmQiOiIyMDI2LTAzLTE5IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJLdWVyc2NobmVyIFBoaWxpcHAgKExJUykiLCJub2RlSWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfEhhbmRsZSBJVCBzZXJ2aWNlIHJlcXVlc3QifSx7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6Ik1haW50YWluIENNREIiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMTQiLCJlbmQiOiIyMDI2LTA1LTIwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJTY2hyb2VkZXIgTWljaGFlbCAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJLcmV0eiBMdWNhcyAoQ09DLUNPVC1JVCkiLCJub2RlSWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfE1haW50YWluIENNREIifSx7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6Ik9wZXJhdGUgYW5kIG1haW50YWluIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMTIiLCJlbmQiOiIyMDI2LTA2LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3JldHogTHVjYXMgKENPQy1DT1QtSVQpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJSdW4gSVQgc2VydmljZSIsInByb2MiOiJPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNC0xNSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3JldHogTHVjYXMgKENPQy1DT1QtSVQpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJSdW4gSVQgc2VydmljZSIsInByb2MiOiJQcm92aWRlIElUIHNlcnZpY2Ugc3VwcG9ydCIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMiIsImVuZCI6IjIwMjYtMDMtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IlNjaHJvZWRlciBNaWNoYWVsIChMSVMpIiwibWFuYWdlciI6IlNpbnQgUmFjaGVsIChMQkgpIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58Q1B8UnVuIElUIHNlcnZpY2V8TDJ8UHJvdmlkZSBJVCBzZXJ2aWNlIHN1cHBvcnQifSx7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6IlByb3ZpZGUgSVQgc2VydmljZSBzdXBwb3J0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjYtMDYtMTUiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxQcm92aWRlIElUIHNlcnZpY2Ugc3VwcG9ydCJ9LHsicGciOiJDUCIsImwxIjoiUnVuIElUIHNlcnZpY2UiLCJwcm9jIjoiUnVuIElUIHNlcnZpY2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMTYiLCJlbmQiOiIyMDI2LTA2LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUyk7QsO2aG1lIE1hdHRoaWFzIChleHQuKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJPZXkgS2FpIChMSVMpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMXxSdW4gSVQgc2VydmljZSJ9LHsicGciOiJTUCIsImwxIjoiRW5zdXJlIEluZm9ybWF0aW9uIHNlY3VyaXR5IiwicHJvYyI6IlBlcmZvcm0gU2FhUyBTZWN1cml0eSBBc3Nlc3NtZW50IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTE5IiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKTtSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IkhlZmVsZSBNaWNoYWVsIChMSU4tTElTKSIsIm5vZGVJZCI6Im58U1B8RW5zdXJlIEluZm9ybWF0aW9uIHNlY3VyaXR5fEwyfFBlcmZvcm0gU2FhUyBTZWN1cml0eSBBc3Nlc3NtZW50In0seyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsInByb2MiOiJDbG9zZSBJVCBwcm9qZWN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTExLTExIiwiZW5kIjoiMjAyNS0xMi0xMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJNw7xobGJhY2hlciBDaHJpc3RpYW4gKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfENsb3NlIElUIHByb2plY3QifSx7InBnIjoiU1AiLCJsMSI6Ik1hbmFnZSBJVCBwcm9qZWN0IiwicHJvYyI6IkluaXRpYXRlIElUIHByb2plY3QiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTEiLCJlbmQiOiIyMDI1LTEyLTEwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6Ik3DvGhsYmFjaGVyIENocmlzdGlhbiAoTElTKSIsIm5vZGVJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8SW5pdGlhdGUgSVQgcHJvamVjdCJ9LHsicGciOiJTUCIsImwxIjoiTWFuYWdlIElUIHByb2plY3QiLCJwcm9jIjoiTWFuYWdlIElUIHByb2plY3QiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTEiLCJlbmQiOiIyMDI1LTEyLTEwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6Ik3DvGhsYmFjaGVyIENocmlzdGlhbiAoTElTKSIsIm5vZGVJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDF8TWFuYWdlIElUIHByb2plY3QifSx7InBnIjoiU1AiLCJsMSI6Ik1hbmFnZSBJVCBwcm9qZWN0IiwicHJvYyI6Ik1hbmFnZSBJVCBwcm9qZWN0IGNoYW5nZSByZXF1ZXN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTExLTExIiwiZW5kIjoiMjAyNS0xMi0xMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJNw7xobGJhY2hlciBDaHJpc3RpYW4gKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfE1hbmFnZSBJVCBwcm9qZWN0IGNoYW5nZSByZXF1ZXN0In0seyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsInByb2MiOiJQbGFuIElUIHByb2plY3QiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTEiLCJlbmQiOiIyMDI1LTEyLTEwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6Ik3DvGhsYmFjaGVyIENocmlzdGlhbiAoTElTKSIsIm5vZGVJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8UGxhbiBJVCBwcm9qZWN0In0seyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsInByb2MiOiJSZXNzb3VyY2VtYW5hZ2VtZW50IGZvciBJVCBwcm9qZWN0cyIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMS0xMSIsImVuZCI6IjIwMjUtMTItMTAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkZyYW5rIE1hcmVuIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiTcO8aGxiYWNoZXIgQ2hyaXN0aWFuIChMSVMpIiwibm9kZUlkIjoibnxTUHxNYW5hZ2UgSVQgcHJvamVjdHxMMnxSZXNzb3VyY2VtYW5hZ2VtZW50IGZvciBJVCBwcm9qZWN0cyJ9LHsicGciOiJTUCIsImwxIjoiTWFuYWdlIElUIHByb2plY3QiLCJwcm9jIjoiU3RlZXIgYW5kIGV4ZWN1dGUgSVQgcHJvamVjdCIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMS0xMSIsImVuZCI6IjIwMjUtMTItMTAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkZyYW5rIE1hcmVuIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiTcO8aGxiYWNoZXIgQ2hyaXN0aWFuIChMSVMpIiwibm9kZUlkIjoibnxTUHxNYW5hZ2UgSVQgcHJvamVjdHxMMnxTdGVlciBhbmQgZXhlY3V0ZSBJVCBwcm9qZWN0In0seyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgc291cmNpbmcgYW5kIHByb2N1cmVtZW50Iiw
3 | icHJvYyI6Ik1hbmFnZSBJVCBzb3VyY2luZyBhbmQgcHJvY3VyZW1lbnQiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDQtMjAiLCJlbmQiOiIyMDI2LTA0LTIyIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJTY2hvZWJlcmwgTG9yZW5hIChMQkgpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiRG9sZGVyZXIgV29sZmdhbmcgKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBzb3VyY2luZyBhbmQgcHJvY3VyZW1lbnR8TDF8TWFuYWdlIElUIHNvdXJjaW5nIGFuZCBwcm9jdXJlbWVudCJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiQXR0cmFjdCBhbmQgaGlyZSBlbXBsb3llZXMiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMDciLCJlbmQiOiIyMDI2LTAzLTE2IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDA1IiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiS2llc2V3ZXR0ZXIgSXZhbmEgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfEF0dHJhY3QgYW5kIGhpcmUgZW1wbG95ZWVzIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJBdHRyYWN0IGFuZCBoaXJlIGVtcGxveWVlcyIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjYtMDQtMDEiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiS2llc2V3ZXR0ZXIgSXZhbmEgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfEF0dHJhY3QgYW5kIGhpcmUgZW1wbG95ZWVzIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJBdHRyYWN0IGFuZCBoaXJlIGVtcGxveWVlcyIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDQtMDEiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiS2llc2V3ZXR0ZXIgSXZhbmEgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfEF0dHJhY3QgYW5kIGhpcmUgZW1wbG95ZWVzIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJDcmVhdGUsIGFwcHJvdmUgYW5kIHB1Ymxpc2ggdHJhaW5pbmdzIGZvciBJVCB3b3JrZm9yY2Ugd2l0aGluIElUIFRyYWluaW5nIENhdGFsb2d1ZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDQtMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDA1IiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiR3JhYm1haXIgTWVsYW5pZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8Q3JlYXRlLCBhcHByb3ZlIGFuZCBwdWJsaXNoIHRyYWluaW5ncyBmb3IgSVQgd29ya2ZvcmNlIHdpdGhpbiBJVCBUcmFpbmluZyBDYXRhbG9ndWUifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IkltcGxlbWVudCBhbmQgbWFpbnRhaW4gSVQgam9iIGFyY2hpdGVjdHVyZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiQW1lbGFuZyBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfEltcGxlbWVudCBhbmQgbWFpbnRhaW4gSVQgam9iIGFyY2hpdGVjdHVyZSJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wNS0zMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJBbWVsYW5nIE5pY29sZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSFI0SVQgc2VydmljZSBkZW1hbmQiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gQ09UIiwic3RhcnQiOiIyMDI2LTA2LTAxIiwiZW5kIjoiMjAyNi0wNi0zMCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJBbWVsYW5nIE5pY29sZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSFI0SVQgc2VydmljZSBkZW1hbmQiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA2LTAxIiwiZW5kIjoiMjAyNi0wNi0zMCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJBbWVsYW5nIE5pY29sZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSFI0SVQgc2VydmljZSBkZW1hbmQiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTFVTIiwic3RhcnQiOiIyMDI2LTA2LTAxIiwiZW5kIjoiMjAyNi0wNi0zMCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJBbWVsYW5nIE5pY29sZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSFI0SVQgc3RyYXRlZ3ksIGdvdmVybmFuZSBhbmQgZnJhbWV3b3JrIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6IkFtZWxhbmcgTmljb2xlIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxNYW5hZ2UgSFI0SVQgc3RyYXRlZ3ksIGdvdmVybmFuZSBhbmQgZnJhbWV3b3JrIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTE1IiwiZW5kIjoiMjAyNi0wMy0zMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJHcmFibWFpciBNZWxhbmllIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjYtMDctMDEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJHcmFibWFpciBNZWxhbmllIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjYtMDctMDEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJHcmFibWFpciBNZWxhbmllIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExVUyIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjYtMDctMDEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExVUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJHcmFibWFpciBNZWxhbmllIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSVQgc2tpbGxzIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTAxIiwiZW5kIjoiMjAyNi0xMi0zMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiR3JhYm1haXIgTWVsYW5pZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIElUIHNraWxscyJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFuYWdlIElUIHNraWxscyIsImx2bCI6IkwzIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjctMDEtMDEiLCJlbmQiOiIyMDI3LTA2LTMwIiwiYWN0dWFsIjoiIiwicGxhbm5lZCI6IlNjaGVkdWxlZCIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJHcmFibWFpciBNZWxhbmllIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgc2tpbGxzIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSVQgc2tpbGxzIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNy0wMS0wMSIsImVuZCI6IjIwMjctMDYtMzAiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBza2lsbHMifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hbmFnZSBJVCBza2lsbHMiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTFVTIiwic3RhcnQiOiIyMDI3LTAxLTAxIiwiZW5kIjoiMjAyNy0wNi0zMCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiR3JhYm1haXIgTWVsYW5pZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIElUIHNraWxscyJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFwcGluZyBhbmQgZXZhbHVhdGUgSVQgY2FyZWVyIGxldmVsIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNy0wMS0wMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiR3JhYm1haXIgTWVsYW5pZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFwcGluZyBhbmQgZXZhbHVhdGUgSVQgY2FyZWVyIGxldmVsIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJPbmJvYXJkIG5ldyBJVCBlbXBsb3llZSBhbmQgbWFuYWdlciIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjYtMDQtMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDA1IiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xPbmJvYXJkIG5ldyBJVCBlbXBsb3llZSBhbmQgbWFuYWdlciJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiUGVyZm9ybSBhY3RpdmUgc291cmNpbmciLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJLaWVzZXdldHRlciBJdmFuYSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UGVyZm9ybSBhY3RpdmUgc291cmNpbmcifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IlBlcmZvcm0gYWN0aXZlIHNvdXJjaW5nIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wMy0wMSIsImVuZCI6IjIwMjYtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJLaWVzZXdldHRlciBJdmFuYSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UGVyZm9ybSBhY3RpdmUgc291cmNpbmcifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IlBlcmZvcm0gb25ib2FyZGluZyIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjYtMDQtMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IiIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8UGVyZm9ybSBvbmJvYXJkaW5nIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJQbGFuIElUIHdvcmtmb3JjZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjUtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJBbWVsYW5nIE5pY29sZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UGxhbiBJVCB3b3JrZm9yY2UifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IlBsYW4gSVQgd29ya2ZvcmNlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wMS0wMSIsImVuZCI6IjIwMjYtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6IkFtZWxhbmcgTmljb2xlIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xQbGFuIElUIHdvcmtmb3JjZSJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiUHJlLWJvYXJkIG5ldyBJVCBlbXBsb3llZSBhbmQgbWFuYWdlciIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjYtMDQtMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IiIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UHJlLWJvYXJkIG5ldyBJVCBlbXBsb3llZSBhbmQgbWFuYWdlciJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI1LTEwLTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiQW1lbGFuZyBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwxfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJSZWNydWl0IGVtcGxveWVlcyBhbmQgbWFuYWdlcnMiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwMjUiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJLaWVzZXdldHRlciBJdmFuYSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UmVjcnVpdCBlbXBsb3llZXMgYW5kIG1hbmFnZXJzIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJSZWNydWl0IGVtcGxveWVlcyBhbmQgbWFuYWdlcnMiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTAzLTAxIiwiZW5kIjoiMjAyNi0xMi0zMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IktpZXNld2V0dGVyIEl2YW5hIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xSZWNydWl0IGVtcGxveWVlcyBhbmQgbWFuYWdlcnMifSx7InBnIjoiU1AiLCJsMSI6IkVuc3VyZSBwZXJmb3JtYW5jZSBhbmQgY29uZm9ybWFuY2Ugb2YgSVQgc2VydmljZXMiLCJwcm9jIjoiRW5zdXJlIHBlcmZvcm1hbmNlIGFuZCBjb25mb3JtYW5jZSBvZiBJVCBzZXJ2aWNlcyIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wNC0xNSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJTY2hyb2VkZXIgTWljaGFlbCAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiI/Iiwibm9kZUlkIjoibnxTUHxFbnN1cmUgcGVyZm9ybWFuY2UgYW5kIGNvbmZvcm1hbmNlIG9mIElUIHNlcnZpY2VzfEwxfEVuc3VyZSBwZXJmb3JtYW5jZSBhbmQgY29uZm9ybWFuY2Ugb2YgSVQgc2VydmljZXMifSx7InBnIjoiU1AiLCJsMSI6Ik1hbmFnZSBJVCBrbm93bGVkZ2UiLCJwcm9jIjoiTWFuYWdlIElUIGtub3dsZWRnZSIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0yMCIsImVuZCI6IjIwMjYtMDItMjUiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IlNjaHJvZWRlciBNaWNoYWVsIChMSVMpIiwibWFuYWdlciI6IlNpbnQgUmFjaGVsIChMQkgpIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58U1B8TWFuYWdlIElUIGtub3dsZWRnZXxMMXxNYW5hZ2UgSVQga25vd2xlZGdlIn0seyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQga25vd2xlZGdlIiwicHJvYyI6Ik1hbmFnZSBJVCBrbm93bGVkZ2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTE1IiwiZW5kIjoiMjAyNi0wNi0zMCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJTY2hyb2VkZXIgTWljaGFlbCAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJLdWVyc2NobmVyIFBoaWxpcHAgKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBrbm93bGVkZ2V8TDF8TWFuYWdlIElUIGtub3dsZWRnZSJ9XSwibm9kZXMiOlt7ImlkIjoicGd8TVAiLCJ0eXBlIjoicGciLCJwZyI6Ik1QIiwibHZsIjoiTDAiLCJuYW1lIjoiTVAiLCJhc3NvY0wxIjoiIiwiaW5kZW50IjowLCJzb3J0S2V5IjowLCJwYXJlbnRJZCI6bnVsbCwiY2hpbGRyZW4iOlsibnxNUHxNYW5hZ2UgSVQgc3RyYXRlZ3l8TDF8TWFuYWdlIElUIHN0cmF0ZWd5IiwibnxNUHxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmt8TDF8TWFuYWdlIElUIGdvdmVybmFuY2UgZnJhbWV3b3JrIiwibnxNUHxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmV8TDF8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwibnxNUHxNYW5hZ2UgSVQgcG9ydGZvbGlvfEwxfE1hbmFnZSBJVCBwb3J0Zm9saW8iLCJufE1QfE1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzfEwxfE1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzIiwibnxNUHxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwc3xMMXxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyIsIm58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMXxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDF8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIl0sIml0ZW1zIjpbXX0seyJpZCI6Im58TVB8TWFuYWdlIElUIHN0cmF0ZWd5fEwxfE1hbmFnZSBJVCBzdHJhdGVneSIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwxIiwibmFtZSI6Ik1hbmFnZSBJVCBzdHJhdGVneSIsImFzc29jTDEiOiJNYW5hZ2UgSVQgc3RyYXRlZ3kiLCJpbmRlbnQiOjEsInNvcnRLZXkiOjEwMDEsInBhcmVudElkIjoicGd8TVAiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgc3RyYXRlZ3kiLCJwcm9jIjoiTWFuYWdlIElUIHN0cmF0ZWd5IiwibHZsIjoiTDEiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAyLTAyIiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiS3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJGZWxkZXIgTWF4IChMTEkpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgc3RyYXRlZ3l8TDF8TWFuYWdlIElUIHN0cmF0ZWd5In0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgc3RyYXRlZ3kiLCJwcm9jIjoiTWFuYWdlIElUIHN0cmF0ZWd5IiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNS0xNCIsImVuZCI6IjIwMjYtMDctMjkiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLcmVpcyBBbmRyZWFzIChMTEkpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkZlbGRlciBNYXggKExMSSkiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBzdHJhdGVneXxMMXxNYW5hZ2UgSVQgc3RyYXRlZ3kifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29ya3xMMnxNYWludGFpbiBJVCBnbG9zc2FyeSIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwyIiwibmFtZSI6Ik1haW50YWluIElUIGdsb3NzYXJ5IiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29yayIsImluZGVudCI6Miwic29ydEtleSI6MTAwMiwicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29ya3xMMXxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsiLCJwcm9jIjoiTWFpbnRhaW4gSVQgZ2xvc3NhcnkiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTAxLTA3IiwiZW5kIjoiMjAyNi0wMS0xNyIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJGZWxkZXIgTWF4IChMTEkpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmt8TDJ8TWFpbnRhaW4gSVQgZ2xvc3NhcnkifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29ya3xMMXxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMSIsIm5hbWUiOiJNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsiLCJhc3NvY0wxIjoiTWFuYWdlIElUIGdvdmVybmFuY2UgZnJhbWV3b3JrIiwiaW5kZW50IjoxLCJzb3J0S2V5IjoxMDAyLCJwYXJlbnRJZCI6InBnfE1QIiwiY2hpbGRyZW4iOlsibnxNUHxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmt8TDJ8TWFpbnRhaW4gSVQgZ2xvc3NhcnkiXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBnb3Zlcm5hbmNlIGZyYW1ld29yayIsInByb2MiOiJNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDMtMTYiLCJlbmQiOiIyMDI2LTA1LTIxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCk7S3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJGZWxkZXIgTWF4IChMTEkpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmt8TDF8TWFuYWdlIElUIGdvdmVybmFuY2UgZnJhbWV3b3JrIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmsiLCJwcm9jIjoiTWFuYWdlIElUIGdvdmVybmFuY2UgZnJhbWV3b3JrIiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNS0yNSIsImVuZCI6IjIwMjYtMDgtMzEiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCk7S3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJGZWxkZXIgTWF4IChMTEkpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgZ292ZXJuYW5jZSBmcmFtZXdvcmt8TDF8TWFuYWdlIElUIGdvdmVybmFuY2UgZnJhbWV3b3JrIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmV8TDF8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDEiLCJuYW1lIjoiTWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwiYXNzb2NMMSI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsImluZGVudCI6MSwic29ydEtleSI6MTAwMywicGFyZW50SWQiOiJwZ3xNUCIsImNoaWxkcmVuIjpbIm58TVB8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlfEwyfFN0cmF0ZWdpYyBhcmNoaXRlY3R1cmUgcHJvY2VzcyJdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwicHJvYyI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMi0yMyIsImVuZCI6IjIwMjYtMDUtMDgiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik51c3NiYXVtZXIgRmxvcmlhbiAoTEJDKSIsImxlYWQiOiJHdWpyYWwgUGFydGggKENPQi1DT1QtSVQpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmV8TDF8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIn0seyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUiLCJwcm9jIjoiTWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNi0wNS0wOCIsImVuZCI6IjIwMjYtMDUtMTEiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiIiLCJtYW5hZ2VyIjoiIiwibGVhZCI6IiIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlfEwxfE1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIiwicHJvYyI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsImx2bCI6IkwxIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDUtMDgiLCJlbmQiOiIyMDI2LTA3LTE2IiwiYWN0dWFsIjoiIiwicGxhbm5lZCI6IlNjaGVkdWxlZCIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiIiwibWFuYWdlciI6IiIsImxlYWQiOiIiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZXxMMXxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsInByb2MiOiJNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTFVTIiwic3RhcnQiOiIyMDI2LTA1LTA4IiwiZW5kIjoiMjAyNi0wNS0xMSIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IiIsIm1hbmFnZXIiOiIiLCJsZWFkIjoiIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmV8TDF8TWFuYWdlIGVudGVycHJpc2UgYXJjaGl0ZWN0dXJlIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmV8TDJ8U3RyYXRlZ2ljIGFyY2hpdGVjdHVyZSBwcm9jZXNzIiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDIiLCJuYW1lIjoiU3RyYXRlZ2ljIGFyY2hpdGVjdHVyZSBwcm9jZXNzIiwiYXNzb2NMMSI6Ik1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZSIsImluZGVudCI6Miwic29ydEtleSI6MTAwMywicGFyZW50SWQiOiJufE1QfE1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZXxMMXxNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgZW50ZXJwcmlzZSBhcmNoaXRlY3R1cmUiLCJwcm9jIjoiU3RyYXRlZ2ljIGFyY2hpdGVjdHVyZSBwcm9jZXNzIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAyLTIzIiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTnVzc2JhdW1lciBGbG9yaWFuIChMQkMpIiwibGVhZCI6Ikd1anJhbCBQYXJ0aCAoQ09CLUNPVC1JVCkiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBlbnRlcnByaXNlIGFyY2hpdGVjdHVyZXxMMnxTdHJhdGVnaWMgYXJjaGl0ZWN0dXJlIHByb2Nlc3MifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBwb3J0Zm9saW98TDF8TWFuYWdlIElUIHBvcnRmb2xpbyIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwxIiwibmFtZSI6Ik1hbmFnZSBJVCBwb3J0Zm9saW8iLCJhc3NvY0wxIjoiTWFuYWdlIElUIHBvcnRmb2xpbyIsImluZGVudCI6MSwic29ydEtleSI6MTAwNCwicGFyZW50SWQiOiJwZ3xNUCIsImNoaWxkcmVuIjpbIm58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMnxNYW5hZ2UgSVQgcHJvamVjdCBwb3J0Zm9saW8iLCJufE1QfE1hbmFnZSBJVCBwb3J0Zm9saW98TDJ8TWFuYWdlIElUIHNlcnZpY2UgcG9ydGZvbGlvIl0sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcG9ydGZvbGlvIiwicHJvYyI6Ik1hbmFnZSBJVCBwb3J0Zm9saW8iLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTEiLCJlbmQiOiIyMDI2LTAxLTI5IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKTtLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiIiwibGVhZCI6IiIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMXxNYW5hZ2UgSVQgcG9ydGZvbGlvIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgcG9ydGZvbGlvfEwyfE1hbmFnZSBJVCBwcm9qZWN0IHBvcnRmb2xpbyIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwyIiwibmFtZSI6Ik1hbmFnZSBJVCBwcm9qZWN0IHBvcnRmb2xpbyIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcG9ydGZvbGlvIiwiaW5kZW50IjoyLCJzb3J0S2V5IjoxMDA0LCJwYXJlbnRJZCI6Im58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMXxNYW5hZ2UgSVQgcG9ydGZvbGlvIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHBvcnRmb2xpbyIsInByb2MiOiJNYW5hZ2UgSVQgcHJvamVjdCBwb3J0Zm9saW8iLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTAiLCJlbmQiOiIyMDI1LTEyLTEwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6Ik3DvGhsYmFjaGVyIENocmlzdGlhbiAoTEl
4 | TKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMnxNYW5hZ2UgSVQgcHJvamVjdCBwb3J0Zm9saW8ifSx7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwb3J0Zm9saW8iLCJwcm9jIjoiTWFuYWdlIElUIHByb2plY3QgcG9ydGZvbGlvIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wMi0wMSIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJNw7xobGJhY2hlciBDaHJpc3RpYW4gKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwb3J0Zm9saW98TDJ8TWFuYWdlIElUIHByb2plY3QgcG9ydGZvbGlvIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgcG9ydGZvbGlvfEwyfE1hbmFnZSBJVCBzZXJ2aWNlIHBvcnRmb2xpbyIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwyIiwibmFtZSI6Ik1hbmFnZSBJVCBzZXJ2aWNlIHBvcnRmb2xpbyIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcG9ydGZvbGlvIiwiaW5kZW50IjoyLCJzb3J0S2V5IjoxMDA0LCJwYXJlbnRJZCI6Im58TVB8TWFuYWdlIElUIHBvcnRmb2xpb3xMMXxNYW5hZ2UgSVQgcG9ydGZvbGlvIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHBvcnRmb2xpbyIsInByb2MiOiJNYW5hZ2UgSVQgc2VydmljZSBwb3J0Zm9saW8iLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDQtMDEiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKTtLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiQ2VpbGlhIFJvc2VyIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcG9ydGZvbGlvfEwyfE1hbmFnZSBJVCBzZXJ2aWNlIHBvcnRmb2xpbyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHBvcnRmb2xpbyIsInByb2MiOiJNYW5hZ2UgSVQgc2VydmljZSBwb3J0Zm9saW8iLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA2LTE1IiwiZW5kIjoiMjAyNi0wOS0wOCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkZyYW5rIE1hcmVuIChMSVMpO0t1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJDZWlsaWEgUm9zZXIgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwb3J0Zm9saW98TDJ8TWFuYWdlIElUIHNlcnZpY2UgcG9ydGZvbGlvIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgYW5kIGNvbnRyb2wgSVQgZmluYW5jaWFsc3xMMXxNYW5hZ2UgYW5kIGNvbnRyb2wgSVQgZmluYW5jaWFscyIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwxIiwibmFtZSI6Ik1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzIiwiYXNzb2NMMSI6Ik1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzIiwiaW5kZW50IjoxLCJzb3J0S2V5IjoxMDA1LCJwYXJlbnRJZCI6InBnfE1QIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJwcm9jIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMTUiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJIeW5layBUb2JpYXMgKExJUyk7S3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNb3NlciBNYXJpbyAoTElTLUxBSCkiLCJsZWFkIjoiRnJhbmsgTmljb2xlIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgYW5kIGNvbnRyb2wgSVQgZmluYW5jaWFsc3xMMXxNYW5hZ2UgYW5kIGNvbnRyb2wgSVQgZmluYW5jaWFscyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJwcm9jIjoiTWFuYWdlIGFuZCBjb250cm9sIElUIGZpbmFuY2lhbHMiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA1LTAxIiwiZW5kIjoiMjAyNi0wNy0zMSIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikh5bmVrIFRvYmlhcyAoTElTKTtLcmVpcyBBbmRyZWFzIChMTEkpIiwibWFuYWdlciI6Ik1vc2VyIE1hcmlvIChMSVMtTEFIKSIsImxlYWQiOiJGcmFuayBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzfEwxfE1hbmFnZSBhbmQgY29udHJvbCBJVCBmaW5hbmNpYWxzIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwc3xMMXxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwxIiwibmFtZSI6Ik1hbmFnZSBJVCBzdGFrZWhvbGRlciByZWxhdGlvbnNoaXBzIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBzdGFrZWhvbGRlciByZWxhdGlvbnNoaXBzIiwiaW5kZW50IjoxLCJzb3J0S2V5IjoxMDA2LCJwYXJlbnRJZCI6InBnfE1QIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHN0YWtlaG9sZGVyIHJlbGF0aW9uc2hpcHMiLCJwcm9jIjoiTWFuYWdlIElUIHN0YWtlaG9sZGVyIHJlbGF0aW9uc2hpcHMiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDQtMDEiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3JlaXMgQW5kcmVhcyAoTExJKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJGZWxkZXIgTWF4IChMTEkpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwc3xMMXxNYW5hZ2UgSVQgc3Rha2Vob2xkZXIgcmVsYXRpb25zaGlwcyJ9LHsicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHN0YWtlaG9sZGVyIHJlbGF0aW9uc2hpcHMiLCJwcm9jIjoiTWFuYWdlIElUIHN0YWtlaG9sZGVyIHJlbGF0aW9uc2hpcHMiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTEwLTE1IiwiZW5kIjoiMjAyNi0xMi0yMyIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IktyZWlzIEFuZHJlYXMgKExMSSkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiRmVsZGVyIE1heCAoTExJKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHN0YWtlaG9sZGVyIHJlbGF0aW9uc2hpcHN8TDF8TWFuYWdlIElUIHN0YWtlaG9sZGVyIHJlbGF0aW9uc2hpcHMifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8QW5hbHlzZSBwcm9jZXNzIiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDMiLCJuYW1lIjoiQW5hbHlzZSBwcm9jZXNzIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjEwMDcsInBhcmVudElkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwyfFBlcmZvcm0gb3BlcmF0aW9uYWwgcHJvY2VzcyBtYW5hZ2VtZW50IChWIDIuMCkiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6IkFuYWx5c2UgcHJvY2VzcyIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTAtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xBbmFseXNlIHByb2Nlc3MifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8RGV2ZWxvcCBhbmQgbWFpbnRhaW4gSVQgQlBNIGZyYW1ld29yayIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwyIiwibmFtZSI6IkRldmVsb3AgYW5kIG1haW50YWluIElUIEJQTSBmcmFtZXdvcmsiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsImluZGVudCI6Miwic29ydEtleSI6MTAwNywicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDF8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJwcm9jIjoiRGV2ZWxvcCBhbmQgbWFpbnRhaW4gSVQgQlBNIGZyYW1ld29yayIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0wOC0wNCIsImVuZCI6IjIwMjUtMDgtMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMnxEZXZlbG9wIGFuZCBtYWludGFpbiBJVCBCUE0gZnJhbWV3b3JrIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwzfEVsYWJvcmF0ZSB0by1iZSBwcm9jZXNzIChWIDIuMCkiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMyIsIm5hbWUiOiJFbGFib3JhdGUgdG8tYmUgcHJvY2VzcyAoViAyLjApIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjEwMDcsInBhcmVudElkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwyfFBlcmZvcm0gb3BlcmF0aW9uYWwgcHJvY2VzcyBtYW5hZ2VtZW50IChWIDIuMCkiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6IkVsYWJvcmF0ZSB0by1iZSBwcm9jZXNzIChWIDIuMCkiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMTIiLCJlbmQiOiIyMDI2LTA1LTMxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwMjUiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwzfEVsYWJvcmF0ZSB0by1iZSBwcm9jZXNzIChWIDIuMCkifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8SWRlbnRpZnkgcHJvY2VzcyBhbmQgZGV0ZXJtaW5lIGdvYWxzIChWIDIuMCkiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMyIsIm5hbWUiOiJJZGVudGlmeSBwcm9jZXNzIGFuZCBkZXRlcm1pbmUgZ29hbHMgKFYgMi4wKSIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwiaW5kZW50IjozLCJzb3J0S2V5IjoxMDA3LCJwYXJlbnRJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMnxQZXJmb3JtIG9wZXJhdGlvbmFsIHByb2Nlc3MgbWFuYWdlbWVudCAoViAyLjApIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsInByb2MiOiJJZGVudGlmeSBwcm9jZXNzIGFuZCBkZXRlcm1pbmUgZ29hbHMgKFYgMi4wKSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMiIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8SWRlbnRpZnkgcHJvY2VzcyBhbmQgZGV0ZXJtaW5lIGdvYWxzIChWIDIuMCkifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8SW1wbGVtZW50IHByb2Nlc3MgKFYgMi4wKSIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwzIiwibmFtZSI6IkltcGxlbWVudCBwcm9jZXNzIChWIDIuMCkiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsImluZGVudCI6Mywic29ydEtleSI6MTAwNywicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8UGVyZm9ybSBvcGVyYXRpb25hbCBwcm9jZXNzIG1hbmFnZW1lbnQgKFYgMi4wKSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJwcm9jIjoiSW1wbGVtZW50IHByb2Nlc3MgKFYgMi4wKSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMiIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8SW1wbGVtZW50IHByb2Nlc3MgKFYgMi4wKSJ9XX0seyJpZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMnxNYW5hZ2UgY29udGludW91cyBpbXByb3ZlbWVudCIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwyIiwibmFtZSI6Ik1hbmFnZSBjb250aW51b3VzIGltcHJvdmVtZW50IiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjEwMDcsInBhcmVudElkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwxfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6Ik1hbmFnZSBjb250aW51b3VzIGltcHJvdmVtZW50IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wMS0zMCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKTtCw7ZobWUgTWF0dGhpYXMgKGV4dC4pIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMnxNYW5hZ2UgY29udGludW91cyBpbXByb3ZlbWVudCJ9XX0seyJpZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMMXxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDEiLCJuYW1lIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwiaW5kZW50IjoxLCJzb3J0S2V5IjoxMDA3LCJwYXJlbnRJZCI6InBnfE1QIiwiY2hpbGRyZW4iOlsibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwyfERldmVsb3AgYW5kIG1haW50YWluIElUIEJQTSBmcmFtZXdvcmsiLCJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8TWFuYWdlIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8UGVyZm9ybSBvcGVyYXRpb25hbCBwcm9jZXNzIG1hbmFnZW1lbnQgKFYgMi4wKSJdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsInByb2MiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwibHZsIjoiTDEiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwxfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDN8UGVyZm9ybSBhbmQgbWVhc3VyZSBwcm9jZXNzIiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDMiLCJuYW1lIjoiUGVyZm9ybSBhbmQgbWVhc3VyZSBwcm9jZXNzIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjEwMDcsInBhcmVudElkIjoibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwyfFBlcmZvcm0gb3BlcmF0aW9uYWwgcHJvY2VzcyBtYW5hZ2VtZW50IChWIDIuMCkiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50IiwicHJvYyI6IlBlcmZvcm0gYW5kIG1lYXN1cmUgcHJvY2VzcyIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTAtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xQZXJmb3JtIGFuZCBtZWFzdXJlIHByb2Nlc3MifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8UGVyZm9ybSBvcGVyYXRpb25hbCBwcm9jZXNzIG1hbmFnZW1lbnQgKFYgMi4wKSIsInR5cGUiOiJwcm9jIiwicGciOiJNUCIsImx2bCI6IkwyIiwibmFtZSI6IlBlcmZvcm0gb3BlcmF0aW9uYWwgcHJvY2VzcyBtYW5hZ2VtZW50IChWIDIuMCkiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsImluZGVudCI6Miwic29ydEtleSI6MTAwNywicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDF8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsImNoaWxkcmVuIjpbIm58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xJZGVudGlmeSBwcm9jZXNzIGFuZCBkZXRlcm1pbmUgZ29hbHMgKFYgMi4wKSIsIm58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xFbGFib3JhdGUgdG8tYmUgcHJvY2VzcyAoViAyLjApIiwibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwzfFBsYW4gcHJvY2VzcyBleGVjdXRpb24gKFYgMi4wKSIsIm58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xJbXBsZW1lbnQgcHJvY2VzcyAoViAyLjApIiwibnxNUHxNYW5hZ2UgSVQgcHJvY2Vzc2VzIGFuZCBjb250aW51b3VzIGltcHJvdmVtZW50fEwzfFBlcmZvcm0gYW5kIG1lYXN1cmUgcHJvY2VzcyIsIm58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xBbmFseXNlIHByb2Nlc3MiXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJwcm9jIjoiUGVyZm9ybSBvcGVyYXRpb25hbCBwcm9jZXNzIG1hbmFnZW1lbnQgKFYgMi4wKSIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0xMiIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8UGVyZm9ybSBvcGVyYXRpb25hbCBwcm9jZXNzIG1hbmFnZW1lbnQgKFYgMi4wKSJ9XX0seyJpZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xQbGFuIHByb2Nlc3MgZXhlY3V0aW9uIChWIDIuMCkiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMyIsIm5hbWUiOiJQbGFuIHByb2Nlc3MgZXhlY3V0aW9uIChWIDIuMCkiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudCIsImluZGVudCI6Mywic29ydEtleSI6MTAwNywicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnR8TDJ8UGVyZm9ybSBvcGVyYXRpb25hbCBwcm9jZXNzIG1hbmFnZW1lbnQgKFYgMi4wKSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCBwcm9jZXNzZXMgYW5kIGNvbnRpbnVvdXMgaW1wcm92ZW1lbnQiLCJwcm9jIjoiUGxhbiBwcm9jZXNzIGV4ZWN1dGlvbiAoViAyLjApIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEyIiwiZW5kIjoiMjAyNi0wNS0zMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHByb2Nlc3NlcyBhbmQgY29udGludW91cyBpbXByb3ZlbWVudHxMM3xQbGFuIHByb2Nlc3MgZXhlY3V0aW9uIChWIDIuMCkifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xEQy9EQ0MvTVNDIElULWNvbXBsaWFuY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMyIsIm5hbWUiOiJEQy9EQ0MvTVNDIElULWNvbXBsaWFuY2UiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjoxMDA4LCJwYXJlbnRJZCI6Im58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwyfE1hbmFnZSBJVCBjb21wbGlhbmNlIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIiwicHJvYyI6IkRDL0RDQy9NU0MgSVQtY29tcGxpYW5jZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDktMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiTXVlc2tlbnMgSmFuIChMSE8pIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8REMvRENDL01TQyBJVC1jb21wbGlhbmNlIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8SW1wbGVtZW50IHRvIGltcHJvdmUiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMyIsIm5hbWUiOiJJbXBsZW1lbnQgdG8gaW1wcm92ZSIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjEwMDgsInBhcmVudElkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDJ8TWFuYWdlIElUIGNvbXBsaWFuY2UiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6Ik1QIiwibDEiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJwcm9jIjoiSW1wbGVtZW50IHRvIGltcHJvdmUiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI2LTA5LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwMjUiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJNb25uaWVyIE11cmllbGxlIChMRUMpIiwibGVhZCI6Ik11ZXNrZW5zIEphbiAoTEhPKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwzfEltcGxlbWVudCB0byBpbXByb3ZlIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDJ8TWFuYWdlIElUIGNvbXBsaWFuY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMiIsIm5hbWUiOiJNYW5hZ2UgSVQgY29tcGxpYW5jZSIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjEwMDgsInBhcmVudElkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDF8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIiwiY2hpbGRyZW4iOlsibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8TW9uaXRvciB0byBkZWxlZ2F0ZSIsIm58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwzfFJlcXVpcmVtZW50cyB0byBtZWFzdXJlcyIsIm58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwzfEltcGxlbWVudCB0byBpbXByb3ZlIiwibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8TWFuYWdlIElULUMgc3RyYXRlZ3kiLCJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xNYW5hZ2UgSVQtQyBmcmFtZXdvcmsiLCJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xEQy9EQ0MvTVNDIElULWNvbXBsaWFuY2UiXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNYW5hZ2UgSVQgY29tcGxpYW5jZSIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDktMzAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAuMDAyNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiTXVlc2tlbnMgSmFuIChMSE8pIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDJ8TWFuYWdlIElUIGNvbXBsaWFuY2UifV19LHsiaWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMMXxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMSIsIm5hbWUiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIiwiaW5kZW50IjoxLCJzb3J0S2V5IjoxMDA4LCJwYXJlbnRJZCI6InBnfE1QIiwiY2hpbGRyZW4iOlsibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDJ8TWFuYWdlIElUIGNvbXBsaWFuY2UiXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI1LTEwLTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik1vbm5pZXIgTXVyaWVsbGUgKExFQykiLCJsZWFkIjoiTXVlc2tlbnMgSmFuIChMSE8pIiwibm9kZUlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDF8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8TWFuYWdlIElULUMgZnJhbWV3b3JrIiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDMiLCJuYW1lIjoiTWFuYWdlIElULUMgZnJhbWV3b3JrIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsImluZGVudCI6Mywic29ydEtleSI6MTAwOCwicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMMnxNYW5hZ2UgSVQgY29tcGxpYW5jZSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNYW5hZ2UgSVQtQyBmcmFtZXdvcmsiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI2LTA5LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwMjUiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJNb25uaWVyIE11cmllbGxlIChMRUMpIiwibGVhZCI6Ik11ZXNrZW5zIEphbiAoTEhPKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwzfE1hbmFnZSBJVC1DIGZyYW1ld29yayJ9XX0seyJpZCI6Im58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwzfE1hbmFnZSBJVC1DIHN0cmF0ZWd5IiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDMiLCJuYW1lIjoiTWFuYWdlIElULUMgc3RyYXRlZ3kiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjoxMDA4LCJwYXJlbnRJZCI6Im58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwyfE1hbmFnZSBJVCBjb21wbGlhbmNlIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJNUCIsImwxIjoiTWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlIiwicHJvYyI6Ik1hbmFnZSBJVC1DIHN0cmF0ZWd5IiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wOS0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTW9ubmllciBNdXJpZWxsZSAoTEVDKSIsImxlYWQiOiJNdWVza2VucyBKYW4gKExITykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xNYW5hZ2UgSVQtQyBzdHJhdGVneSJ9XX0seyJpZCI6Im58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwzfE1vbml0b3IgdG8gZGVsZWdhdGUiLCJ0eXBlIjoicHJvYyIsInBnIjoiTVAiLCJsdmwiOiJMMyIsIm5hbWUiOiJNb25pdG9yIHRvIGRlbGVnYXRlIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsImluZGVudCI6Mywic29ydEtleSI6MTAwOCwicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMMnxNYW5hZ2UgSVQgY29tcGxpYW5jZSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJNb25pdG9yIHRvIGRlbGVnYXRlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wOS0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTW9ubmllciBNdXJpZWxsZSAoTEVDKSIsImxlYWQiOiJNdWVza2VucyBKYW4gKExITykiLCJub2RlSWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMM3xNb25pdG9yIHRvIGRlbGVnYXRlIn1dfSx7ImlkIjoibnxNUHxNYW5hZ2UgSVQgcmlza3MgYW5kIGNvbXBsaWFuY2V8TDN8UmVxdWlyZW1lbnRzIHRvIG1lYXN1cmVzIiwidHlwZSI6InByb2MiLCJwZyI6Ik1QIiwibHZsIjoiTDMiLCJuYW1lIjoiUmVxdWlyZW1lbnRzIHRvIG1lYXN1cmVzIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsImluZGVudCI6Mywic29ydEtleSI6MTAwOCwicGFyZW50SWQiOiJufE1QfE1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZXxMMnxNYW5hZ2UgSVQgY29tcGxpYW5jZSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiTVAiLCJsMSI6Ik1hbmFnZSBJVCByaXNrcyBhbmQgY29tcGxpYW5jZSIsInByb2MiOiJSZXF1aXJlbWVudHMgdG8gbWVhc3VyZXMiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMDEiLCJlbmQiOiIyMDI2LTA5LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwMjUiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJNb25uaWVyIE11cmllbGxlIChMRUMpIiwibGVhZCI6Ik11ZXNrZW5zIEphbiAoTEhPKSIsIm5vZGVJZCI6Im58TVB8TWFuYWdlIElUIHJpc2tzIGFuZCBjb21wbGlhbmNlfEwzfFJlcXVpcmVtZW50cyB0byBtZWFzdXJlcyJ9XX0seyJpZCI6InBnfENQIiwidHlwZSI6InBnIiwicGciOiJDUCIsImx2bCI6IkwwIiwibmFtZSI6IkNQIiwiYXNzb2NMMSI6IiIsImluZGVudCI6MCwic29ydEtleSI6MCwicGFyZW50SWQiOm51bGwsImNoaWxkcmVuIjpbIm58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwxfFBsYW4gSVQgc2VydmljZSIsIm58Q1B8QnVpbGQgSVQgU2VydmljZXxMMXxCdWlsZCBJVCBTZXJ2aWNlIiwibnxDUHxEZWxpdmVyIElUIHNlcnZpY2V8TDF8RGVsaXZlciBJVCBzZXJ2aWNlIiwibnxDUHxSdW4gSVQgc2VydmljZXxMMXxSdW4gSVQgc2VydmljZSJdLCJpdGVtcyI6W119LHsiaWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMM3xBbmFseXNlIGFyY2hpdGVjdHVyZSBpbXBhY3QiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMyIsIm5hbWUiOiJBbmFseXNlIGFyY2hpdGVjdHVyZSBpbXBhY3QiLCJhc3NvY0wxIjoiUGxhbiBJVCBzZXJ2aWNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjoyMDAxLCJwYXJlbnRJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwyfEV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJBbmFseXNlIGFyY2hpdGVjdHVyZSBpbXBhY3QiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMDgtMDEiLCJlbmQiOiIyMDI1LTEwLTE1IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiUGVybmV0IEJlbm9pdCAoTEVDKSAoTUlOKSIsIm5vZGVJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwzfEFuYWx5c2UgYXJjaGl0ZWN0dXJlIGltcGFjdCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkFuYWx5c2UgYXJjaGl0ZWN0dXJlIGltcGFjdCIsImx2bCI6IkwzIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjUtMTAtMTYiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJQZXJuZXQgQmVub2l0IChMRUMpIChNSU4pIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDN8QW5hbHlzZSBhcmNoaXRlY3R1cmUgaW1wYWN0In1dfSx7ImlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8QXBwcm92ZSBJVCBkZW1hbmQiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJBcHByb3ZlIElUIGRlbWFuZCIsImFzc29jTDEiOiJQbGFuIElUIHNlcnZpY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjIwMDEsInBhcmVudElkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDF8UGxhbiBJVCBzZXJ2aWNlIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkFwcHJvdmUgSVQgZGVtYW5kIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTA4LTAxIiwiZW5kIjoiMjAyNS0wOC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8QXBwcm92ZSBJVCBkZW1hbmQifSx7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJBcHByb3ZlIElUIGRlbWFuZCIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjUtMTEtMDMiLCJlbmQiOiIyMDI2LTAzLTMxIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBDT1QgRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0
5 | gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8QXBwcm92ZSBJVCBkZW1hbmQifSx7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJBcHByb3ZlIElUIGRlbWFuZCIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjUtMTEtMDEiLCJlbmQiOiIyMDI2LTAyLTI4IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMgRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8QXBwcm92ZSBJVCBkZW1hbmQifV19LHsiaWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxFdmFsdWF0ZSBhbmQgcXVhbGlmeSBJVCBkZW1hbmQiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJFdmFsdWF0ZSBhbmQgcXVhbGlmeSBJVCBkZW1hbmQiLCJhc3NvY0wxIjoiUGxhbiBJVCBzZXJ2aWNlIiwiaW5kZW50IjoyLCJzb3J0S2V5IjoyMDAxLCJwYXJlbnRJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwxfFBsYW4gSVQgc2VydmljZSIsImNoaWxkcmVuIjpbIm58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwzfEFuYWx5c2UgYXJjaGl0ZWN0dXJlIGltcGFjdCJdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0wOC0wMSIsImVuZCI6IjIwMjUtMDgtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJTcGlldGggVGluYSAoTElTKSIsIm5vZGVJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwyfEV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IkV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjUtMTEtMDMiLCJlbmQiOiIyMDI2LTAzLTMxIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBDT1QgRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8RXZhbHVhdGUgYW5kIHF1YWxpZnkgSVQgZGVtYW5kIn0seyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiRXZhbHVhdGUgYW5kIHF1YWxpZnkgSVQgZGVtYW5kIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNS0xMS0wMSIsImVuZCI6IjIwMjYtMDItMjgiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxFdmFsdWF0ZSBhbmQgcXVhbGlmeSBJVCBkZW1hbmQifV19LHsiaWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxQZXJmb3JtIGluaXRpYWwgYXNzZXNzbWVudCBvZiBjdXN0b21lciBuZWVkIiwidHlwZSI6InByb2MiLCJwZyI6IkNQIiwibHZsIjoiTDIiLCJuYW1lIjoiUGVyZm9ybSBpbml0aWFsIGFzc2Vzc21lbnQgb2YgY3VzdG9tZXIgbmVlZCIsImFzc29jTDEiOiJQbGFuIElUIHNlcnZpY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjIwMDEsInBhcmVudElkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDF8UGxhbiBJVCBzZXJ2aWNlIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IlBlcmZvcm0gaW5pdGlhbCBhc3Nlc3NtZW50IG9mIGN1c3RvbWVyIG5lZWQiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMDgtMDEiLCJlbmQiOiIyMDI1LTA4LTAxIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMnxQZXJmb3JtIGluaXRpYWwgYXNzZXNzbWVudCBvZiBjdXN0b21lciBuZWVkIn0seyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiUGVyZm9ybSBpbml0aWFsIGFzc2Vzc21lbnQgb2YgY3VzdG9tZXIgbmVlZCIsImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBDT1QiLCJzdGFydCI6IjIwMjUtMTEtMDMiLCJlbmQiOiIyMDI2LTAzLTMxIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBDT1QgRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8UGVyZm9ybSBpbml0aWFsIGFzc2Vzc21lbnQgb2YgY3VzdG9tZXIgbmVlZCJ9LHsicGciOiJDUCIsImwxIjoiUGxhbiBJVCBzZXJ2aWNlIiwicHJvYyI6IlBlcmZvcm0gaW5pdGlhbCBhc3Nlc3NtZW50IG9mIGN1c3RvbWVyIG5lZWQiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI1LTExLTAxIiwiZW5kIjoiMjAyNi0wMi0yOCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJTcGlldGggVGluYSAoTElTKSIsIm5vZGVJZCI6Im58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwyfFBlcmZvcm0gaW5pdGlhbCBhc3Nlc3NtZW50IG9mIGN1c3RvbWVyIG5lZWQifV19LHsiaWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMXxQbGFuIElUIHNlcnZpY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMSIsIm5hbWUiOiJQbGFuIElUIHNlcnZpY2UiLCJhc3NvY0wxIjoiUGxhbiBJVCBzZXJ2aWNlIiwiaW5kZW50IjoxLCJzb3J0S2V5IjoyMDAxLCJwYXJlbnRJZCI6InBnfENQIiwiY2hpbGRyZW4iOlsibnxDUHxQbGFuIElUIHNlcnZpY2V8TDJ8UGVyZm9ybSBpbml0aWFsIGFzc2Vzc21lbnQgb2YgY3VzdG9tZXIgbmVlZCIsIm58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwyfEV2YWx1YXRlIGFuZCBxdWFsaWZ5IElUIGRlbWFuZCIsIm58Q1B8UGxhbiBJVCBzZXJ2aWNlfEwyfEFwcHJvdmUgSVQgZGVtYW5kIl0sIml0ZW1zIjpbeyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiUGxhbiBJVCBzZXJ2aWNlIiwibHZsIjoiTDEiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTE2IiwiZW5kIjoiMjAyNS0xMC0zMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDF8UGxhbiBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJQbGFuIElUIHNlcnZpY2UiLCJwcm9jIjoiUGxhbiBJVCBzZXJ2aWNlIiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNS0xMS0wMyIsImVuZCI6IjIwMjYtMDMtMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiU3BpZXRoIFRpbmEgKExJUykiLCJub2RlSWQiOiJufENQfFBsYW4gSVQgc2VydmljZXxMMXxQbGFuIElUIHNlcnZpY2UifSx7InBnIjoiQ1AiLCJsMSI6IlBsYW4gSVQgc2VydmljZSIsInByb2MiOiJQbGFuIElUIHNlcnZpY2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI1LTExLTAxIiwiZW5kIjoiMjAyNi0wMi0yOCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIERvbmUiLCJwY3QiOiIwLjAwNzUiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IlNwaWV0aCBUaW5hIChMSVMpIiwibm9kZUlkIjoibnxDUHxQbGFuIElUIHNlcnZpY2V8TDF8UGxhbiBJVCBzZXJ2aWNlIn1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwxfEJ1aWxkIElUIFNlcnZpY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMSIsIm5hbWUiOiJCdWlsZCBJVCBTZXJ2aWNlIiwiYXNzb2NMMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJpbmRlbnQiOjEsInNvcnRLZXkiOjIwMDIsInBhcmVudElkIjoicGd8Q1AiLCJjaGlsZHJlbiI6WyJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8RGVzaWduIElUIHNlcnZpY2UiLCJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8RGV2ZWxvcCBhbmQgY3VzdG9taXNlIElUIHNlcnZpY2UiLCJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8RGVwbG95IElUIHNlcnZpY2UiLCJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8VGVzdCBhbmQgdmFsaWRhdGUgSVQgc2VydmljZSIsIm58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxNYW5hZyBJVCBzZXJ2aWNlIGNoYW5nZSIsIm58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxNYW5hZ2UgSVQgc2VydmljZSByZWxlYXNlIl0sIml0ZW1zIjpbXX0seyJpZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMNHxDb25kdWN0IG1hcmtldCBhbmFseXNpcyBhbmQgY29tcGlsZSBsb25nIG9yIHNob3J0IGxpc3QiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMNCIsIm5hbWUiOiJDb25kdWN0IG1hcmtldCBhbmFseXNpcyBhbmQgY29tcGlsZSBsb25nIG9yIHNob3J0IGxpc3QiLCJhc3NvY0wxIjoiQnVpbGQgSVQgU2VydmljZSIsImluZGVudCI6NCwic29ydEtleSI6MjAwMiwicGFyZW50SWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8UGVyZm9ybSBzb2Z0d2FyZSBzZWxlY3Rpb24iLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkNvbmR1Y3QgbWFya2V0IGFuYWx5c2lzIGFuZCBjb21waWxlIGxvbmcgb3Igc2hvcnQgbGlzdCIsImx2bCI6Ikw0IiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTAtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUHJlaXNzIE1hdHRoaWFzIChMQkMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fENvbmR1Y3QgbWFya2V0IGFuYWx5c2lzIGFuZCBjb21waWxlIGxvbmcgb3Igc2hvcnQgbGlzdCJ9XX0seyJpZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xEZWZpbmUgc29sdXRpb24gdGFyZ2V0IGFyY2hpdGVjdHVyZSIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwzIiwibmFtZSI6IkRlZmluZSBzb2x1dGlvbiB0YXJnZXQgYXJjaGl0ZWN0dXJlIiwiYXNzb2NMMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjIwMDIsInBhcmVudElkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfERlc2lnbiBJVCBzZXJ2aWNlIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJEZWZpbmUgc29sdXRpb24gdGFyZ2V0IGFyY2hpdGVjdHVyZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMi0wNSIsImVuZCI6IjIwMjYtMDQtMjEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJOdXNzYmF1bWVyIEZsb3JpYW4gKExCQykiLCJsZWFkIjoiSGFtbWVyIE1hcmNvIChBRVIpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwzfERlZmluZSBzb2x1dGlvbiB0YXJnZXQgYXJjaGl0ZWN0dXJlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkRlZmluZSBzb2x1dGlvbiB0YXJnZXQgYXJjaGl0ZWN0dXJlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNi0wNC0yMiIsImVuZCI6IjIwMjYtMDQtMjIiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik51c3NiYXVtZXIgRmxvcmlhbiAoTEJDKSIsImxlYWQiOiJIYW1tZXIgTWFyY28gKEFFUikiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8RGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTIyIiwiZW5kIjoiMjAyNi0wNi0yMiIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6Ik51c3NiYXVtZXIgRmxvcmlhbiAoTEJDKSIsImxlYWQiOiJIYW1tZXIgTWFyY28gKEFFUikiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8RGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTFVTIiwic3RhcnQiOiIyMDI2LTAxLTE0IiwiZW5kIjoiMjAyNi0wMS0xNCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTFVTIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiTnVzc2JhdW1lciBGbG9yaWFuIChMQkMpIiwibGVhZCI6IkhhbW1lciBNYXJjbyAoQUVSKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xEZWZpbmUgc29sdXRpb24gdGFyZ2V0IGFyY2hpdGVjdHVyZSJ9XX0seyJpZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxEZXBsb3kgSVQgc2VydmljZSIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwyIiwibmFtZSI6IkRlcGxveSBJVCBzZXJ2aWNlIiwiYXNzb2NMMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjIwMDIsInBhcmVudElkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwxfEJ1aWxkIElUIFNlcnZpY2UiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkRlcGxveSBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTA0LTE1IiwiZW5kIjoiMjAyNi0wNi0xNSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJXaWVoZSBBbGV4YW5kZXIgKENPQikiLCJsZWFkIjoiRGFsZWsgTWFydGluIChMSVMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfERlcGxveSBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IkRlcGxveSBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNy0xNSIsImVuZCI6IjIwMjYtMDgtMzEiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IkRhbGVrIE1hcnRpbiAoTElTKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxEZXBsb3kgSVQgc2VydmljZSJ9XX0seyJpZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxEZXNpZ24gSVQgc2VydmljZSIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwyIiwibmFtZSI6IkRlc2lnbiBJVCBzZXJ2aWNlIiwiYXNzb2NMMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjIwMDIsInBhcmVudElkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwxfEJ1aWxkIElUIFNlcnZpY2UiLCJjaGlsZHJlbiI6WyJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8RGVmaW5lIHNvbHV0aW9uIHRhcmdldCBhcmNoaXRlY3R1cmUiLCJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8UGVyZm9ybSBzb2Z0d2FyZSBzZWxlY3Rpb24iXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVzaWduIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDItMTYiLCJlbmQiOiIyMDI2LTA1LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJEYWxlayBNYXJ0aW4gKExJUykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8RGVzaWduIElUIHNlcnZpY2UifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGVzaWduIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA1LTE4IiwiZW5kIjoiMjAyNi0wOC0xNCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJXaWVoZSBBbGV4YW5kZXIgKENPQikiLCJsZWFkIjoiRGFsZWsgTWFydGluIChMSVMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfERlc2lnbiBJVCBzZXJ2aWNlIn1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfERldmVsb3AgYW5kIGN1c3RvbWlzZSBJVCBzZXJ2aWNlIiwidHlwZSI6InByb2MiLCJwZyI6IkNQIiwibHZsIjoiTDIiLCJuYW1lIjoiRGV2ZWxvcCBhbmQgY3VzdG9taXNlIElUIHNlcnZpY2UiLCJhc3NvY0wxIjoiQnVpbGQgSVQgU2VydmljZSIsImluZGVudCI6Miwic29ydEtleSI6MjAwMiwicGFyZW50SWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDF8QnVpbGQgSVQgU2VydmljZSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGV2ZWxvcCBhbmQgY3VzdG9taXNlIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDItMTYiLCJlbmQiOiIyMDI2LTA1LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJEYWxlayBNYXJ0aW4gKExJUykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8RGV2ZWxvcCBhbmQgY3VzdG9taXNlIElUIHNlcnZpY2UifSx7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiRGV2ZWxvcCBhbmQgY3VzdG9taXNlIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI1LTA1LTI2IiwiZW5kIjoiMjAyNS0wOC0xNSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6Ikt1bnogQ2hyaXN0aW5hIChMSVMtTUhQIE1hbmFnZW1lbnQtIHVuZCBJVCBCZXJhdHVuZyBHbWJIKSIsIm1hbmFnZXIiOiJXaWVoZSBBbGV4YW5kZXIgKENPQikiLCJsZWFkIjoiRGFsZWsgTWFydGluIChMSVMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfERldmVsb3AgYW5kIGN1c3RvbWlzZSBJVCBzZXJ2aWNlIn1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfE1hbmFnIElUIHNlcnZpY2UgY2hhbmdlIiwidHlwZSI6InByb2MiLCJwZyI6IkNQIiwibHZsIjoiTDIiLCJuYW1lIjoiTWFuYWcgSVQgc2VydmljZSBjaGFuZ2UiLCJhc3NvY0wxIjoiQnVpbGQgSVQgU2VydmljZSIsImluZGVudCI6Miwic29ydEtleSI6MjAwMiwicGFyZW50SWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDF8QnVpbGQgSVQgU2VydmljZSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiTWFuYWcgSVQgc2VydmljZSBjaGFuZ2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMTIiLCJlbmQiOiIyMDI2LTAzLTE4IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCk7RnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IlNpbnQgUmFjaGVsIChMQkgpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfE1hbmFnIElUIHNlcnZpY2UgY2hhbmdlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6Ik1hbmFnIElUIHNlcnZpY2UgY2hhbmdlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNC0xNSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpO0ZyYW5rIE1hcmVuIChMSVMpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJTaW50IFJhY2hlbCAoTEJIKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxNYW5hZyBJVCBzZXJ2aWNlIGNoYW5nZSJ9XX0seyJpZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxNYW5hZ2UgSVQgc2VydmljZSByZWxlYXNlIiwidHlwZSI6InByb2MiLCJwZyI6IkNQIiwibHZsIjoiTDIiLCJuYW1lIjoiTWFuYWdlIElUIHNlcnZpY2UgcmVsZWFzZSIsImFzc29jTDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwiaW5kZW50IjoyLCJzb3J0S2V5IjoyMDAyLCJwYXJlbnRJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMXxCdWlsZCBJVCBTZXJ2aWNlIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJNYW5hZ2UgSVQgc2VydmljZSByZWxlYXNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAyLTIwIiwiZW5kIjoiMjAyNi0wNS0wOCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpO0ZyYW5rIE1hcmVuIChMSVMpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJTaW50IFJhY2hlbCAoTEJIKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxNYW5hZ2UgSVQgc2VydmljZSByZWxlYXNlIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6Ik1hbmFnZSBJVCBzZXJ2aWNlIHJlbGVhc2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTE1IiwiZW5kIjoiMjAyNi0wNi0zMCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCk7RnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IlNpbnQgUmFjaGVsIChMQkgpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfE1hbmFnZSBJVCBzZXJ2aWNlIHJlbGVhc2UifV19LHsiaWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDN8UGVyZm9ybSBzb2Z0d2FyZSBzZWxlY3Rpb24iLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMyIsIm5hbWUiOiJQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImFzc29jTDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjoyMDAyLCJwYXJlbnRJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxEZXNpZ24gSVQgc2VydmljZSIsImNoaWxkcmVuIjpbIm58Q1B8QnVpbGQgSVQgU2VydmljZXxMNHxSZWNvcmQgYW5kIHBsYW4gZnVuY3Rpb25hbCByZXF1aXJlbWVudHMiLCJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDR8Q29uZHVjdCBtYXJrZXQgYW5hbHlzaXMgYW5kIGNvbXBpbGUgbG9uZyBvciBzaG9ydCBsaXN0IiwibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fFBlcmZvcm0gdmVuZG9yIHVzZSBjYXNlIHBpdGNoIGFuZCB1c2FiaWxpdHkgdGVzdCIsIm58Q1B8QnVpbGQgSVQgU2VydmljZXxMNHxWYWxpZGF0ZSBzdHJhdGVnaWMgZml0IiwibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fFJlY29tbWVuZGF0aW9uIGFuZCBFQSBhcHByb3ZhbCJdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTItMjMiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUHJlaXNzIE1hdHRoaWFzIChMQkMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwzfFBlcmZvcm0gc29mdHdhcmUgc2VsZWN0aW9uIn0seyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IlBlcmZvcm0gc29mdHdhcmUgc2VsZWN0aW9uIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjUtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIENPVCBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlJlaW5lciBIZWlrbyAoSEFVLUlUU0EpIiwibGVhZCI6IlByZWlzcyBNYXR0aGlhcyAoTEJDKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImx2bCI6IkwzIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDItMTYiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiUHJlaXNzIE1hdHRoaWFzIChMQkMpIiwibm9kZUlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwzfFBlcmZvcm0gc29mdHdhcmUgc2VsZWN0aW9uIn1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fFBlcmZvcm0gdmVuZG9yIHVzZSBjYXNlIHBpdGNoIGFuZCB1c2FiaWxpdHkgdGVzdCIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6Ikw0IiwibmFtZSI6IlBlcmZvcm0gdmVuZG9yIHVzZSBjYXNlIHBpdGNoIGFuZCB1c2FiaWxpdHkgdGVzdCIsImFzc29jTDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwiaW5kZW50Ijo0LCJzb3J0S2V5IjoyMDAyLCJwYXJlbnRJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiUGVyZm9ybSB2ZW5kb3IgdXNlIGNhc2UgcGl0Y2ggYW5kIHVzYWJpbGl0eSB0ZXN0IiwibHZsIjoiTDQiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJQcmVpc3MgTWF0dGhpYXMgKExCQykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDR8UGVyZm9ybSB2ZW5kb3IgdXNlIGNhc2UgcGl0Y2ggYW5kIHVzYWJpbGl0eSB0ZXN0In1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fFJlY29tbWVuZGF0aW9uIGFuZCBFQSBhcHByb3ZhbCIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6Ikw0IiwibmFtZSI6IlJlY29tbWVuZGF0aW9uIGFuZCBFQSBhcHByb3ZhbCIsImFzc29jTDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwiaW5kZW50Ijo0LCJzb3J0S2V5IjoyMDAyLCJwYXJlbnRJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiUmVjb21tZW5kYXRpb24gYW5kIEVBIGFwcHJvdmFsIiwibHZsIjoiTDQiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJQcmVpc3MgTWF0dGhpYXMgKExCQykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDR8UmVjb21tZW5kYXRpb24gYW5kIEVBIGFwcHJvdmFsIn1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fFJlY29yZCBhbmQgcGxhbiBmdW5jdGlvbmFsIHJlcXVpcmVtZW50cyIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6Ikw0IiwibmFtZSI6IlJlY29yZCBhbmQgcGxhbiBmdW5jdGlvbmFsIHJlcXVpcmVtZW50cyIsImFzc29jTDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwiaW5kZW50Ijo0LCJzb3J0S2V5IjoyMDAyLCJwYXJlbnRJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMM3xQZXJmb3JtIHNvZnR3YXJlIHNlbGVjdGlvbiIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJwcm9jIjoiUmVjb3JkIGFuZCBwbGFuIGZ1bmN0aW9uYWwgcmVxdWlyZW1lbnRzIiwibHZsIjoiTDQiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJQcmVpc3MgTWF0dGhpYXMgKExCQykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDR8UmVjb3JkIGFuZCBwbGFuIGZ1bmN0aW9uYWwgcmVxdWlyZW1lbnRzIn1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwyfFRlc3QgYW5kIHZhbGlkYXRlIElUIHNlcnZpY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJUZXN0IGFuZCB2YWxpZGF0ZSBJVCBzZXJ2aWNlIiwiYXNzb2NMMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjIwMDIsInBhcmVudElkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwxfEJ1aWxkIElUIFNlcnZpY2UiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IkNQIiwibDEiOiJCdWlsZCBJVCBTZXJ2aWNlIiwicHJvYyI6IlRlc3QgYW5kIHZhbGlkYXRlIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDQtMTUiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiS3VueiBDaHJpc3RpbmEgKExJUy1NSFAgTWFuYWdlbWVudC0gdW5kIElUIEJlcmF0dW5nIEdtYkgpIiwibWFuYWdlciI6IldpZWhlIEFsZXhhbmRlciAoQ09CKSIsImxlYWQiOiJEYWxlayBNYXJ0aW4gKExJUykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDJ8VGVzdCBhbmQgdmFsaWRhdGUgSVQgc2VydmljZSJ9LHsicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJUZXN0IGFuZCB2YWxpZGF0ZSBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNy0xNSIsImVuZCI6IjIwMjYtMDgtMzEiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJLdW56IENocmlzdGluYSAoTElTLU1IUCBNYW5hZ2VtZW50LSB1bmQgSVQgQmVyYXR1bmcgR21iSCkiLCJtYW5hZ2VyIjoiV2llaGUgQWxleGFuZGVyIChDT0IpIiwibGVhZCI6IkRhbGVrIE1hcnRpbiAoTElTKSIsIm5vZGVJZCI6Im58Q1B8QnVpbGQgSVQgU2VydmljZXxMMnxUZXN0IGFuZCB2YWxpZGF0ZSBJVCBzZXJ2aWNlIn1dfSx7ImlkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEw0fFZhbGlkYXRlIHN0cmF0ZWdpYyBmaXQiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMNCIsIm5hbWUiOiJWYWxpZGF0ZSBzdHJhdGVnaWMgZml0IiwiYXNzb2NMMSI6IkJ1aWxkIElUIFNlcnZpY2UiLCJpbmRlbnQiOjQsInNvcnRLZXkiOjIwMDIsInBhcmVudElkIjoibnxDUHxCdWlsZCBJVCBTZXJ2aWNlfEwzfFBlcmZvcm0gc29mdHdhcmUgc2VsZWN0aW9uIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiQnVpbGQgSVQgU2VydmljZSIsInByb2MiOiJWYWxpZGF0ZSBzdHJhdGVnaWMgZml0IiwibHZsIjoiTDQiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiSG9lcm1hbm4gUGF0cmljayAoTExJKSIsIm1hbmFnZXIiOiJSZWluZXIgSGVpa28gKEhBVS1JVFNBKSIsImxlYWQiOiJQcmVpc3MgTWF0dGhpYXMgKExCQykiLCJub2RlSWQiOiJufENQfEJ1aWxkIElUIFNlcnZpY2V8TDR8VmFsaWRhdGUgc3RyYXRlZ2ljIGZpdCJ9XX0seyJpZCI6Im58Q1B8RGVsaXZlciBJVCBzZXJ2aWNlfEwxfERlbGl2ZXIgSVQgc2VydmljZSIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwxIiwibmFtZSI6IkRlbGl2ZXIgSVQgc2VydmljZSIsImFzc29jTDEiOiJEZWxpdmVyIElUIHNlcnZpY2UiLCJpbmRlbnQiOjEsInNvcnRLZXkiOjIwMDMsInBhcmVudElkIjoicGd8Q1AiLCJjaGlsZHJlbiI6WyJufENQfERlbGl2ZXIgSVQgc2VydmljZXxMMnxNYW5hZ2UgSVQgc2VydmljZSBwcm92aXNpb24gcmVxdWVzdCIsIm58Q1B8RGVsaXZlciBJVCBzZXJ2aWNlfEwyfEhhbmRsZSBJVCBzZXJ2aWNlIG9yZGVyIl0sIml0ZW1zIjpbXX0seyJpZCI6Im58Q1B8RGVsaXZlciBJVCBzZXJ2aWNlfEwyfEhhbmRsZSBJVCBzZXJ2aWNlIG9yZGVyIiwidHlwZSI6InByb2MiLCJwZyI6IkNQIiwibHZsIjoiTDIiLCJuYW1lIjoiSGFuZGxlIElUIHNlcnZpY2Ugb3JkZXIiLCJhc3NvY0wxIjoiRGVsaXZlciBJVCBzZXJ2aWNlIiwiaW5kZW50IjoyLCJzb3J0S2V5IjoyMDAzLCJwYXJlbnRJZCI6Im58Q1B8RGVsaXZlciBJVCBzZXJ2aWNlfEwxfERlbGl2ZXIgSVQgc2VydmljZSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IkRlbGl2ZXIgSVQgc2VydmljZSIsInByb2MiOiJIYW5kbGUgSVQgc2VydmljZSBvcmRlciIsImx2bCI6IkwyIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjYtMDYtMTciLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlNjaG51cnJlbmJlcmdlciBDaHJpc3RvcGggKExJUy1MSU4pIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58Q1B8RGVsaXZlciBJVCBzZXJ2aWNlfEwyfEhhbmRsZSBJVCBzZXJ2aWNlIG9yZGVyIn0seyJwZyI6IkNQIiwibDEiOiJEZWxpdmVyIElUIHNlcnZpY2UiLCJwcm9jIjoiSGFuZGxlIElUIHNlcnZpY2Ugb3JkZXIiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNi0xNSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpIiwibWFuYWdlciI6IlNjaG51cnJlbmJlcmdlciBDaHJpc3RvcGggKExJUy1MSU4pIiwibGVhZCI6Ikt1ZXJzY2huZXIgUGhpbGlwcCAoTElTKSIsIm5vZGVJZCI6Im58Q1B8RGVsaXZlciBJVCBzZXJ2aWNlfEwyfEhhbmRsZSBJVCBzZXJ2aWNlIG9yZGVyIn1dfSx7ImlkIjoibnxDUHxEZWxpdmVyIElUIHNlcnZpY2V8TDJ8TWFuYWdlIElUIHNlcnZpY2UgcHJvdmlzaW9uIHJlcXVlc3QiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJNYW5hZ2UgSVQgc2VydmljZSBwcm92aXNpb24gcmVxdWVzdCIsImFzc29jTDEiOiJEZWxpdmVyIElUIHNlcnZpY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjIwMDMsInBhcmVudElkIjoibnxDUHxEZWxpdmVyIElUIHNlcnZpY2V8TDF8RGVsaXZlciBJVCBzZXJ2aWNlIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiRGVsaXZlciBJVCBzZXJ2aWNlIiwicHJvYyI6Ik1hbmFnZSBJVCBzZXJ2aWNlIHByb3Zpc2lvbiByZXF1ZXN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNi0xNyIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiU2NobnVycmVuYmVyZ2VyIENocmlzdG9waCAoTElTLUxJTikiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxEZWxpdmVyIElUIHNlcnZpY2V8TDJ8TWFuYWdlIElUIHNlcnZpY2UgcHJvdmlzaW9uIHJlcXVlc3QifSx7InBnIjoiQ1AiLCJsMSI6IkRlbGl2ZXIgSVQgc2VydmljZSIsInByb2MiOiJNYW5hZ2UgSVQgc2VydmljZSBwcm92aXNpb24gcmVxdWVzdCI
6 | sImx2bCI6IkwyIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjYtMDQtMDEiLCJlbmQiOiIyMDI2LTA2LTE1IiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkhvZXJtYW5uIFBhdHJpY2sgKExMSSkiLCJtYW5hZ2VyIjoiU2NobnVycmVuYmVyZ2VyIENocmlzdG9waCAoTElTLUxJTikiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxEZWxpdmVyIElUIHNlcnZpY2V8TDJ8TWFuYWdlIElUIHNlcnZpY2UgcHJvdmlzaW9uIHJlcXVlc3QifV19LHsiaWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfEhhbmRsZSBJVCBJbmNpZGVudCIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwzIiwibmFtZSI6IkhhbmRsZSBJVCBJbmNpZGVudCIsImFzc29jTDEiOiJSdW4gSVQgc2VydmljZSIsImluZGVudCI6Mywic29ydEtleSI6MjAwNCwicGFyZW50SWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwyfFByb3ZpZGUgSVQgc2VydmljZSBzdXBwb3J0IiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiUnVuIElUIHNlcnZpY2UiLCJwcm9jIjoiSGFuZGxlIElUIEluY2lkZW50IiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEzIiwiZW5kIjoiMjAyNi0wMy0xOSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAwNzUiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMM3xIYW5kbGUgSVQgSW5jaWRlbnQifV19LHsiaWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfEhhbmRsZSBJVCBwcm9ibGVtIiwidHlwZSI6InByb2MiLCJwZyI6IkNQIiwibHZsIjoiTDMiLCJuYW1lIjoiSGFuZGxlIElUIHByb2JsZW0iLCJhc3NvY0wxIjoiUnVuIElUIHNlcnZpY2UiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjIwMDQsInBhcmVudElkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxQcm92aWRlIElUIHNlcnZpY2Ugc3VwcG9ydCIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6IkhhbmRsZSBJVCBwcm9ibGVtIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEzIiwiZW5kIjoiMjAyNi0wMy0xOSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAwNzUiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMM3xIYW5kbGUgSVQgcHJvYmxlbSJ9XX0seyJpZCI6Im58Q1B8UnVuIElUIHNlcnZpY2V8TDN8SGFuZGxlIElUIHNlcnZpY2UgcmVxdWVzdCIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwzIiwibmFtZSI6IkhhbmRsZSBJVCBzZXJ2aWNlIHJlcXVlc3QiLCJhc3NvY0wxIjoiUnVuIElUIHNlcnZpY2UiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjIwMDQsInBhcmVudElkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxQcm92aWRlIElUIHNlcnZpY2Ugc3VwcG9ydCIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6IkhhbmRsZSBJVCBzZXJ2aWNlIHJlcXVlc3QiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDItMDIiLCJlbmQiOiIyMDI2LTAzLTE5IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJLdWVyc2NobmVyIFBoaWxpcHAgKExJUykiLCJub2RlSWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfEhhbmRsZSBJVCBzZXJ2aWNlIHJlcXVlc3QifV19LHsiaWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfE1haW50YWluIENNREIiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMyIsIm5hbWUiOiJNYWludGFpbiBDTURCIiwiYXNzb2NMMSI6IlJ1biBJVCBzZXJ2aWNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjoyMDA0LCJwYXJlbnRJZCI6Im58Q1B8UnVuIElUIHNlcnZpY2V8TDJ8T3BlcmF0ZSBhbmQgbWFpbnRhaW4gSVQgc2VydmljZSIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6Ik1haW50YWluIENNREIiLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMTQiLCJlbmQiOiIyMDI2LTA1LTIwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJTY2hyb2VkZXIgTWljaGFlbCAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJLcmV0eiBMdWNhcyAoQ09DLUNPVC1JVCkiLCJub2RlSWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfE1haW50YWluIENNREIifV19LHsiaWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwyfE9wZXJhdGUgYW5kIG1haW50YWluIElUIHNlcnZpY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiQ1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIiwiYXNzb2NMMSI6IlJ1biBJVCBzZXJ2aWNlIiwiaW5kZW50IjoyLCJzb3J0S2V5IjoyMDA0LCJwYXJlbnRJZCI6Im58Q1B8UnVuIElUIHNlcnZpY2V8TDF8UnVuIElUIHNlcnZpY2UiLCJjaGlsZHJlbiI6WyJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfE1haW50YWluIENNREIiXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6Ik9wZXJhdGUgYW5kIG1haW50YWluIElUIHNlcnZpY2UiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMTIiLCJlbmQiOiIyMDI2LTA2LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3JldHogTHVjYXMgKENPQy1DT1QtSVQpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIn0seyJwZyI6IkNQIiwibDEiOiJSdW4gSVQgc2VydmljZSIsInByb2MiOiJPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIiwibHZsIjoiTDIiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNC0xNSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3JldHogTHVjYXMgKENPQy1DT1QtSVQpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIn1dfSx7ImlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxQcm92aWRlIElUIHNlcnZpY2Ugc3VwcG9ydCIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwyIiwibmFtZSI6IlByb3ZpZGUgSVQgc2VydmljZSBzdXBwb3J0IiwiYXNzb2NMMSI6IlJ1biBJVCBzZXJ2aWNlIiwiaW5kZW50IjoyLCJzb3J0S2V5IjoyMDA0LCJwYXJlbnRJZCI6Im58Q1B8UnVuIElUIHNlcnZpY2V8TDF8UnVuIElUIHNlcnZpY2UiLCJjaGlsZHJlbiI6WyJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfEhhbmRsZSBJVCBJbmNpZGVudCIsIm58Q1B8UnVuIElUIHNlcnZpY2V8TDN8SGFuZGxlIElUIHByb2JsZW0iLCJufENQfFJ1biBJVCBzZXJ2aWNlfEwzfEhhbmRsZSBJVCBzZXJ2aWNlIHJlcXVlc3QiXSwiaXRlbXMiOlt7InBnIjoiQ1AiLCJsMSI6IlJ1biBJVCBzZXJ2aWNlIiwicHJvYyI6IlByb3ZpZGUgSVQgc2VydmljZSBzdXBwb3J0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTEyIiwiZW5kIjoiMjAyNi0wMy0zMCIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMnxQcm92aWRlIElUIHNlcnZpY2Ugc3VwcG9ydCJ9LHsicGciOiJDUCIsImwxIjoiUnVuIElUIHNlcnZpY2UiLCJwcm9jIjoiUHJvdmlkZSBJVCBzZXJ2aWNlIHN1cHBvcnQiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNi0xNSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJTY2hyb2VkZXIgTWljaGFlbCAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJLdWVyc2NobmVyIFBoaWxpcHAgKExJUykiLCJub2RlSWQiOiJufENQfFJ1biBJVCBzZXJ2aWNlfEwyfFByb3ZpZGUgSVQgc2VydmljZSBzdXBwb3J0In1dfSx7ImlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMXxSdW4gSVQgc2VydmljZSIsInR5cGUiOiJwcm9jIiwicGciOiJDUCIsImx2bCI6IkwxIiwibmFtZSI6IlJ1biBJVCBzZXJ2aWNlIiwiYXNzb2NMMSI6IlJ1biBJVCBzZXJ2aWNlIiwiaW5kZW50IjoxLCJzb3J0S2V5IjoyMDA0LCJwYXJlbnRJZCI6InBnfENQIiwiY2hpbGRyZW4iOlsibnxDUHxSdW4gSVQgc2VydmljZXxMMnxPcGVyYXRlIGFuZCBtYWludGFpbiBJVCBzZXJ2aWNlIiwibnxDUHxSdW4gSVQgc2VydmljZXxMMnxQcm92aWRlIElUIHNlcnZpY2Ugc3VwcG9ydCJdLCJpdGVtcyI6W3sicGciOiJDUCIsImwxIjoiUnVuIElUIHNlcnZpY2UiLCJwcm9jIjoiUnVuIElUIHNlcnZpY2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMTYiLCJlbmQiOiIyMDI2LTA2LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUyk7QsO2aG1lIE1hdHRoaWFzIChleHQuKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJPZXkgS2FpIChMSVMpIiwibm9kZUlkIjoibnxDUHxSdW4gSVQgc2VydmljZXxMMXxSdW4gSVQgc2VydmljZSJ9XX0seyJpZCI6InBnfFNQIiwidHlwZSI6InBnIiwicGciOiJTUCIsImx2bCI6IkwwIiwibmFtZSI6IlNQIiwiYXNzb2NMMSI6IiIsImluZGVudCI6MCwic29ydEtleSI6MCwicGFyZW50SWQiOm51bGwsImNoaWxkcmVuIjpbIm58U1B8RW5zdXJlIEluZm9ybWF0aW9uIHNlY3VyaXR5fEwxfEVuc3VyZSBJbmZvcm1hdGlvbiBzZWN1cml0eSIsIm58U1B8TWFuYWdlIElUIHByb2plY3R8TDF8TWFuYWdlIElUIHByb2plY3QiLCJufFNQfE1hbmFnZSBJVCBzb3VyY2luZyBhbmQgcHJvY3VyZW1lbnR8TDF8TWFuYWdlIElUIHNvdXJjaW5nIGFuZCBwcm9jdXJlbWVudCIsIm58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDF8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJufFNQfEVuc3VyZSBwZXJmb3JtYW5jZSBhbmQgY29uZm9ybWFuY2Ugb2YgSVQgc2VydmljZXN8TDF8RW5zdXJlIHBlcmZvcm1hbmNlIGFuZCBjb25mb3JtYW5jZSBvZiBJVCBzZXJ2aWNlcyIsIm58U1B8TWFuYWdlIElUIGtub3dsZWRnZXxMMXxNYW5hZ2UgSVQga25vd2xlZGdlIl0sIml0ZW1zIjpbXX0seyJpZCI6Im58U1B8RW5zdXJlIEluZm9ybWF0aW9uIHNlY3VyaXR5fEwxfEVuc3VyZSBJbmZvcm1hdGlvbiBzZWN1cml0eSIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwxIiwibmFtZSI6IkVuc3VyZSBJbmZvcm1hdGlvbiBzZWN1cml0eSIsImFzc29jTDEiOiJFbnN1cmUgSW5mb3JtYXRpb24gc2VjdXJpdHkiLCJpbmRlbnQiOjEsInNvcnRLZXkiOjMwMDEsInBhcmVudElkIjoicGd8U1AiLCJjaGlsZHJlbiI6WyJufFNQfEVuc3VyZSBJbmZvcm1hdGlvbiBzZWN1cml0eXxMMnxQZXJmb3JtIFNhYVMgU2VjdXJpdHkgQXNzZXNzbWVudCJdLCJpdGVtcyI6W119LHsiaWQiOiJufFNQfEVuc3VyZSBJbmZvcm1hdGlvbiBzZWN1cml0eXxMMnxQZXJmb3JtIFNhYVMgU2VjdXJpdHkgQXNzZXNzbWVudCIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwyIiwibmFtZSI6IlBlcmZvcm0gU2FhUyBTZWN1cml0eSBBc3Nlc3NtZW50IiwiYXNzb2NMMSI6IkVuc3VyZSBJbmZvcm1hdGlvbiBzZWN1cml0eSIsImluZGVudCI6Miwic29ydEtleSI6MzAwMSwicGFyZW50SWQiOiJufFNQfEVuc3VyZSBJbmZvcm1hdGlvbiBzZWN1cml0eXxMMXxFbnN1cmUgSW5mb3JtYXRpb24gc2VjdXJpdHkiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJFbnN1cmUgSW5mb3JtYXRpb24gc2VjdXJpdHkiLCJwcm9jIjoiUGVyZm9ybSBTYWFTIFNlY3VyaXR5IEFzc2Vzc21lbnQiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMTkiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJIb2VybWFubiBQYXRyaWNrIChMTEkpO1JvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJtYW5hZ2VyIjoiUmVpbmVyIEhlaWtvIChIQVUtSVRTQSkiLCJsZWFkIjoiSGVmZWxlIE1pY2hhZWwgKExJTi1MSVMpIiwibm9kZUlkIjoibnxTUHxFbnN1cmUgSW5mb3JtYXRpb24gc2VjdXJpdHl8TDJ8UGVyZm9ybSBTYWFTIFNlY3VyaXR5IEFzc2Vzc21lbnQifV19LHsiaWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfENsb3NlIElUIHByb2plY3QiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJDbG9zZSBJVCBwcm9qZWN0IiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBwcm9qZWN0IiwiaW5kZW50IjoyLCJzb3J0S2V5IjozMDAyLCJwYXJlbnRJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDF8TWFuYWdlIElUIHByb2plY3QiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsInByb2MiOiJDbG9zZSBJVCBwcm9qZWN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTExLTExIiwiZW5kIjoiMjAyNS0xMi0xMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJNw7xobGJhY2hlciBDaHJpc3RpYW4gKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfENsb3NlIElUIHByb2plY3QifV19LHsiaWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfEluaXRpYXRlIElUIHByb2plY3QiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJJbml0aWF0ZSBJVCBwcm9qZWN0IiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBwcm9qZWN0IiwiaW5kZW50IjoyLCJzb3J0S2V5IjozMDAyLCJwYXJlbnRJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDF8TWFuYWdlIElUIHByb2plY3QiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsInByb2MiOiJJbml0aWF0ZSBJVCBwcm9qZWN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTExLTExIiwiZW5kIjoiMjAyNS0xMi0xMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJNw7xobGJhY2hlciBDaHJpc3RpYW4gKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfEluaXRpYXRlIElUIHByb2plY3QifV19LHsiaWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwxfE1hbmFnZSBJVCBwcm9qZWN0IiwidHlwZSI6InByb2MiLCJwZyI6IlNQIiwibHZsIjoiTDEiLCJuYW1lIjoiTWFuYWdlIElUIHByb2plY3QiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHByb2plY3QiLCJpbmRlbnQiOjEsInNvcnRLZXkiOjMwMDIsInBhcmVudElkIjoicGd8U1AiLCJjaGlsZHJlbiI6WyJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfEluaXRpYXRlIElUIHByb2plY3QiLCJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfFBsYW4gSVQgcHJvamVjdCIsIm58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8U3RlZXIgYW5kIGV4ZWN1dGUgSVQgcHJvamVjdCIsIm58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8Q2xvc2UgSVQgcHJvamVjdCIsIm58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8TWFuYWdlIElUIHByb2plY3QgY2hhbmdlIHJlcXVlc3QiLCJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfFJlc3NvdXJjZW1hbmFnZW1lbnQgZm9yIElUIHByb2plY3RzIl0sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsInByb2MiOiJNYW5hZ2UgSVQgcHJvamVjdCIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMS0xMSIsImVuZCI6IjIwMjUtMTItMTAiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkZyYW5rIE1hcmVuIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiTcO8aGxiYWNoZXIgQ2hyaXN0aWFuIChMSVMpIiwibm9kZUlkIjoibnxTUHxNYW5hZ2UgSVQgcHJvamVjdHxMMXxNYW5hZ2UgSVQgcHJvamVjdCJ9XX0seyJpZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8TWFuYWdlIElUIHByb2plY3QgY2hhbmdlIHJlcXVlc3QiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJNYW5hZ2UgSVQgcHJvamVjdCBjaGFuZ2UgcmVxdWVzdCIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsImluZGVudCI6Miwic29ydEtleSI6MzAwMiwicGFyZW50SWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwxfE1hbmFnZSBJVCBwcm9qZWN0IiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJTUCIsImwxIjoiTWFuYWdlIElUIHByb2plY3QiLCJwcm9jIjoiTWFuYWdlIElUIHByb2plY3QgY2hhbmdlIHJlcXVlc3QiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTEiLCJlbmQiOiIyMDI1LTEyLTEwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6Ik3DvGhsYmFjaGVyIENocmlzdGlhbiAoTElTKSIsIm5vZGVJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8TWFuYWdlIElUIHByb2plY3QgY2hhbmdlIHJlcXVlc3QifV19LHsiaWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfFBsYW4gSVQgcHJvamVjdCIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwyIiwibmFtZSI6IlBsYW4gSVQgcHJvamVjdCIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsImluZGVudCI6Miwic29ydEtleSI6MzAwMiwicGFyZW50SWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwxfE1hbmFnZSBJVCBwcm9qZWN0IiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJTUCIsImwxIjoiTWFuYWdlIElUIHByb2plY3QiLCJwcm9jIjoiUGxhbiBJVCBwcm9qZWN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTExLTExIiwiZW5kIjoiMjAyNS0xMi0xMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJNw7xobGJhY2hlciBDaHJpc3RpYW4gKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfFBsYW4gSVQgcHJvamVjdCJ9XX0seyJpZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8UmVzc291cmNlbWFuYWdlbWVudCBmb3IgSVQgcHJvamVjdHMiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJSZXNzb3VyY2VtYW5hZ2VtZW50IGZvciBJVCBwcm9qZWN0cyIsImFzc29jTDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsImluZGVudCI6Miwic29ydEtleSI6MzAwMiwicGFyZW50SWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwxfE1hbmFnZSBJVCBwcm9qZWN0IiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJTUCIsImwxIjoiTWFuYWdlIElUIHByb2plY3QiLCJwcm9jIjoiUmVzc291cmNlbWFuYWdlbWVudCBmb3IgSVQgcHJvamVjdHMiLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTEtMTEiLCJlbmQiOiIyMDI1LTEyLTEwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJGcmFuayBNYXJlbiAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6Ik3DvGhsYmFjaGVyIENocmlzdGlhbiAoTElTKSIsIm5vZGVJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDJ8UmVzc291cmNlbWFuYWdlbWVudCBmb3IgSVQgcHJvamVjdHMifV19LHsiaWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfFN0ZWVyIGFuZCBleGVjdXRlIElUIHByb2plY3QiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMiIsIm5hbWUiOiJTdGVlciBhbmQgZXhlY3V0ZSBJVCBwcm9qZWN0IiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBwcm9qZWN0IiwiaW5kZW50IjoyLCJzb3J0S2V5IjozMDAyLCJwYXJlbnRJZCI6Im58U1B8TWFuYWdlIElUIHByb2plY3R8TDF8TWFuYWdlIElUIHByb2plY3QiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQgcHJvamVjdCIsInByb2MiOiJTdGVlciBhbmQgZXhlY3V0ZSBJVCBwcm9qZWN0IiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTExLTExIiwiZW5kIjoiMjAyNS0xMi0xMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiRnJhbmsgTWFyZW4gKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJNw7xobGJhY2hlciBDaHJpc3RpYW4gKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBwcm9qZWN0fEwyfFN0ZWVyIGFuZCBleGVjdXRlIElUIHByb2plY3QifV19LHsiaWQiOiJufFNQfE1hbmFnZSBJVCBzb3VyY2luZyBhbmQgcHJvY3VyZW1lbnR8TDF8TWFuYWdlIElUIHNvdXJjaW5nIGFuZCBwcm9jdXJlbWVudCIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwxIiwibmFtZSI6Ik1hbmFnZSBJVCBzb3VyY2luZyBhbmQgcHJvY3VyZW1lbnQiLCJhc3NvY0wxIjoiTWFuYWdlIElUIHNvdXJjaW5nIGFuZCBwcm9jdXJlbWVudCIsImluZGVudCI6MSwic29ydEtleSI6MzAwMywicGFyZW50SWQiOiJwZ3xTUCIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6Ik1hbmFnZSBJVCBzb3VyY2luZyBhbmQgcHJvY3VyZW1lbnQiLCJwcm9jIjoiTWFuYWdlIElUIHNvdXJjaW5nIGFuZCBwcm9jdXJlbWVudCIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wNC0yMCIsImVuZCI6IjIwMjYtMDQtMjIiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IlNjaG9lYmVybCBMb3JlbmEgKExCSCkiLCJtYW5hZ2VyIjoiTW9ubmllciBNdXJpZWxsZSAoTEVDKSIsImxlYWQiOiJEb2xkZXJlciBXb2xmZ2FuZyAoTElTKSIsIm5vZGVJZCI6Im58U1B8TWFuYWdlIElUIHNvdXJjaW5nIGFuZCBwcm9jdXJlbWVudHxMMXxNYW5hZ2UgSVQgc291cmNpbmcgYW5kIHByb2N1cmVtZW50In1dfSx7ImlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxBdHRyYWN0IGFuZCBoaXJlIGVtcGxveWVlcyIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwyIiwibmFtZSI6IkF0dHJhY3QgYW5kIGhpcmUgZW1wbG95ZWVzIiwiYXNzb2NMMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiaW5kZW50IjoyLCJzb3J0S2V5IjozMDA0LCJwYXJlbnRJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDF8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJjaGlsZHJlbiI6WyJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfFBlcmZvcm0gYWN0aXZlIHNvdXJjaW5nIiwibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xSZWNydWl0IGVtcGxveWVlcyBhbmQgbWFuYWdlcnMiXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IkF0dHJhY3QgYW5kIGhpcmUgZW1wbG95ZWVzIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI2LTAxLTA3IiwiZW5kIjoiMjAyNi0wMy0xNiIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAwNSIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IktpZXNld2V0dGVyIEl2YW5hIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxBdHRyYWN0IGFuZCBoaXJlIGVtcGxveWVlcyJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiQXR0cmFjdCBhbmQgaGlyZSBlbXBsb3llZXMiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gQ09UIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNi0xNSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gQ09UIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IktpZXNld2V0dGVyIEl2YW5hIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxBdHRyYWN0IGFuZCBoaXJlIGVtcGxveWVlcyJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiQXR0cmFjdCBhbmQgaGlyZSBlbXBsb3llZXMiLCJsdmwiOiJMMiIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNi0xNSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IktpZXNld2V0dGVyIEl2YW5hIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxBdHRyYWN0IGFuZCBoaXJlIGVtcGxveWVlcyJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8Q3JlYXRlLCBhcHByb3ZlIGFuZCBwdWJsaXNoIHRyYWluaW5ncyBmb3IgSVQgd29ya2ZvcmNlIHdpdGhpbiBJVCBUcmFpbmluZyBDYXRhbG9ndWUiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMyIsIm5hbWUiOiJDcmVhdGUsIGFwcHJvdmUgYW5kIHB1Ymxpc2ggdHJhaW5pbmdzIGZvciBJVCB3b3JrZm9yY2Ugd2l0aGluIElUIFRyYWluaW5nIENhdGFsb2d1ZSIsImFzc29jTDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImluZGVudCI6Mywic29ydEtleSI6MzAwNCwicGFyZW50SWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfFBlcmZvcm0gb25ib2FyZGluZyIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IkNyZWF0ZSwgYXBwcm92ZSBhbmQgcHVibGlzaCB0cmFpbmluZ3MgZm9yIElUIHdvcmtmb3JjZSB3aXRoaW4gSVQgVHJhaW5pbmcgQ2F0YWxvZ3VlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJHcmFibWFpciBNZWxhbmllIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xDcmVhdGUsIGFwcHJvdmUgYW5kIHB1Ymxpc2ggdHJhaW5pbmdzIGZvciBJVCB3b3JrZm9yY2Ugd2l0aGluIElUIFRyYWluaW5nIENhdGFsb2d1ZSJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8SW1wbGVtZW50IGFuZCBtYWludGFpbiBJVCBqb2IgYXJjaGl0ZWN0dXJlIiwidHlwZSI6InByb2MiLCJwZyI6IlNQIiwibHZsIjoiTDMiLCJuYW1lIjoiSW1wbGVtZW50IGFuZCBtYWludGFpbiBJVCBqb2IgYXJjaGl0ZWN0dXJlIiwiYXNzb2NMMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjozMDA0LCJwYXJlbnRJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8TWFuYWdlIEhSNElUIHN0cmF0ZWd5LCBnb3Zlcm5hbmUgYW5kIGZyYW1ld29yayIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IkltcGxlbWVudCBhbmQgbWFpbnRhaW4gSVQgam9iIGFyY2hpdGVjdHVyZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiQW1lbGFuZyBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfEltcGxlbWVudCBhbmQgbWFpbnRhaW4gSVQgam9iIGFyY2hpdGVjdHVyZSJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIiwidHlwZSI6InByb2MiLCJwZyI6IlNQIiwibHZsIjoiTDMiLCJuYW1lIjoiTWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIiwiYXNzb2NMMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjozMDA0LCJwYXJlbnRJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8TWFuYWdlIEhSNElUIHN0cmF0ZWd5LCBnb3Zlcm5hbmUgYW5kIGZyYW1ld29yayIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hbmFnZSBIUjRJVCBzZXJ2aWNlIGRlbWFuZCIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDUtMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiQW1lbGFuZyBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBIUjRJVCBzZXJ2aWNlIGRlbWFuZCJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIENPVCIsInN0YXJ0IjoiMjAyNi0wNi0wMSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiQW1lbGFuZyBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBIUjRJVCBzZXJ2aWNlIGRlbWFuZCJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNi0wMSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiQW1lbGFuZyBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBIUjRJVCBzZXJ2aWNlIGRlbWFuZCJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExVUyIsInN0YXJ0IjoiMjAyNi0wNi0wMSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6IlJvbGxpbmdlciBBbGV4YW5kZXIgKExJUykiLCJsZWFkIjoiQW1lbGFuZyBOaWNvbGUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBIUjRJVCBzZXJ2aWNlIGRlbWFuZCJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8TWFuYWdlIEhSNElUIHN0cmF0ZWd5LCBnb3Zlcm5hbmUgYW5kIGZyYW1ld29yayIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwyIiwibmFtZSI6Ik1hbmFnZSBIUjRJVCBzdHJhdGVneSwgZ292ZXJuYW5lIGFuZCBmcmFtZXdvcmsiLCJhc3NvY0wxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJpbmRlbnQiOjIsInNvcnRLZXkiOjMwMDQsInBhcmVudElkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMXxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImNoaWxkcmVuIjpbIm58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UGxhbiBJVCB3b3JrZm9yY2UiLCJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfEltcGxlbWVudCBhbmQgbWFpbnRhaW4gSVQgam9iIGFyY2hpdGVjdHVyZSIsIm58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIEhSNElUIHNlcnZpY2UgZGVtYW5kIl0sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSFI0SVQgc3RyYXRlZ3ksIGdvdmVybmFuZSBhbmQgZnJhbWV3b3JrIiwibHZsIjoiTDIiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNS0xMC0wMSIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gRG9uZSIsInBjdCI6IjAuMDEiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6IkFtZWxhbmcgTmljb2xlIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxNYW5hZ2UgSFI0SVQgc3RyYXRlZ3ksIGdvdmVybmFuZSBhbmQgZnJhbWV3b3JrIn1dfSx7ImlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIiwidHlwZSI6InByb2MiLCJwZyI6IlNQIiwibHZsIjoiTDMiLCJuYW1lIjoiTWFuYWdlIElUIGdsb2JhbCBvcmllbnRhdGlvbiBwcm9ncmFtbWUgaW5jbC4gam9iIHNoYWRvd2luZyIsImFzc29jTDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImluZGVudCI6Mywic29ydEtleSI6MzAwNCwicGFyZW50SWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfFBlcmZvcm0gb25ib2FyZGluZyIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmciLCJsdmwiOiJMMyIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMTUiLCJlbmQiOiIyMDI2LTAzLTMxIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmcifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmciLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gQ09UIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNy0wMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gQ09UIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmcifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmciLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNy0wMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmcifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmciLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTFVTIiwic3RhcnQiOiIyMDI2LTA0LTAxIiwiZW5kIjoiMjAyNi0wNy0wMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTFVTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiw
7 | ibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBnbG9iYWwgb3JpZW50YXRpb24gcHJvZ3JhbW1lIGluY2wuIGpvYiBzaGFkb3dpbmcifV19LHsiaWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBza2lsbHMiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMyIsIm5hbWUiOiJNYW5hZ2UgSVQgc2tpbGxzIiwiYXNzb2NMMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjozMDA0LCJwYXJlbnRJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8UGVyZm9ybSBvbmJvYXJkaW5nIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFuYWdlIElUIHNraWxscyIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wMS0wMSIsImVuZCI6IjIwMjYtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBza2lsbHMifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hbmFnZSBJVCBza2lsbHMiLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gQ09UIiwic3RhcnQiOiIyMDI3LTAxLTAxIiwiZW5kIjoiMjAyNy0wNi0zMCIsImFjdHVhbCI6IiIsInBsYW5uZWQiOiJTY2hlZHVsZWQiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiR3JhYm1haXIgTWVsYW5pZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFuYWdlIElUIHNraWxscyJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiTWFuYWdlIElUIHNraWxscyIsImx2bCI6IkwzIiwicGhhc2UiOiJJbXBsZW1lbnRhdGlvbiBMSVMiLCJzdGFydCI6IjIwMjctMDEtMDEiLCJlbmQiOiIyMDI3LTA2LTMwIiwiYWN0dWFsIjoiIiwicGxhbm5lZCI6IlNjaGVkdWxlZCIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJHcmFibWFpciBNZWxhbmllIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgc2tpbGxzIn0seyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJNYW5hZ2UgSVQgc2tpbGxzIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExVUyIsInN0YXJ0IjoiMjAyNy0wMS0wMSIsImVuZCI6IjIwMjctMDYtMzAiLCJhY3R1YWwiOiIiLCJwbGFubmVkIjoiU2NoZWR1bGVkIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hbmFnZSBJVCBza2lsbHMifV19LHsiaWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hcHBpbmcgYW5kIGV2YWx1YXRlIElUIGNhcmVlciBsZXZlbCIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwzIiwibmFtZSI6Ik1hcHBpbmcgYW5kIGV2YWx1YXRlIElUIGNhcmVlciBsZXZlbCIsImFzc29jTDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImluZGVudCI6Mywic29ydEtleSI6MzAwNCwicGFyZW50SWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfFBlcmZvcm0gb25ib2FyZGluZyIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik1hcHBpbmcgYW5kIGV2YWx1YXRlIElUIGNhcmVlciBsZXZlbCIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNi0wNC0wMSIsImVuZCI6IjIwMjctMDEtMDEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IkdyYWJtYWlyIE1lbGFuaWUgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE1hcHBpbmcgYW5kIGV2YWx1YXRlIElUIGNhcmVlciBsZXZlbCJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8T25ib2FyZCBuZXcgSVQgZW1wbG95ZWUgYW5kIG1hbmFnZXIiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMyIsIm5hbWUiOiJPbmJvYXJkIG5ldyBJVCBlbXBsb3llZSBhbmQgbWFuYWdlciIsImFzc29jTDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImluZGVudCI6Mywic29ydEtleSI6MzAwNCwicGFyZW50SWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfFBlcmZvcm0gb25ib2FyZGluZyIsImNoaWxkcmVuIjpbXSwiaXRlbXMiOlt7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6Ik9uYm9hcmQgbmV3IElUIGVtcGxveWVlIGFuZCBtYW5hZ2VyIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTE2IiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDUiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiIiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE9uYm9hcmQgbmV3IElUIGVtcGxveWVlIGFuZCBtYW5hZ2VyIn1dfSx7ImlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xQZXJmb3JtIGFjdGl2ZSBzb3VyY2luZyIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwzIiwibmFtZSI6IlBlcmZvcm0gYWN0aXZlIHNvdXJjaW5nIiwiYXNzb2NMMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiaW5kZW50IjozLCJzb3J0S2V5IjozMDA0LCJwYXJlbnRJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8QXR0cmFjdCBhbmQgaGlyZSBlbXBsb3llZXMiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJQZXJmb3JtIGFjdGl2ZSBzb3VyY2luZyIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjYtMDQtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IktpZXNld2V0dGVyIEl2YW5hIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xQZXJmb3JtIGFjdGl2ZSBzb3VyY2luZyJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiUGVyZm9ybSBhY3RpdmUgc291cmNpbmciLCJsdmwiOiJMMyIsInBoYXNlIjoiSW1wbGVtZW50YXRpb24gTElTIiwic3RhcnQiOiIyMDI2LTAzLTAxIiwiZW5kIjoiMjAyNi0xMi0zMSIsImFjdHVhbCI6IkRlbGF5ZWQiLCJwbGFubmVkIjoiSW1wbGVtZW50YXRpb24gTElTIiwicGN0IjoiMCIsImNvbnN1bHRhbnQiOiJDaGVuIExlaWxlaSAoZXh0Lik7SHluZWsgVG9iaWFzIChMSVMpIiwibWFuYWdlciI6Ik1pZWxlbnogVGhvbWFzIChMTVQpIiwibGVhZCI6IktpZXNld2V0dGVyIEl2YW5hIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xQZXJmb3JtIGFjdGl2ZSBzb3VyY2luZyJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8UGVyZm9ybSBvbmJvYXJkaW5nIiwidHlwZSI6InByb2MiLCJwZyI6IlNQIiwibHZsIjoiTDIiLCJuYW1lIjoiUGVyZm9ybSBvbmJvYXJkaW5nIiwiYXNzb2NMMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiaW5kZW50IjoyLCJzb3J0S2V5IjozMDA0LCJwYXJlbnRJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDF8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJjaGlsZHJlbiI6WyJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfFByZS1ib2FyZCBuZXcgSVQgZW1wbG95ZWUgYW5kIG1hbmFnZXIiLCJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfE9uYm9hcmQgbmV3IElUIGVtcGxveWVlIGFuZCBtYW5hZ2VyIiwibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xDcmVhdGUsIGFwcHJvdmUgYW5kIHB1Ymxpc2ggdHJhaW5pbmdzIGZvciBJVCB3b3JrZm9yY2Ugd2l0aGluIElUIFRyYWluaW5nIENhdGFsb2d1ZSIsIm58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8TWFwcGluZyBhbmQgZXZhbHVhdGUgSVQgY2FyZWVyIGxldmVsIiwibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgc2tpbGxzIiwibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xNYW5hZ2UgSVQgZ2xvYmFsIG9yaWVudGF0aW9uIHByb2dyYW1tZSBpbmNsLiBqb2Igc2hhZG93aW5nIl0sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJQZXJmb3JtIG9uYm9hcmRpbmciLCJsdmwiOiJMMiIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjUtMTAtMTYiLCJlbmQiOiIyMDI2LTA0LTMwIiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwbGFubmVkIjoiRWxhYm9yYXRpb24gaW4gcHJvZ3Jlc3MiLCJwY3QiOiIwLjAwMjUiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiIiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfFBlcmZvcm0gb25ib2FyZGluZyJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UGxhbiBJVCB3b3JrZm9yY2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMyIsIm5hbWUiOiJQbGFuIElUIHdvcmtmb3JjZSIsImFzc29jTDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImluZGVudCI6Mywic29ydEtleSI6MzAwNCwicGFyZW50SWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfE1hbmFnZSBIUjRJVCBzdHJhdGVneSwgZ292ZXJuYW5lIGFuZCBmcmFtZXdvcmsiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJQbGFuIElUIHdvcmtmb3JjZSIsImx2bCI6IkwzIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0xNiIsImVuZCI6IjIwMjUtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJBbWVsYW5nIE5pY29sZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UGxhbiBJVCB3b3JrZm9yY2UifSx7InBnIjoiU1AiLCJsMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwicHJvYyI6IlBsYW4gSVQgd29ya2ZvcmNlIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wMS0wMSIsImVuZCI6IjIwMjYtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJSb2xsaW5nZXIgQWxleGFuZGVyIChMSVMpIiwibGVhZCI6IkFtZWxhbmcgTmljb2xlIChMSVMpIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xQbGFuIElUIHdvcmtmb3JjZSJ9XX0seyJpZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UHJlLWJvYXJkIG5ldyBJVCBlbXBsb3llZSBhbmQgbWFuYWdlciIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwzIiwibmFtZSI6IlByZS1ib2FyZCBuZXcgSVQgZW1wbG95ZWUgYW5kIG1hbmFnZXIiLCJhc3NvY0wxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJpbmRlbnQiOjMsInNvcnRLZXkiOjMwMDQsInBhcmVudElkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxQZXJmb3JtIG9uYm9hcmRpbmciLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJQcmUtYm9hcmQgbmV3IElUIGVtcGxveWVlIGFuZCBtYW5hZ2VyIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTE2IiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiIiwibm9kZUlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMM3xQcmUtYm9hcmQgbmV3IElUIGVtcGxveWVlIGFuZCBtYW5hZ2VyIn1dfSx7ImlkIjoibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMXxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwxIiwibmFtZSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiYXNzb2NMMSI6IlByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlIiwiaW5kZW50IjoxLCJzb3J0S2V5IjozMDA0LCJwYXJlbnRJZCI6InBnfFNQIiwiY2hpbGRyZW4iOlsibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxNYW5hZ2UgSFI0SVQgc3RyYXRlZ3ksIGdvdmVybmFuZSBhbmQgZnJhbWV3b3JrIiwibnxTUHxQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZXxMMnxBdHRyYWN0IGFuZCBoaXJlIGVtcGxveWVlcyIsIm58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDJ8UGVyZm9ybSBvbmJvYXJkaW5nIl0sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsInByb2MiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImx2bCI6IkwxIiwicGhhc2UiOiJFbGFib3JhdGlvbiIsInN0YXJ0IjoiMjAyNS0xMC0wMSIsImVuZCI6IjIwMjUtMTAtMDEiLCJhY3R1YWwiOiJFbGFib3JhdGlvbiBEb25lIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIERvbmUiLCJwY3QiOiIwLjAxIiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiUm9sbGluZ2VyIEFsZXhhbmRlciAoTElTKSIsImxlYWQiOiJBbWVsYW5nIE5pY29sZSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDF8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UifV19LHsiaWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfFJlY3J1aXQgZW1wbG95ZWVzIGFuZCBtYW5hZ2VycyIsInR5cGUiOiJwcm9jIiwicGciOiJTUCIsImx2bCI6IkwzIiwibmFtZSI6IlJlY3J1aXQgZW1wbG95ZWVzIGFuZCBtYW5hZ2VycyIsImFzc29jTDEiOiJQcm92aWRlIGFuZCBkZXZlbG9wIElUIHdvcmtmb3JjZSIsImluZGVudCI6Mywic29ydEtleSI6MzAwNCwicGFyZW50SWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwyfEF0dHJhY3QgYW5kIGhpcmUgZW1wbG95ZWVzIiwiY2hpbGRyZW4iOltdLCJpdGVtcyI6W3sicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiUmVjcnVpdCBlbXBsb3llZXMgYW5kIG1hbmFnZXJzIiwibHZsIjoiTDMiLCJwaGFzZSI6IkVsYWJvcmF0aW9uIiwic3RhcnQiOiIyMDI1LTEwLTAxIiwiZW5kIjoiMjAyNi0wNC0zMCIsImFjdHVhbCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGxhbm5lZCI6IkVsYWJvcmF0aW9uIGluIHByb2dyZXNzIiwicGN0IjoiMC4wMDI1IiwiY29uc3VsdGFudCI6IkNoZW4gTGVpbGVpIChleHQuKTtIeW5layBUb2JpYXMgKExJUykiLCJtYW5hZ2VyIjoiTWllbGVueiBUaG9tYXMgKExNVCkiLCJsZWFkIjoiS2llc2V3ZXR0ZXIgSXZhbmEgKExJUykiLCJub2RlSWQiOiJufFNQfFByb3ZpZGUgYW5kIGRldmVsb3AgSVQgd29ya2ZvcmNlfEwzfFJlY3J1aXQgZW1wbG95ZWVzIGFuZCBtYW5hZ2VycyJ9LHsicGciOiJTUCIsImwxIjoiUHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2UiLCJwcm9jIjoiUmVjcnVpdCBlbXBsb3llZXMgYW5kIG1hbmFnZXJzIiwibHZsIjoiTDMiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wMy0wMSIsImVuZCI6IjIwMjYtMTItMzEiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiQ2hlbiBMZWlsZWkgKGV4dC4pO0h5bmVrIFRvYmlhcyAoTElTKSIsIm1hbmFnZXIiOiJNaWVsZW56IFRob21hcyAoTE1UKSIsImxlYWQiOiJLaWVzZXdldHRlciBJdmFuYSAoTElTKSIsIm5vZGVJZCI6Im58U1B8UHJvdmlkZSBhbmQgZGV2ZWxvcCBJVCB3b3JrZm9yY2V8TDN8UmVjcnVpdCBlbXBsb3llZXMgYW5kIG1hbmFnZXJzIn1dfSx7ImlkIjoibnxTUHxFbnN1cmUgcGVyZm9ybWFuY2UgYW5kIGNvbmZvcm1hbmNlIG9mIElUIHNlcnZpY2VzfEwxfEVuc3VyZSBwZXJmb3JtYW5jZSBhbmQgY29uZm9ybWFuY2Ugb2YgSVQgc2VydmljZXMiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMSIsIm5hbWUiOiJFbnN1cmUgcGVyZm9ybWFuY2UgYW5kIGNvbmZvcm1hbmNlIG9mIElUIHNlcnZpY2VzIiwiYXNzb2NMMSI6IkVuc3VyZSBwZXJmb3JtYW5jZSBhbmQgY29uZm9ybWFuY2Ugb2YgSVQgc2VydmljZXMiLCJpbmRlbnQiOjEsInNvcnRLZXkiOjMwMDUsInBhcmVudElkIjoicGd8U1AiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJFbnN1cmUgcGVyZm9ybWFuY2UgYW5kIGNvbmZvcm1hbmNlIG9mIElUIHNlcnZpY2VzIiwicHJvYyI6IkVuc3VyZSBwZXJmb3JtYW5jZSBhbmQgY29uZm9ybWFuY2Ugb2YgSVQgc2VydmljZXMiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDQtMTUiLCJlbmQiOiIyMDI2LTA2LTMwIiwiYWN0dWFsIjoiRGVsYXllZCIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBpbiBwcm9ncmVzcyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiPyIsIm5vZGVJZCI6Im58U1B8RW5zdXJlIHBlcmZvcm1hbmNlIGFuZCBjb25mb3JtYW5jZSBvZiBJVCBzZXJ2aWNlc3xMMXxFbnN1cmUgcGVyZm9ybWFuY2UgYW5kIGNvbmZvcm1hbmNlIG9mIElUIHNlcnZpY2VzIn1dfSx7ImlkIjoibnxTUHxNYW5hZ2UgSVQga25vd2xlZGdlfEwxfE1hbmFnZSBJVCBrbm93bGVkZ2UiLCJ0eXBlIjoicHJvYyIsInBnIjoiU1AiLCJsdmwiOiJMMSIsIm5hbWUiOiJNYW5hZ2UgSVQga25vd2xlZGdlIiwiYXNzb2NMMSI6Ik1hbmFnZSBJVCBrbm93bGVkZ2UiLCJpbmRlbnQiOjEsInNvcnRLZXkiOjMwMDYsInBhcmVudElkIjoicGd8U1AiLCJjaGlsZHJlbiI6W10sIml0ZW1zIjpbeyJwZyI6IlNQIiwibDEiOiJNYW5hZ2UgSVQga25vd2xlZGdlIiwicHJvYyI6Ik1hbmFnZSBJVCBrbm93bGVkZ2UiLCJsdmwiOiJMMSIsInBoYXNlIjoiRWxhYm9yYXRpb24iLCJzdGFydCI6IjIwMjYtMDEtMjAiLCJlbmQiOiIyMDI2LTAyLTI1IiwiYWN0dWFsIjoiRWxhYm9yYXRpb24gRG9uZSIsInBsYW5uZWQiOiJFbGFib3JhdGlvbiBEb25lIiwicGN0IjoiMC4wMSIsImNvbnN1bHRhbnQiOiJTY2hyb2VkZXIgTWljaGFlbCAoTElTKSIsIm1hbmFnZXIiOiJTaW50IFJhY2hlbCAoTEJIKSIsImxlYWQiOiJLdWVyc2NobmVyIFBoaWxpcHAgKExJUykiLCJub2RlSWQiOiJufFNQfE1hbmFnZSBJVCBrbm93bGVkZ2V8TDF8TWFuYWdlIElUIGtub3dsZWRnZSJ9LHsicGciOiJTUCIsImwxIjoiTWFuYWdlIElUIGtub3dsZWRnZSIsInByb2MiOiJNYW5hZ2UgSVQga25vd2xlZGdlIiwibHZsIjoiTDEiLCJwaGFzZSI6IkltcGxlbWVudGF0aW9uIExJUyIsInN0YXJ0IjoiMjAyNi0wNC0xNSIsImVuZCI6IjIwMjYtMDYtMzAiLCJhY3R1YWwiOiJEZWxheWVkIiwicGxhbm5lZCI6IkltcGxlbWVudGF0aW9uIExJUyIsInBjdCI6IjAiLCJjb25zdWx0YW50IjoiU2Nocm9lZGVyIE1pY2hhZWwgKExJUykiLCJtYW5hZ2VyIjoiU2ludCBSYWNoZWwgKExCSCkiLCJsZWFkIjoiS3VlcnNjaG5lciBQaGlsaXBwIChMSVMpIiwibm9kZUlkIjoibnxTUHxNYW5hZ2UgSVQga25vd2xlZGdlfEwxfE1hbmFnZSBJVCBrbm93bGVkZ2UifV19XX0=</textarea> <script> const dataEl=document.getElementById('dataB64'); const rawB64=((dataEl&&(dataEl.value¦¦dataEl.textContent))?(dataEl.value¦¦dataEl.textContent):'').replace(/s+/g,''); function fromBase64Utf8(b64){ try{ const bin=atob(b64); const bytes=new Uint8Array(bin.length); for(let i=0;i<bin.length;i++) bytes[i]=bin.charCodeAt(i); return new TextDecoder('utf-8').decode(bytes); }catch(e){ console.warn('Base64 decode failed',e); return ''; } } let PAYLOAD={data:[],nodes:[]}; const decoded=fromBase64Utf8(rawB64); if(decoded){ try{ PAYLOAD=JSON.parse(decoded);}catch(e){ console.warn('JSON parse failed',e);} } let DATA=Array.isArray(PAYLOAD.data)?PAYLOAD.data:[]; let NODES=Array.isArray(PAYLOAD.nodes)?PAYLOAD.nodes:[]; const DATA_RAWLEN=rawB64.length; const el=function(id){return document.getElementById(id);}; const fGroup=el('fGroup'), fL1=el('fL1'), fConsultant=el('fConsultant'), fManager=el('fManager'), fLead=el('fLead'); const labelsEl=el('labels'), barsEl=el('bars'), axisEl=el('axis'), legendEl=el('legend'); const detailBody=el('detailBody'), countInfo=el('countInfo'); const chipDelayed=el('chipDelayed'), chipReset=el('chipReset'); const btnExpand=el('btnExpand'), btnCollapse=el('btnCollapse'); const timeline=el('timeline'); const phaseColors={'Elaboration':'#8b5cf6','Implementation LIS':'#2563eb','Implementation LUS':'#10b981','Implementation COT':'#06b6d4'}; const phaseOrder=['Elaboration','Implementation LIS','Implementation LUS','Implementation COT']; let selectedPhases=new Set(phaseOrder); const expanded=new Set(); function setDefaultExpanded(){ expanded.clear(); for(var i=0;i<NODES.length;i++){ var n=NODES[i]; if(n.type==='pg'¦¦n.lvl==='L1'){ expanded.add(n.id);} } } function isDelayed(it){ var a=(it.actual¦¦'').toLowerCase(); var p=(it.planned¦¦'').toLowerCase(); return a.indexOf('delayed')>=0 ¦¦ p.indexOf('delayed')>=0; } function phaseColor(phase){ return phaseColors[phase]¦¦'#94a3b8'; } function dateMs(s){ var d=new Date(s); var t=d.getTime(); return isNaN(t)?null:t; } function rollupRange(items){ var min=null,max=null; for(var i=0;i<items.length;i++){ var it=items[i]; var s=dateMs(it.start), e=dateMs(it.end); if(s===null¦¦e===null) continue; if(min===null¦¦s<min) min=s; if(max===null¦¦e>max) max=e; } if(min===null¦¦max===null) return null; return {start:min,end:max}; } function escapeHtml(s){ return String(s¦¦'').replace(/[&<>\"']/g,function(c){return {'&':'&amp;','<':'&lt;','>':'&gt;','\"':'&quot;',''':'&#39;'}[c];}); } function buildL1(){ var pg=fGroup.value; var set=new Set(); for(var i=0;i<DATA.length;i++){ var d=DATA[i]; if(pg && d.pg!==pg) continue; if(d.l1) set.add(d.l1); } var arr=Array.from(set); arr.sort(); var html='<option value="">All L1 Processes</option>'; for(i=0;i<arr.length;i++){ html+='<option value="'+escapeHtml(arr[i])+'">'+escapeHtml(arr[i])+'</option>'; } fL1.innerHTML=html; } function currentFiltered(applyPhase){ if(applyPhase===undefined) applyPhase=true; var pg=fGroup.value, l1=fL1.value; var c=fConsultant.value, m=fManager.value, l=fLead.value; var out=[]; for(var i=0;i<DATA.length;i++){ var it=DATA[i]; if(pg && it.pg!==pg) continue; if(l1 && it.l1!==l1) continue; if(c && it.consultant!==c) continue; if(m && it.manager!==m) continue; if(l && it.lead!==l) continue; if(chipDelayed.classList.contains('active') && !isDelayed(it)) continue; if(applyPhase && !selectedPhases.has(it.phase)) continue; out.push(it); } return out; } function buildRoleFilters(){ var items=currentFiltered(false); function uniq(get){ var s=new Set(); for(var i=0;i<items.length;i++){ var v=get(items[i]); if(v) s.add(v);} var a=Array.from(s); a.sort(); return a; } function fill(sel,label,arr){ var cur=sel.value; var html='<option value="">'+label+'</option>'; for(var i=0;i<arr.length;i++){ html+='<option value="'+escapeHtml(arr[i])+'">'+escapeHtml(arr[i])+'</option>'; } sel.innerHTML=html; if(cur && arr.indexOf(cur)!==-1){ sel.value=cur; return false; } sel.value=''; return cur!==''; } var cleared=false; cleared = fill(fConsultant,'IT Process Consultant',uniq(function(x){return x.consultant;})) ¦¦ cleared; cleared = fill(fManager,'IT Process Manager',uniq(function(x){return x.manager;})) ¦¦ cleared; cleared = fill(fLead,'IT Process Initiative Lead',uniq(function(x){return x.lead;})) ¦¦ cleared; return cleared; } function buildFilters(){ var order={'MP':1,'CP':2,'SP':3}; var set=new Set(); for(var i=0;i<DATA.length;i++){ if(DATA[i].pg) set.add(DATA[i].pg);} var pgs=Array.from(set); pgs.sort(function(a,b){ return (order[a]¦¦99)-(order[b]¦¦99) ¦¦ a.localeCompare(b);}); var html='<option value="">All Process Groups</option>'; for(i=0;i<pgs.length;i++){ html+='<option value="'+pgs[i]+'">'+pgs[i]+'</option>'; } fGroup.innerHTML=html; buildL1(); buildRoleFilters(); } function visibleRows(){ var byId=new Map(); for(var i=0;i<NODES.length;i++){ byId.set(NODES[i].id,NODES[i]); } function getChildren(id){ var n=byId.get(id); return (n&&n.children)?n.children:[]; } var order={'MP':1,'CP':2,'SP':3}; var pgNodes=NODES.filter(function(n){return n.type==='pg';}).sort(function(a,b){return (order[a.pg]¦¦99)-(order[b.pg]¦¦99);}); var out=[]; function walk(id,indent){ var n=byId.get(id); if(!n) return; out.push({node:n,indent:indent}); if(expanded.has(id)){ var kids=getChildren(id); for(var k=0;k<kids.length;k++){ walk(kids[k], Math.min(indent+1,4)); } } } for(i=0;i<pgNodes.length;i++){ if(fGroup.value && pgNodes[i].pg!==fGroup.value) continue; walk(pgNodes[i].id,0); } return out; } function renderLegend(){ legendEl.innerHTML=''; for(var i=0;i<phaseOrder.length;i++){ (function(ph){ var d=document.createElement('div'); d.className='legItem'+(selectedPhases.has(ph)?'':' off'); d.innerHTML='<span class="sw" style="background:'+phaseColor(ph)+'"></span><span>'+ph+'</span>'; d.addEventListener('click',function(){ if(selectedPhases.has(ph)) selectedPhases.delete(ph); else selectedPhases.add(ph); render();}); legendEl.appendChild(d); })(phaseOrder[i]); } var dd=document.createElement('div'); dd.className='legItem'; dd.innerHTML='<span class="sw" style="background:#fff;border:2px dashed rgba(239,68,68,.9)"></span><span>Delayed</span>'; legendEl.appendChild(dd); } function renderTodayLine(domainStart,domainEnd){ var now=new Date(); var t=now.getTime(); if(t<domainStart¦¦t>domainEnd) return; var span=domainEnd-domainStart; var x=((t-domainStart)/span)*100; var line=document.getElementById('todayLine'); if(!line){ line=document.createElement('div'); line.id='todayLine'; line.className='todayLine'; barsEl.appendChild(line);} line.style.left=x+'%'; } function renderDetail(items){ detailBody.innerHTML=''; var max=Math.min(items.length,300); var html=''; for(var i=0;i<max;i++){ var it=items[i]; var pct=it.pct?Math.round(parseFloat(it.pct)*100)+'%':''; var status=isDelayed(it)?'Delayed':(it.actual¦¦it.planned¦¦''); html+='<tr><td>'+escapeHtml(it.proc¦¦'')+'</td><td>'+escapeHtml(it.lvl¦¦'')+'</td><td>'+escapeHtml(it.phase¦¦'')+'</td><td>'+escapeHtml(it.start¦¦'')+'</td><td>'+escapeHtml(it.end¦¦'')+'</td><td>'+escapeHtml(pct)+'</td><td>'+escapeHtml(it.lead¦¦'')+'</td><td>'+escapeHtml(it.manager¦¦'')+'</td><td>'+escapeHtml(it.consultant¦¦'')+'</td><td>'+escapeHtml(status)+'</td></tr>'; } detailBody.innerHTML=html; } function render(){ var items=currentFiltered(true); countInfo.textContent=items.length+' tasks (with Start/End)'; var allRange=rollupRange(items); if(!allRange){ labelsEl.innerHTML='<div class="hint" style="padding:12px;">No data to display. If this is unexpected, please re-export the HTML (copy ALL chunks) and ensure it is saved as .html.</div>'; barsEl.innerHTML=''; axisEl.innerHTML=''; detailBody.innerHTML=''; renderLegend(); return; } var domainStart=allRange.start, domainEnd=allRange.end, span=domainEnd-domainStart; axisEl.innerHTML=''; var startD=new Date(domainStart), endD=new Date(domainEnd); var first=new Date(startD.getFullYear(), startD.getMonth(), 1); for(var d=new Date(first); d<=endD; d=new Date(d.getFullYear(), d.getMonth()+1, 1)){ var x=((d.getTime()-domainStart)/span)*100; var tick=document.createElement('div'); tick.className='tick'; tick.style.left=x+'%'; var lab=d.toLocaleDateString('en-US',{month:'short',year:'2-digit'}); tick.innerHTML='<span>'+lab+'</span>'; axisEl.appendChild(tick);} labelsEl.innerHTML=''; barsEl.innerHTML=''; var byNode=new Map(); for(var i=0;i<items.length;i++){ var it=items[i]; if(!byNode.has(it.nodeId)) byNode.set(it.nodeId,[]); byNode.get(it.nodeId).push(it);} var rows=visibleRows(); for(i=0;i<rows.length;i++){ var n=rows[i].node; var hasItems=byNode.has(n.id); var hasKids=(n.children&&n.children.length); if(n.type!=='pg' && !hasItems && !hasKids) continue; var label=document.createElement('div'); var isPg=(n.type==='pg'); var isL1=(n.lvl==='L1'); var cls='labelRow '+(isPg?'pg ':'')+(isL1?'l1 ':'')+'indent-'+Math.min(rows[i].indent,4); if(isPg){ cls+=' pg-'+String(n.pg¦¦'').toLowerCase(); } label.className=cls; var canToggle=hasKids; var tog=document.createElement('div'); tog.className='toggle'+(canToggle?'':' hidden'); tog.textContent=canToggle?(expanded.has(n.id)?'-':'+'):''; if(canToggle){ (function(id){ tog.addEventListener('click',function(ev){ ev.stopPropagation(); if(expanded.has(id)) expanded.delete(id); else expanded.add(id); render();}); })(n.id);} var name=document.createElement('div'); name.className='name'; if(isPg){ name.textContent=(n.pg==='MP'?'Management Processes':(n.pg==='CP'?'Core Processes':(n.pg==='SP'?'Support Processes':n.name))); } else { name.textContent=n.name; } label.appendChild(tog); label.appendChild(name); labelsEl.appendChild(label); var timeRow=document.createElement('div'); timeRow.className='timeRow'; var rowItems=[]; if(isPg){ for(var j=0;j<items.length;j++){ if(items[j].pg===n.pg) rowItems.push(items[j]); } } else { if(hasItems) rowItems=rowItems.concat(byNode.get(n.id)); } var rr=rollupRange(rowItems); if(rr){ var left=((rr.start-domainStart)/span)*100; var width=Math.max(0.6,((rr.end-rr.start)/span)*100); var b=document.createElement('div'); b.className='bar rollup'+(rowItems.some(isDelayed)?' delayed':''); b.style.left=left+'%'; b.style.width=width+'%'; var pgCol=(n.pg==='MP')?getComputedStyle(document.documentElement).getPropertyValue('--pg-mp'):(n.pg==='CP'?getComputedStyle(document.documentElement).getPropertyValue('--pg-cp'):getComputedStyle(document.documentElement).getPropertyValue('--pg-sp')); b.style.background=isPg?pgCol:(isL1?'rgba(100,116,139,.85)':'rgba(148,163,184,.9)'); timeRow.appendChild(b);} if(hasItems){ var these=byNode.get(n.id).slice().sort(function(a,b){return phaseOrder.indexOf(a.phase)-phaseOrder.indexOf(b.phase);}); for(var j=0;j<these.length;j++){ var it=these[j]; var s=dateMs(it.start), e=dateMs(it.end); var left=((s-domainStart)/span)*100; var width=Math.max(0.6,((e-s)/span)*100); var bb=document.createElement('div'); bb.className='bar'+(isDelayed(it)?' delayed':''); bb.style.left=left+'%'; bb.style.width=width+'%'; bb.style.top=(6+(j%2)*10)+'px'; bb.style.height='10px'; bb.style.background=phaseColor(it.phase); timeRow.appendChild(bb);} } barsEl.appendChild(timeRow);} renderTodayLine(domainStart,domainEnd); renderLegend(); renderDetail(items); labelsEl.scrollTop=timeline.scrollTop; } timeline.addEventListener('scroll',function(){ labelsEl.scrollTop=timeline.scrollTop; }); labelsEl.addEventListener('wheel',function(e){ timeline.scrollTop += e.deltaY; e.preventDefault(); },{passive:false}); btnExpand.addEventListener('click',function(){ expanded.clear(); for(var i=0;i<NODES.length;i++){ var n=NODES[i]; if(n.children && n.children.length) expanded.add(n.id);} render();}); btnCollapse.addEventListener('click',function(){ expanded.clear(); for(var i=0;i<NODES.length;i++){ var n=NODES[i]; if(n.type==='pg') expanded.add(n.id);} render();}); chipDelayed.addEventListener('click',function(){ chipDelayed.classList.toggle('active'); render();}); chipReset.addEventListener('click',function(){ fGroup.value=''; buildL1(); fL1.value=''; fConsultant.value=''; fManager.value=''; fLead.value=''; chipDelayed.classList.remove('active'); setDefaultExpanded(); buildRoleFilters(); render();}); fGroup.addEventListener('change',function(){ buildL1(); buildRoleFilters(); render();}); fL1.addEventListener('change',function(){ buildRoleFilters(); render();}); fConsultant.addEventListener('change',function(){ buildRoleFilters(); render();}); fManager.addEventListener('change',function(){ buildRoleFilters(); render();}); fLead.addEventListener('change',function(){ buildRoleFilters(); render();}); buildFilters(); setDefaultExpanded(); render(); </script> </body> </html>