## Cockpit
IT | IT Process Portfolio – Cockpit
Datenstand Draft April 2026 · Quelle: Process_Portfolio_Timeline.xlsx · Mappe erzeugt am 01.09.2026
Auswahlfelder ändern – Kennzahlen, Diagramme und Liste rechnen sofort neu.
| PROZESSGRUPPE | INITIATIVE | L1-PROZESS | EBENE | STATUS | PROCESS MANAGER | STICHTAG
| (Alle) | (Alle) | (Alle) | (Alle) | (Alle) | (Alle) | 2026-09-01
| PROZESSE IM FILTER | Ø FORTSCHRITT | VERZÖGERT | ÜBERFÄLLIG | ELABORATION FERTIG | IN IMPLEMENTIERUNG | TERMINE IN 90 TAGEN
| 124 | 40.4% | 29 | 52 | 30 | 20 | 8
PROZESSE IM FILTER – VERZÖGERTE ZUERST, ERSTE 15
| Prozess | Gruppe | Status | % fertig | Ende | Process Manager
| Analyse architecture impact | CP | Verzögert | 100% | 2026-04-30 | Mielenz Thomas (LMT)
| Approve IT demand | CP | Verzögert | 100% | 2026-03-31 | Mielenz Thomas (LMT)
| Attract and hire employees | SP | Verzögert | 18% | 2026-12-31 | Mielenz Thomas (LMT)
| Define solution target architecture | CP | Verzögert | 50% | 2026-06-22 | Nussbaumer Florian (LBC)
| Ensure performance and conformance of IT services | SP | Verzögert | 0% | 0 | Sint Rachel (LBH)
| Evaluate and qualify IT demand | CP | Verzögert | 100% | 2026-04-30 | Mielenz Thomas (LMT)
| Handle IT service order | CP | Verzögert | 0% | 2026-06-17 | Schnurrenberger Christoph (LIS-LIN)
| Implement and maintain IT job architecture | SP | Verzögert | 0% | 2026-05-31 | Rollinger Alexander (LIS)
| Maintain IT glossary | MP | Verzögert | 25% | 2026-01-17 | Mielenz Thomas (LMT)
| Manage HR4IT service demand | SP | Verzögert | 0% | 2026-06-30 | Rollinger Alexander (LIS)
| Manage IT global orientation programme incl. job shadowing | SP | Verzögert | 0% | 2026-07-01 | Mielenz Thomas (LMT)
| Manage IT knowledge | SP | Verzögert | 100% | 2026-06-30 | Sint Rachel (LBH)
| Manage IT project portfolio | MP | Verzögert | 100% | 2026-05-31 | Rollinger Alexander (LIS)
| Manage IT service provision request | CP | Verzögert | 0% | 2026-06-17 | Schnurrenberger Christoph (LIS-LIN)
| Manage IT skills | SP | Verzögert | 0% | 2027-06-30 | Mielenz Thomas (LMT)

## Prozesse
Nr | Prozess | Pfad | Gruppe | Initiative | L1-Prozess | Ebene | Status | Fortschritt | Start | Ende | Dauer (T) | Elaboration | Initiative Lead | Process Manager | Consultant | Überfällig | In Implementierung | Treffer | Rang
1 | Analyse architecture impact | Plan IT service › Evaluate and qualify IT demand › Analyse architecture impact | CP | Corporate IT body | Plan IT service | L3 | Verzögert | 100% | 2025-08-01 | 2026-04-30 | 195 | Abgeschlossen | Pernet Benoit (LEC)) | Mielenz Thomas (LMT) | Kunz Christina (LIS-MHP) | 1 | 1 | 1 | 1
2 | Approve IT demand | Plan IT service › Approve IT demand | CP | Corporate IT body | Plan IT service | L2 | Verzögert | 100% | 2025-08-01 | 2026-03-31 | 1 | Abgeschlossen | Spieth Tina (LIS) | Mielenz Thomas (LMT) | Kunz Christina (LIS-MHP) | 1 | 1 | 1 | 2
3 | Attract and hire employees | Provide and develop IT workforce › Attract and hire employees | SP | HR initiatives for IT | Provide and develop IT workforce | L2 | Verzögert | 18% | 2025-10-01 | 2026-12-31 | 327 | In Arbeit | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 3
4 | Define solution target architecture | Build IT Service › Design IT service › Define solution target architecture | CP | Architecture management | Build IT Service | L3 | Verzögert | 50% | 2026-01-14 | 2026-06-22 | 114 | In Arbeit | Hammer Marco (AER) | Nussbaumer Florian (LBC) | Hoermann Patrick (LLI) | 1 | 0 | 1 | 4
5 | Ensure performance and conformance of IT services | Ensure performance and conformance of IT services | SP | ITSM | Ensure performance and conformance of IT services | L1 | Verzögert | 0% |  |  |  | Verzögert | – | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 5
6 | Evaluate and qualify IT demand | Plan IT service › Evaluate and qualify IT demand | CP | Corporate IT body | Plan IT service | L2 | Verzögert | 100% | 2025-08-01 | 2026-04-30 | 195 | Abgeschlossen | Spieth Tina (LIS) | Mielenz Thomas (LMT) | Kunz Christina (LIS-MHP) | 1 | 1 | 1 | 6
7 | Handle IT service order | Deliver IT service › Handle IT service order | CP | ITSM | Deliver IT service | L2 | Verzögert | 0% | 2026-04-01 | 2026-06-17 | 56 | Verzögert | – | Schnurrenberger Christoph (LIS-LIN) | – | 1 | 0 | 1 | 7
8 | Implement and maintain IT job architecture | Provide and develop IT workforce › Manage HR4IT strategy, governane and framework › Implement and maintain IT job architecture | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 0% | 2025-10-16 | 2026-05-31 | 162 | Verzögert | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 8
9 | Maintain IT glossary | Manage IT governance framework › Maintain IT glossary | MP | Corporate IT body | Manage IT governance framework | L2 | Verzögert | 25% | 2026-01-07 | 2026-01-17 | 8 | Ohne Angabe | Felder Max (LLI) | Mielenz Thomas (LMT) | Kunz Christina (LIS-MHP) | 1 | 0 | 1 | 9
10 | Manage HR4IT service demand | Provide and develop IT workforce › Manage HR4IT strategy, governane and framework › Manage HR4IT service demand | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 0% | 2025-10-01 | 2026-06-30 | 195 | Verzögert | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 10
11 | Manage IT global orientation programme incl. job shadowing | Provide and develop IT workforce › Perform, learn and grow › Manage IT global orientation programme incl. job shadowing | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 0% | 2026-01-15 | 2026-07-01 | 120 | Verzögert | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 11
12 | Manage IT knowledge | Manage IT knowledge | SP | ITSM | Manage IT knowledge | L1 | Verzögert | 100% | 2026-01-20 | 2026-06-30 | 116 | Abgeschlossen | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 1 | 1 | 1 | 12
13 | Manage IT project portfolio | Manage IT portfolio › Manage IT project portfolio | MP | IT project management | Manage IT portfolio | L2 | Verzögert | 100% | 2025-11-10 | 2026-05-31 | 145 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 1 | 0 | 1 | 13
14 | Manage IT service provision request | Deliver IT service › Manage IT service provision request | CP | ITSM | Deliver IT service | L2 | Verzögert | 0% | 2026-04-01 | 2026-06-17 | 56 | Verzögert | – | Schnurrenberger Christoph (LIS-LIN) | – | 1 | 0 | 1 | 14
15 | Manage IT skills | Provide and develop IT workforce › Perform, learn and grow › Manage IT skills | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 0% | 2026-01-01 | 2027-06-30 | 390 | Verzögert | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 15
16 | Manage IT stakeholder relationships | Manage IT stakeholder relationships | MP | Corporate IT body | Manage IT stakeholder relationships | L1 | Verzögert | 0% | 2026-04-01 | 2026-12-23 | 191 | Verzögert | Felder Max (LLI) | Mielenz Thomas (LMT) | Kreis Andreas (LLI) | 0 | 0 | 1 | 16
17 | Manage continuous improvement | Manage IT processes and continuous improvement › Manage continuous improvement | MP | ITSM | Manage IT processes and continuous improvement | L2 | Verzögert | 0% | 2025-10-01 | 2026-01-30 | 88 | Verzögert | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | Boehme Matthias (LIS-BPMO), Rollinger Alexander (LIS) | 1 | 0 | 1 | 17
18 | Manage enterprise architecture | Manage enterprise architecture | MP | Corporate IT body | Manage enterprise architecture | L1 | Verzögert | 0% | 2025-10-16 | 2026-07-16 | 195.85 | Verzögert | – | – | – | 1 | 0 | 1 | 18
19 | Mapping and evaluate IT career level | Provide and develop IT workforce › Perform, learn and grow › Mapping and evaluate IT career level | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 0% | 2026-04-01 | 2027-01-01 | 198 | Verzögert | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 19
20 | Operate and maintain IT service | Run IT service › Operate and maintain IT service | CP | ITSM | Run IT service | L2 | Verzögert | 21% | 2025-10-15 | 2026-06-30 | 185 | Verzögert | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 1 | 0 | 1 | 20
21 | Perform active sourcing | Provide and develop IT workforce › Attract and hire employees › Perform active sourcing | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 0% | 2025-10-01 | 2026-12-31 | 327 | Verzögert | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 21
22 | Perform initial assessment of customer need | Plan IT service › Perform initial assessment of customer need | CP | Corporate IT body | Plan IT service | L2 | Verzögert | 100% | 2025-08-01 | 2026-03-31 | 3 | Abgeschlossen | Spieth Tina (LIS) | Mielenz Thomas (LMT) | Kunz Christina (LIS-MHP) | 1 | 1 | 1 | 22
23 | Perform software selection | Build IT Service › Design IT service › Perform software selection | CP | Architecture management | Build IT Service | L3 | Verzögert | 100% | 2025-10-01 | 2026-04-30 | 152 | Abgeschlossen | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 1 | 1 | 1 | 23
24 | Plan IT service | Plan IT service | CP | Corporate IT body | Plan IT service | L1 | Verzögert | 100% | 2025-08-01 | 2026-04-30 | 195 | Abgeschlossen | Spieth Tina (LIS) | Mielenz Thomas (LMT) | Kunz Christina (LIS-MHP) | 1 | 1 | 1 | 24
25 | Plan IT workforce | Provide and develop IT workforce › Manage HR4IT strategy, governane and framework › Plan IT workforce | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 0% | 2025-10-16 | 2026-12-31 | 316 | Verzögert | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 25
26 | Provide IT service support | Run IT service › Provide IT service support | CP | ITSM | Run IT service | L2 | Verzögert | 57% | 2025-10-16 | 2026-06-15 | 173 | Verzögert | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 1 | 0 | 1 | 26
27 | Recruit employees and managers | Provide and develop IT workforce › Attract and hire employees › Recruit employees and managers | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Verzögert | 25% | 2025-10-01 | 2026-12-31 | 327 | In Arbeit | Kiesewetter Ivana (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 27
28 | Run IT service | Run IT service | CP | ITSM | Run IT service | L1 | Verzögert | 17% | 2025-10-15 | 2026-09-25 | 248 | Verzögert | Oey Kai (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS), Boehme Matthias (LIS-BPMO) | 0 | 0 | 1 | 28
29 | Strategic architecture process | Manage enterprise architecture › Strategic architecture process | MP | Corporate IT body | Manage enterprise architecture | L2 | Verzögert | 0% | 2025-10-16 | 2026-04-30 |  | Verzögert | – | – | – | 1 | 0 | 1 | 29
30 | Apply cost model to calculate service cost per unit | Manage and control IT financials › Model and allocate IT costs › Apply cost model to calculate service cost per unit | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 30
31 | Approve and communicate budget plan | Manage and control IT financials › Create and maintain IT budgets › Approve and communicate budget plan | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 31
32 | Build IT Service | Build IT Service | CP | ITSM | Build IT Service | L1 | In Arbeit | 41% |  |  |  | Ohne Angabe | Dalek Martin (LIS) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP) | 0 | 0 | 1 | 32
33 | Collect and consolidate budget from stakeholders | Manage and control IT financials › Create and maintain IT budgets › Collect and consolidate budget from stakeholders | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 33
34 | Compare actual cost to budget forecast | Manage and control IT financials › Manage IT costs › Compare actual cost to budget forecast | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 34
35 | Create and maintain IT budgets | Manage and control IT financials › Create and maintain IT budgets | MP | IT planning and steering | Manage and control IT financials | L2 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 35
36 | Create, approve and publish trainings for IT workforce within IT Training Catalogue | Provide and develop IT workforce › Perform, learn and grow › Create, approve and publish trainings for IT workforce within IT Training Catalogue | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | In Arbeit | 50% | 2025-10-01 | 2026-04-30 | 152 | In Arbeit | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 36
37 | DC/DCC/MSC IT-compliance | Manage IT risks and compliance › Manage IT compliance › DC/DCC/MSC IT-compliance | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L3 | In Arbeit | 25% | 2025-10-01 | 2026-09-30 | 261 | In Arbeit | Mueskens Jan (LHO) | Monnier Murielle (LEC) | Kreis Andreas (LLI) | 0 | 0 | 1 | 37
38 | Define cost allocation principles | Manage and control IT financials › Model and allocate IT costs › Define cost allocation principles | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 38
39 | Define financial management framework | Manage and control IT financials › Manage finance and accounting › Define financial management framework | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 39
40 | Deploy IT service | Build IT Service › Deploy IT service | CP | ITSM | Build IT Service | L2 | In Arbeit | 0% | 2026-05-04 | 2026-07-31 |  | In Arbeit | Dalek Martin (LIS) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP) | 1 | 0 | 1 | 40
41 | Design IT service | Build IT Service › Design IT service | CP | ITSM | Build IT Service | L2 | In Arbeit | 50% | 2026-05-04 | 2026-07-31 |  | In Arbeit | Dalek Martin (LIS) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP) | 1 | 0 | 1 | 41
42 | Develop and customise IT service | Build IT Service › Develop and customise IT service | CP | ITSM | Build IT Service | L2 | In Arbeit | 0% | 2026-05-04 | 2026-07-31 |  | In Arbeit | Dalek Martin (LIS) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP) | 1 | 0 | 1 | 42
43 | Develop preliminary budget plan | Manage and control IT financials › Create and maintain IT budgets › Develop preliminary budget plan | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 43
44 | Elaborate to-be process | Manage IT processes and continuous improvement › Perform operational process management › Elaborate to-be process | MP | ITSM | Manage IT processes and continuous improvement | L3 | In Arbeit | 25% | 2026-01-12 | 2026-05-31 | 100 | In Arbeit | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Rollinger Alexander (LIS) | 1 | 0 | 1 | 44
45 | Ensure Information security | Ensure Information security | SP | Information security | Ensure Information security | L1 | In Arbeit | 50% | 2025-10-16 | 2025-10-16 | 1 | Ohne Angabe | Da Silva Alessandro (LIN) | Monnier Murielle (LEC) | Rollinger Alexander (LIS) | 1 | 0 | 1 | 45
46 | Establish cost allocation model | Manage and control IT financials › Model and allocate IT costs › Establish cost allocation model | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 46
47 | Establish financial accounting structure | Manage and control IT financials › Manage finance and accounting › Establish financial accounting structure | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 47
48 | Evaluate success of IT service rollout | Build IT Service › Evaluate success of IT service rollout | CP | ITSM | Build IT Service | L2 | In Arbeit | 0% | 2026-05-04 | 2026-07-31 |  | In Arbeit | Dalek Martin (LIS) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP) | 1 | 0 | 1 | 48
49 | Gather relevant cost and consumption data | Manage and control IT financials › Model and allocate IT costs › Gather relevant cost and consumption data | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 49
50 | Handle IT Incident | Run IT service › Provide IT service support › Handle IT Incident | CP | ITSM | Run IT service | L3 | In Arbeit | 75% | 2026-01-13 | 2026-03-19 | 48 | In Arbeit | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 1 | 0 | 1 | 50
51 | Handle IT problem | Run IT service › Provide IT service support › Handle IT problem | CP | ITSM | Run IT service | L3 | In Arbeit | 75% | 2026-01-13 | 2026-03-19 | 48 | In Arbeit | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 1 | 0 | 1 | 51
52 | Identify process and determine goals | Manage IT processes and continuous improvement › Perform operational process management › Identify process and determine goals | MP | ITSM | Manage IT processes and continuous improvement | L3 | In Arbeit | 25% | 2026-01-12 | 2026-05-31 | 100 | In Arbeit | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Rollinger Alexander (LIS) | 1 | 0 | 1 | 52
53 | Implement cost allocation to stakeholders or companies | Manage and control IT financials › Model and allocate IT costs › Implement cost allocation to stakeholders or companies | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 53
54 | Implement process | Manage IT processes and continuous improvement › Perform operational process management › Implement process | MP | ITSM | Manage IT processes and continuous improvement | L3 | In Arbeit | 25% | 2026-01-12 | 2026-05-31 | 100 | In Arbeit | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Rollinger Alexander (LIS) | 1 | 0 | 1 | 54
55 | Implement to improve | Manage IT risks and compliance › Manage IT compliance › Implement to improve | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L3 | In Arbeit | 25% | 2025-10-01 | 2026-09-30 | 261 | In Arbeit | Mueskens Jan (LHO) | Monnier Murielle (LEC) | – | 0 | 0 | 1 | 55
56 | Initiate corrective or preventive actions | Manage and control IT financials › Manage IT costs › Initiate corrective or preventive actions | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 56
57 | Leverage IT innovation | Leverage IT innovation | SP | ITSM | Leverage IT innovation | L1 | In Arbeit | 25% | 2026-05-01 | 2026-10-31 | 55 | Ohne Angabe | Abbondio Viviana (LIS) | Sint Rachel (LBH) | Chen Leilei (LIS-BPMO) | 0 | 0 | 1 | 57
58 | Maintain CMDB | Run IT service › Operate and maintain IT service › Maintain CMDB | CP | ITSM | Run IT service | L3 | In Arbeit | 50% | 2026-01-14 | 2026-06-16 | 91 | In Arbeit | Kretz Lucas (COC-COT-IT) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 1 | 0 | 1 | 58
59 | Maintan and adjust budget | Manage and control IT financials › Create and maintain IT budgets › Maintan and adjust budget | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 59
60 | Manage IT compliance | Manage IT risks and compliance › Manage IT compliance | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L2 | In Arbeit | 25% | 2025-10-01 | 2026-09-30 | 261 | In Arbeit | Mueskens Jan (LHO) | Monnier Murielle (LEC) | Kreis Andreas (LLI) | 0 | 0 | 1 | 60
61 | Manage IT costs | Manage and control IT financials › Manage IT costs | MP | IT planning and steering | Manage and control IT financials | L2 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 61
62 | Manage IT governance framework | Manage IT governance framework | MP | Corporate IT body | Manage IT governance framework | L1 | In Arbeit | 50% | 2026-01-07 | 2026-08-31 | 169 | In Arbeit | Felder Max (LLI) | Mielenz Thomas (LMT) | Kunz Christina (LIS-MHP), Kreis Andreas (LLI) | 1 | 0 | 1 | 62
63 | Manage IT portfolio | Manage IT portfolio | MP | ITSM | Manage IT portfolio | L1 | In Arbeit | 78% | 2025-11-10 | 2026-05-15 | 135 | Abgeschlossen | – | – | Frank Maren (LIS), Kunz Christina (LIS-MHP) | 1 | 0 | 1 | 63
64 | Manage IT processes and continuous improvement | Manage IT processes and continuous improvement | MP | ITSM | Manage IT processes and continuous improvement | L1 | In Arbeit | 21% | 2025-10-01 | 2026-05-31 | 173 | Abgeschlossen | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 1 | 0 | 1 | 64
65 | Manage IT risks and compliance | Manage IT risks and compliance | MP | n/a | Manage IT risks and compliance | L1 | In Arbeit | 22% | 2025-10-01 | 2026-09-30 |  | Abgeschlossen | Mueskens Jan (LHO) | Monnier Murielle (LEC) | Hoermann Patrick (LLI) | 0 | 0 | 1 | 65
66 | Manage IT service portfolio | Manage IT portfolio › Manage IT service portfolio | MP | ITSM | Manage IT portfolio | L2 | In Arbeit | 50% | 2026-04-01 | 2026-09-08 | 115 | In Arbeit | Birgit Gerathewohl (LIS) | Reiner Heiko (HAU-ITSA) | Frank Maren (LIS), Kunz Christina (LIS-MHP) | 0 | 0 | 1 | 66
67 | Manage IT service release | Build IT Service › Manage IT service release | CP | ITSM | Build IT Service | L2 | In Arbeit | 50% | 2026-02-20 | 2026-06-30 | 93 | In Arbeit | Hoeller Martin (LBH) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP), Frank Maren (LIS) | 1 | 0 | 1 | 67
68 | Manage IT sourcing and procurement | Manage IT sourcing and procurement | SP | ITSM | Manage IT sourcing and procurement | L1 | In Arbeit | 25% | 2026-04-20 | 2026-07-08 | 118 | In Arbeit | Dolderer Wolfgang (LIS) | Monnier Murielle (LEC) | Schoeberl Lorena (LBH) | 1 | 1 | 1 | 68
69 | Manage IT strategy | Manage IT strategy | MP | Corporate IT body | Manage IT strategy | L1 | In Arbeit | 50% | 2026-02-02 | 2026-07-29 | 128 | In Arbeit | Felder Max (LLI) | Mielenz Thomas (LMT) | Kreis Andreas (LLI) | 1 | 0 | 1 | 69
70 | Manage IT-C framework | Manage IT risks and compliance › Manage IT compliance › Manage IT-C framework | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L3 | In Arbeit | 25% | 2025-10-01 | 2026-09-30 | 261 | In Arbeit | Mueskens Jan (LHO) | Monnier Murielle (LEC) | Kreis Andreas (LLI) | 0 | 0 | 1 | 70
71 | Manage IT-C strategy | Manage IT risks and compliance › Manage IT compliance › Manage IT-C strategy | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L3 | In Arbeit | 25% | 2025-10-01 | 2026-09-30 | 261 | In Arbeit | Mueskens Jan (LHO) | Monnier Murielle (LEC) | Kreis Andreas (LLI) | 0 | 0 | 1 | 71
72 | Manage and control IT financials | Manage and control IT financials | MP | IT planning and steering | Manage and control IT financials | L1 | In Arbeit | 50% | 2025-10-15 | 2026-07-31 | 208 | In Arbeit | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 1 | 0 | 1 | 72
73 | Manage finance and accounting | Manage and control IT financials › Manage finance and accounting | MP | IT planning and steering | Manage and control IT financials | L2 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 73
74 | Model and allocate IT costs | Manage and control IT financials › Model and allocate IT costs | MP | IT planning and steering | Manage and control IT financials | L2 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 74
75 | Monitor to delegate | Manage IT risks and compliance › Manage IT compliance › Monitor to delegate | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L3 | In Arbeit | 25% | 2025-10-01 | 2026-09-30 | 261 | In Arbeit | Mueskens Jan (LHO) | Monnier Murielle (LEC) | – | 0 | 0 | 1 | 75
76 | Onboard new IT employee and manager | Provide and develop IT workforce › Perform onboarding › Onboard new IT employee and manager | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | In Arbeit | 50% | 2025-10-16 | 2026-04-30 | 141 | In Arbeit | – | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 76
77 | Perform SaaS Security Assessment | Ensure Information security › Perform SaaS Security Assessment | SP | Information security | Ensure Information security | L2 | In Arbeit | 50% | 2025-10-19 | 2025-11-30 |  | In Arbeit | Hefele Michael (LIN-LIS) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI), Rollinger Alexander (LIS) | 1 | 0 | 1 | 77
78 | Perform onboarding | Provide and develop IT workforce › Perform onboarding | SP | HR initiatives for IT | Provide and develop IT workforce | L2 | In Arbeit | 33% | 2025-10-16 | 2026-04-30 | 141 | In Arbeit | – | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 78
79 | Perform operational process management | Manage IT processes and continuous improvement › Perform operational process management | MP | ITSM | Manage IT processes and continuous improvement | L2 | In Arbeit | 25% | 2025-10-01 | 2026-05-31 | 173 | In Arbeit | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Rollinger Alexander (LIS) | 1 | 0 | 1 | 79
80 | Perform, learn and grow | Provide and develop IT workforce › Perform, learn and grow | SP | HR initiatives for IT | Provide and develop IT workforce | L2 | In Arbeit | 11% | 2025-10-01 | 2027-06-30 | 456 | Ohne Angabe | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 80
81 | Plan process execution | Manage IT processes and continuous improvement › Perform operational process management › Plan process execution | MP | ITSM | Manage IT processes and continuous improvement | L3 | In Arbeit | 25% | 2026-01-12 | 2026-05-31 | 100 | In Arbeit | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Rollinger Alexander (LIS) | 1 | 0 | 1 | 81
82 | Pre-board new IT employee and manager | Provide and develop IT workforce › Perform onboarding › Pre-board new IT employee and manager | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | In Arbeit | 25% | 2025-10-16 | 2026-04-30 | 141 | In Arbeit | – | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 82
83 | Provide and develop IT workforce | Provide and develop IT workforce | SP | HR initiatives for IT | Provide and develop IT workforce | L1 | In Arbeit | 15% | 2025-10-01 | 2027-06-30 | 456 | Abgeschlossen | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 83
84 | Report actual IT costs | Manage and control IT financials › Manage IT costs › Report actual IT costs | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Moser Mario (LIS-LAH) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 84
85 | Requirements to measures | Manage IT risks and compliance › Manage IT compliance › Requirements to measures | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L3 | In Arbeit | 25% | 2025-10-01 | 2026-09-30 | 261 | In Arbeit | Mueskens Jan (LHO) | Monnier Murielle (LEC) | – | 0 | 0 | 1 | 85
86 | Review budget plan | Manage and control IT financials › Create and maintain IT budgets › Review budget plan | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 86
87 | Revise and optimize budget plan | Manage and control IT financials › Create and maintain IT budgets › Revise and optimize budget plan | MP | IT planning and steering | Manage and control IT financials | L3 | In Arbeit | 50% | 2025-10-15 |  |  | Ohne Angabe | Frank Nicole (LIS) | Mielenz Thomas (LMT) | Hynek Tobias (LIS), Kreis Andreas (LLI) | 0 | 0 | 1 | 87
88 | Test and validate IT service | Build IT Service › Test and validate IT service | CP | ITSM | Build IT Service | L2 | In Arbeit | 0% | 2026-05-04 | 2026-07-31 |  | In Arbeit | Dalek Martin (LIS) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP) | 1 | 0 | 1 | 88
89 | Deliver IT service | Deliver IT service | CP | ITSM | Deliver IT service | L1 | Terminiert | 0% | 2026-04-01 | 2026-06-17 | 56 | Ohne Angabe | – | Schnurrenberger Christoph (LIS-LIN) | – | 1 | 0 | 1 | 89
90 | Manage HR4IT strategy, governane and framework | Provide and develop IT workforce › Manage HR4IT strategy, governane and framework | SP | HR initiatives for IT | Provide and develop IT workforce | L2 | Terminiert | 0% | 2025-10-01 | 2026-12-31 |  | Abgeschlossen | Amelang Nicole (LIS) | Rollinger Alexander (LIS) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 0 | 0 | 1 | 90
91 | Manage IT development programme | Provide and develop IT workforce › Perform, learn and grow › Manage IT development programme | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Terminiert | 0% | 2025-10-16 | 2025-10-16 | 0 | Ohne Angabe | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 91
92 | Manage IT risks | Manage IT risks and compliance › Manage IT risks | MP | Central area (Jan Müskens) | Manage IT risks and compliance | L2 | Terminiert | 0% | 2025-10-01 | 2026-09-30 | 261 | Ohne Angabe | – | Monnier Murielle (LEC) | – | 0 | 0 | 1 | 92
93 | Manage IT talent pool and identify potential | Provide and develop IT workforce › Perform, learn and grow › Manage IT talent pool and identify potential | SP | HR initiatives for IT | Provide and develop IT workforce | L3 | Terminiert | 0% | 2025-10-16 | 2025-10-16 | 0 | Ohne Angabe | Grabmair Melanie (LIS) | Mielenz Thomas (LMT) | Chen Leilei (LIS-BPMO), Hynek Tobias (LIS) | 1 | 0 | 1 | 93
94 | Monitor and report IT service level | Run IT service › Monitor and report IT service performance › Monitor and report IT service level | CP | ITSM | Run IT service | L3 | Terminiert | 0% | 2026-04-15 | 2026-07-31 | 0 | Ohne Angabe | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 1 | 0 | 1 | 94
95 | Monitor and report IT service performance | Run IT service › Monitor and report IT service performance | CP | ITSM | Run IT service | L2 | Terminiert | 0% | 2026-04-15 |  |  | Ohne Angabe | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 95
96 | Ensure IT service continuity | Run IT service › Ensure IT service continuity | CP | ITSM | Run IT service | L2 | Nicht geplant | 0% |  |  |  | Ohne Angabe | – | Sint Rachel (LBH) | Schroeder Michael (LIS), Boehme Matthias (LIS-BPMO) | 0 | 0 | 1 | 96
97 | Maintain IT asset database | Run IT service › Operate and maintain IT service › Maintain IT asset database | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | – | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 97
98 | Maintain standard change catalogue for IT service | Run IT service › Operate and maintain IT service › Maintain standard change catalogue for IT service | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | – | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 98
99 | Manage IT service capacity | Run IT service › Ensure IT service continuity › Manage IT service capacity | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | – | Sint Rachel (LBH) | Schroeder Michael (LIS), Boehme Matthias (LIS-BPMO) | 0 | 0 | 1 | 99
100 | Manage IT service desk | Run IT service › Provide IT service support › Manage IT service desk | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | – | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 100
101 | Manage a common approach to contiual improvement | Manage IT processes and continuous improvement › Manage continuous improvement › Manage a common approach to contiual improvement | MP | ITSM | Manage IT processes and continuous improvement | L3 | Nicht geplant | 0% |  | 2025-10-16 |  | Ohne Angabe | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | Boehme Matthias (LIS-BPMO), Rollinger Alexander (LIS) | 1 | 0 | 1 | 101
102 | Manage continual improvement initiative | Manage IT processes and continuous improvement › Manage continuous improvement › Manage continual improvement initiative | MP | ITSM | Manage IT processes and continuous improvement | L3 | Nicht geplant | 0% |  | 2025-10-16 |  | Ohne Angabe | Kuerschner Philipp (LIS) | Reiner Heiko (HAU-ITSA) | Boehme Matthias (LIS-BPMO), Rollinger Alexander (LIS) | 1 | 0 | 1 | 102
103 | Monitor IT service risk and compliance | Run IT service › Monitor and report IT service performance › Monitor IT service risk and compliance | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 103
104 | Monitor and analyse events | Run IT service › Monitor and report IT service performance › Monitor and analyse events | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 104
105 | Monitor and report IT service financials | Run IT service › Monitor and report IT service performance › Monitor and report IT service financials | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 105
106 | Monitor user experience | Run IT service › Monitor and report IT service performance › Monitor user experience | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Schroeder Michael (LIS) | 0 | 0 | 1 | 106
107 | Review and maintain IT service continuity plan | Run IT service › Ensure IT service continuity › Review and maintain IT service continuity plan | CP | ITSM | Run IT service | L3 | Nicht geplant | 0% |  |  |  | Ohne Angabe | – | Sint Rachel (LBH) | Schroeder Michael (LIS), Boehme Matthias (LIS-BPMO) | 0 | 0 | 1 | 107
108 | Analyse process | Manage IT processes and continuous improvement › Perform operational process management › Analyse process | MP | ITSM | Manage IT processes and continuous improvement | L3 | Abgeschlossen | 100% | 2025-10-01 | 2025-10-01 | 1 | Abgeschlossen | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 0 | 1 | 108
109 | Assign personnel resources to IT project | Manage IT project › Assign personnel resources to IT project | SP | IT project management | Manage IT project | L2 | Abgeschlossen | 100% | 2025-07-14 | 2025-12-10 | 1 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 0 | 1 | 1 | 109
110 | Close IT project | Manage IT project › Close IT project | SP | IT project management | Manage IT project | L2 | Abgeschlossen | 100% | 2025-07-14 | 2025-12-10 | 1 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 0 | 1 | 1 | 110
111 | Conduct market analysis and compile long or short list | Build IT Service › Design IT service › Perform software selection › Conduct market analysis and compile long or short list | CP | Architecture management | Build IT Service | L4 | Abgeschlossen | 100% | 2025-10-01 | 2026-04-30 | 1 | Abgeschlossen | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 1 | 1 | 111
112 | Develop and maintain IT BPM framework | Manage IT processes and continuous improvement › Develop and maintain IT BPM framework | MP | ITSM | Manage IT processes and continuous improvement | L2 | Abgeschlossen | 100% | 2025-08-04 | 2025-10-16 | 1 | Abgeschlossen | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 0 | 1 | 112
113 | Handle IT service request | Run IT service › Provide IT service support › Handle IT service request | CP | ITSM | Run IT service | L3 | Abgeschlossen | 100% | 2026-02-02 | 2026-03-19 |  | Abgeschlossen | Kuerschner Philipp (LIS) | Sint Rachel (LBH) | Frank Maren (LIS) | 0 | 0 | 1 | 113
114 | Initiate IT project | Manage IT project › Initiate IT project | SP | IT project management | Manage IT project | L2 | Abgeschlossen | 100% | 2025-07-14 | 2025-12-10 | 1 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 0 | 1 | 1 | 114
115 | Manage IT project | Manage IT project | SP | IT project management | Manage IT project | L1 | Abgeschlossen | 100% | 2025-07-14 | 2025-12-10 | 108 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 0 | 1 | 1 | 115
116 | Manage IT project change request | Manage IT project › Manage IT project change request | SP | IT project management | Manage IT project | L2 | Abgeschlossen | 100% | 2025-07-14 | 2025-12-10 | 1 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 0 | 1 | 1 | 116
117 | Manage IT service change | Build IT Service › Manage IT service change | CP | ITSM | Build IT Service | L2 | Abgeschlossen | 100% | 2026-01-12 | 2026-06-30 | 122 | Abgeschlossen | Sint Rachel (LBH) | Wiehe Alexander (COB) | Kunz Christina (LIS-MHP), Frank Maren (LIS) | 0 | 0 | 1 | 117
118 | Perform and measure process | Manage IT processes and continuous improvement › Perform operational process management › Perform and measure process | MP | ITSM | Manage IT processes and continuous improvement | L3 | Abgeschlossen | 100% | 2025-10-01 | 2025-10-01 | 1 | Abgeschlossen | Rollinger Alexander (LIS) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 0 | 1 | 118
119 | Perform vendor use case pitch and usability test | Build IT Service › Design IT service › Perform software selection › Perform vendor use case pitch and usability test | CP | Architecture management | Build IT Service | L4 | Abgeschlossen | 100% | 2025-10-01 | 2026-04-30 | 1 | Abgeschlossen | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 1 | 1 | 119
120 | Plan IT project | Manage IT project › Plan IT project | SP | IT project management | Manage IT project | L2 | Abgeschlossen | 100% | 2025-07-14 | 2025-12-10 | 1 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 0 | 1 | 1 | 120
121 | Recommendation and EA approval | Build IT Service › Design IT service › Perform software selection › Recommendation and EA approval | CP | Architecture management | Build IT Service | L4 | Abgeschlossen | 100% | 2025-10-01 | 2026-04-30 | 1 | Abgeschlossen | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 1 | 1 | 121
122 | Record and plan functional requirements | Build IT Service › Design IT service › Perform software selection › Record and plan functional requirements | CP | Architecture management | Build IT Service | L4 | Abgeschlossen | 100% | 2025-10-01 | 2026-04-30 | 1 | Abgeschlossen | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 1 | 1 | 122
123 | Steer and execute IT project | Manage IT project › Steer and execute IT project | SP | IT project management | Manage IT project | L2 | Abgeschlossen | 100% | 2025-07-14 | 2025-12-10 | 1 | Abgeschlossen | Mühlbacher Christian (LIS) | Rollinger Alexander (LIS) | Frank Maren (LIS) | 0 | 1 | 1 | 123
124 | Validate strategic fit | Build IT Service › Design IT service › Perform software selection › Validate strategic fit | CP | Architecture management | Build IT Service | L4 | Abgeschlossen | 100% | 2025-10-01 | 2026-04-30 | 2 | Abgeschlossen | Preiss Matthias (LBC) | Reiner Heiko (HAU-ITSA) | Hoermann Patrick (LLI) | 0 | 1 | 1 | 124

## Phasen
Nr | Prozess | Gruppe | Phase | Status | Start | Ende | Dauer (T) | Treffer
1 | Analyse architecture impact | CP | Elaboration | Abgeschlossen | 2025-08-01 | 2025-10-15 | 54 | 1
1 | Analyse architecture impact | CP | Implementation LIS | Ohne Angabe | 2026-11-01 | 2026-02-28 | 0 | 1
1 | Analyse architecture impact | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
1 | Analyse architecture impact | CP | Implementation COT | Verzögert | 2025-10-16 | 2026-04-30 | 141 | 1
2 | Approve IT demand | CP | Elaboration | Abgeschlossen | 2025-08-01 | 2025-08-01 | 1 | 1
2 | Approve IT demand | CP | Implementation LIS | Verzögert | 2025-11-01 | 2026-02-28 | 85 | 1
2 | Approve IT demand | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
2 | Approve IT demand | CP | Implementation COT | Verzögert | 2025-11-03 | 2026-03-31 | 107 | 1
3 | Attract and hire employees | SP | Elaboration | In Arbeit | 2026-01-07 | 2026-03-16 | 49 | 1
3 | Attract and hire employees | SP | Implementation LIS | Verzögert | 2026-04-01 | 2026-06-15 | 54 | 1
3 | Attract and hire employees | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
3 | Attract and hire employees | SP | Implementation COT | Verzögert | 2026-04-01 | 2026-06-15 | 54 | 1
4 | Define solution target architecture | CP | Elaboration | In Arbeit | 2026-02-05 | 2026-06-15 | 54 | 1
4 | Define solution target architecture | CP | Implementation LIS | Verzögert |  |  |  | 1
4 | Define solution target architecture | CP | Implementation LUS | Verzögert |  |  |  | 1
4 | Define solution target architecture | CP | Implementation COT | Verzögert |  |  |  | 1
5 | Ensure performance and conformance of IT services | SP | Elaboration | Verzögert |  |  |  | 1
5 | Ensure performance and conformance of IT services | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
5 | Ensure performance and conformance of IT services | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
5 | Ensure performance and conformance of IT services | SP | Implementation COT | Ohne Angabe |  |  |  | 1
6 | Evaluate and qualify IT demand | CP | Elaboration | Abgeschlossen | 2025-08-01 | 2025-08-01 | 1 | 1
6 | Evaluate and qualify IT demand | CP | Implementation LIS | Verzögert | 2025-11-01 | 2026-02-28 | 85 | 1
6 | Evaluate and qualify IT demand | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
6 | Evaluate and qualify IT demand | CP | Implementation COT | Verzögert | 2025-11-03 | 2026-03-31 | 107 | 1
7 | Handle IT service order | CP | Elaboration | Verzögert | 2026-04-01 | 2026-06-17 | 56 | 1
7 | Handle IT service order | CP | Implementation LIS | Verzögert | 2026-04-01 | 2026-06-15 | 54 | 1
7 | Handle IT service order | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
7 | Handle IT service order | CP | Implementation COT | Ohne Angabe |  |  |  | 1
8 | Implement and maintain IT job architecture | SP | Elaboration | Verzögert | 2025-10-16 | 2026-05-31 | 162 | 1
8 | Implement and maintain IT job architecture | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
8 | Implement and maintain IT job architecture | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
8 | Implement and maintain IT job architecture | SP | Implementation COT | Ohne Angabe |  |  |  | 1
9 | Maintain IT glossary | MP | Elaboration | Ohne Angabe | 2026-01-07 |  |  | 1
9 | Maintain IT glossary | MP | Implementation LIS | Verzögert | 2026-01-07 | 2026-01-17 | 7 | 1
9 | Maintain IT glossary | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
9 | Maintain IT glossary | MP | Implementation COT | Ohne Angabe | 2026-01-07 |  |  | 1
10 | Manage HR4IT service demand | SP | Elaboration | Verzögert | 2025-10-01 | 2026-05-31 | 173 | 1
10 | Manage HR4IT service demand | SP | Implementation LIS | Terminiert | 2026-06-01 | 2026-06-30 | 22 | 1
10 | Manage HR4IT service demand | SP | Implementation LUS | Terminiert | 2026-06-01 | 2026-06-30 | 22 | 1
10 | Manage HR4IT service demand | SP | Implementation COT | Terminiert | 2026-06-01 | 2026-06-30 | 22 | 1
11 | Manage IT global orientation programme incl. job shadowing | SP | Elaboration | Verzögert | 2026-01-15 | 2026-03-31 | 54 | 1
11 | Manage IT global orientation programme incl. job shadowing | SP | Implementation LIS | Verzögert | 2026-04-01 | 2026-07-01 | 66 | 1
11 | Manage IT global orientation programme incl. job shadowing | SP | Implementation LUS | Verzögert | 2026-04-01 | 2026-07-01 | 66 | 1
11 | Manage IT global orientation programme incl. job shadowing | SP | Implementation COT | Verzögert | 2026-04-01 | 2026-07-01 | 66 | 1
12 | Manage IT knowledge | SP | Elaboration | Abgeschlossen | 2026-01-20 | 2026-02-25 | 27 | 1
12 | Manage IT knowledge | SP | Implementation LIS | Verzögert | 2026-04-15 | 2026-06-30 | 55 | 1
12 | Manage IT knowledge | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
12 | Manage IT knowledge | SP | Implementation COT | Ohne Angabe |  |  |  | 1
13 | Manage IT project portfolio | MP | Elaboration | Abgeschlossen | 2025-11-10 | 2025-12-10 | 23 | 1
13 | Manage IT project portfolio | MP | Implementation LIS | Verzögert | 2026-02-01 | 2026-05-31 | 85 | 1
13 | Manage IT project portfolio | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
13 | Manage IT project portfolio | MP | Implementation COT | Ohne Angabe |  |  |  | 1
14 | Manage IT service provision request | CP | Elaboration | Verzögert | 2026-04-01 | 2026-06-17 | 56 | 1
14 | Manage IT service provision request | CP | Implementation LIS | Verzögert | 2026-04-01 | 2026-06-15 | 54 | 1
14 | Manage IT service provision request | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
14 | Manage IT service provision request | CP | Implementation COT | Ohne Angabe |  |  |  | 1
15 | Manage IT skills | SP | Elaboration | Verzögert | 2026-01-01 | 2026-12-31 | 261 | 1
15 | Manage IT skills | SP | Implementation LIS | Terminiert | 2027-01-01 | 2027-06-30 | 129 | 1
15 | Manage IT skills | SP | Implementation LUS | Terminiert | 2027-01-01 | 2027-06-30 | 129 | 1
15 | Manage IT skills | SP | Implementation COT | Terminiert | 2027-01-01 | 2027-06-30 | 129 | 1
16 | Manage IT stakeholder relationships | MP | Elaboration | Verzögert | 2026-04-01 | 2026-06-15 | 54 | 1
16 | Manage IT stakeholder relationships | MP | Implementation LIS | Terminiert | 2026-10-15 | 2026-12-23 | 50 | 1
16 | Manage IT stakeholder relationships | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
16 | Manage IT stakeholder relationships | MP | Implementation COT | Ohne Angabe |  |  |  | 1
17 | Manage continuous improvement | MP | Elaboration | Verzögert | 2025-10-01 | 2026-01-30 | 88 | 1
17 | Manage continuous improvement | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
17 | Manage continuous improvement | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
17 | Manage continuous improvement | MP | Implementation COT | Ohne Angabe |  |  |  | 1
18 | Manage enterprise architecture | MP | Elaboration | Verzögert | 2026-02-23 | 2026-05-08 |  | 1
18 | Manage enterprise architecture | MP | Implementation LIS | Terminiert | 2026-05-08 | 2026-07-16 |  | 1
18 | Manage enterprise architecture | MP | Implementation LUS | Terminiert | 2026-05-08 | 2026-05-11 |  | 1
18 | Manage enterprise architecture | MP | Implementation COT | Terminiert | 2026-05-08 | 2026-05-11 |  | 1
19 | Mapping and evaluate IT career level | SP | Elaboration | Verzögert | 2026-04-01 | 2027-01-01 | 198 | 1
19 | Mapping and evaluate IT career level | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
19 | Mapping and evaluate IT career level | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
19 | Mapping and evaluate IT career level | SP | Implementation COT | Ohne Angabe |  |  |  | 1
20 | Operate and maintain IT service | CP | Elaboration | Verzögert | 2026-01-12 | 2026-06-30 | 122 | 1
20 | Operate and maintain IT service | CP | Implementation LIS | Verzögert | 2026-04-15 | 2026-06-30 | 55 | 1
20 | Operate and maintain IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
20 | Operate and maintain IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
21 | Perform active sourcing | SP | Elaboration | Verzögert | 2025-10-01 | 2026-04-30 | 152 | 1
21 | Perform active sourcing | SP | Implementation LIS | Verzögert | 2026-03-01 | 2026-12-31 | 219 | 1
21 | Perform active sourcing | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
21 | Perform active sourcing | SP | Implementation COT | Ohne Angabe |  |  |  | 1
22 | Perform initial assessment of customer need | CP | Elaboration | Abgeschlossen | 2025-08-01 | 2025-08-01 | 1 | 1
22 | Perform initial assessment of customer need | CP | Implementation LIS | Verzögert | 2025-11-01 | 2026-02-28 | 85 | 1
22 | Perform initial assessment of customer need | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
22 | Perform initial assessment of customer need | CP | Implementation COT | Verzögert | 2025-11-03 | 2026-03-31 | 107 | 1
23 | Perform software selection | CP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-12-23 | 60 | 1
23 | Perform software selection | CP | Implementation LIS | Verzögert | 2026-02-16 | 2026-04-30 | 54 | 1
23 | Perform software selection | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
23 | Perform software selection | CP | Implementation COT | Verzögert | 2025-10-16 | 2025-12-31 | 55 | 1
24 | Plan IT service | CP | Elaboration | Abgeschlossen | 2025-10-16 | 2025-10-31 | 12 | 1
24 | Plan IT service | CP | Implementation LIS | Verzögert | 2025-11-01 | 2026-02-28 | 85 | 1
24 | Plan IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
24 | Plan IT service | CP | Implementation COT | Verzögert | 2025-11-03 | 2026-03-31 | 107 | 1
25 | Plan IT workforce | SP | Elaboration | Verzögert | 2025-10-16 | 2025-12-31 | 55 | 1
25 | Plan IT workforce | SP | Implementation LIS | Verzögert | 2026-01-01 | 2026-12-31 | 261 | 1
25 | Plan IT workforce | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
25 | Plan IT workforce | SP | Implementation COT | Ohne Angabe |  |  |  | 1
26 | Provide IT service support | CP | Elaboration | Verzögert | 2026-01-12 | 2026-03-30 | 56 | 1
26 | Provide IT service support | CP | Implementation LIS | Verzögert | 2026-04-01 | 2026-06-15 | 54 | 1
26 | Provide IT service support | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
26 | Provide IT service support | CP | Implementation COT | Ohne Angabe |  |  |  | 1
27 | Recruit employees and managers | SP | Elaboration | In Arbeit | 2025-10-01 | 2026-04-30 | 152 | 1
27 | Recruit employees and managers | SP | Implementation LIS | Verzögert | 2026-03-01 | 2026-12-31 | 219 | 1
27 | Recruit employees and managers | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
27 | Recruit employees and managers | SP | Implementation COT | Ohne Angabe |  |  |  | 1
28 | Run IT service | CP | Elaboration | Verzögert | 2025-10-16 | 2026-06-30 | 184 | 1
28 | Run IT service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
28 | Run IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
28 | Run IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
29 | Strategic architecture process | MP | Elaboration | Verzögert | 2026-02-23 | 2026-04-30 |  | 1
29 | Strategic architecture process | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
29 | Strategic architecture process | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
29 | Strategic architecture process | MP | Implementation COT | Ohne Angabe |  |  |  | 1
30 | Apply cost model to calculate service cost per unit | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
30 | Apply cost model to calculate service cost per unit | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
30 | Apply cost model to calculate service cost per unit | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
30 | Apply cost model to calculate service cost per unit | MP | Implementation COT | Ohne Angabe |  |  |  | 1
31 | Approve and communicate budget plan | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
31 | Approve and communicate budget plan | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
31 | Approve and communicate budget plan | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
31 | Approve and communicate budget plan | MP | Implementation COT | Ohne Angabe |  |  |  | 1
32 | Build IT Service | CP | Elaboration | Ohne Angabe |  |  |  | 1
32 | Build IT Service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
32 | Build IT Service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
32 | Build IT Service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
33 | Collect and consolidate budget from stakeholders | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
33 | Collect and consolidate budget from stakeholders | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
33 | Collect and consolidate budget from stakeholders | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
33 | Collect and consolidate budget from stakeholders | MP | Implementation COT | Ohne Angabe |  |  |  | 1
34 | Compare actual cost to budget forecast | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
34 | Compare actual cost to budget forecast | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
34 | Compare actual cost to budget forecast | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
34 | Compare actual cost to budget forecast | MP | Implementation COT | Ohne Angabe |  |  |  | 1
35 | Create and maintain IT budgets | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
35 | Create and maintain IT budgets | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
35 | Create and maintain IT budgets | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
35 | Create and maintain IT budgets | MP | Implementation COT | Ohne Angabe |  |  |  | 1
36 | Create, approve and publish trainings for IT workforce within IT Training Catalogue | SP | Elaboration | In Arbeit | 2025-10-01 | 2026-04-30 | 152 | 1
36 | Create, approve and publish trainings for IT workforce within IT Training Catalogue | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
36 | Create, approve and publish trainings for IT workforce within IT Training Catalogue | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
36 | Create, approve and publish trainings for IT workforce within IT Training Catalogue | SP | Implementation COT | Ohne Angabe |  |  |  | 1
37 | DC/DCC/MSC IT-compliance | MP | Elaboration | In Arbeit | 2025-10-01 | 2026-09-30 | 261 | 1
37 | DC/DCC/MSC IT-compliance | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
37 | DC/DCC/MSC IT-compliance | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
37 | DC/DCC/MSC IT-compliance | MP | Implementation COT | Ohne Angabe |  |  |  | 1
38 | Define cost allocation principles | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
38 | Define cost allocation principles | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
38 | Define cost allocation principles | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
38 | Define cost allocation principles | MP | Implementation COT | Ohne Angabe |  |  |  | 1
39 | Define financial management framework | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
39 | Define financial management framework | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
39 | Define financial management framework | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
39 | Define financial management framework | MP | Implementation COT | Ohne Angabe |  |  |  | 1
40 | Deploy IT service | CP | Elaboration | In Arbeit | 2026-05-04 | 2026-07-31 | 44 | 1
40 | Deploy IT service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
40 | Deploy IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
40 | Deploy IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
41 | Design IT service | CP | Elaboration | In Arbeit | 2026-05-04 | 2026-07-31 | 65 | 1
41 | Design IT service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
41 | Design IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
41 | Design IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
42 | Develop and customise IT service | CP | Elaboration | In Arbeit | 2026-05-04 | 2026-07-31 | 65 | 1
42 | Develop and customise IT service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
42 | Develop and customise IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
42 | Develop and customise IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
43 | Develop preliminary budget plan | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
43 | Develop preliminary budget plan | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
43 | Develop preliminary budget plan | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
43 | Develop preliminary budget plan | MP | Implementation COT | Ohne Angabe |  |  |  | 1
44 | Elaborate to-be process | MP | Elaboration | In Arbeit | 2026-01-12 | 2026-05-31 | 100 | 1
44 | Elaborate to-be process | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
44 | Elaborate to-be process | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
44 | Elaborate to-be process | MP | Implementation COT | Ohne Angabe |  |  |  | 1
45 | Ensure Information security | SP | Elaboration | Ohne Angabe | 2025-10-16 |  |  | 1
45 | Ensure Information security | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
45 | Ensure Information security | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
45 | Ensure Information security | SP | Implementation COT | Ohne Angabe |  |  |  | 1
46 | Establish cost allocation model | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
46 | Establish cost allocation model | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
46 | Establish cost allocation model | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
46 | Establish cost allocation model | MP | Implementation COT | Ohne Angabe |  |  |  | 1
47 | Establish financial accounting structure | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
47 | Establish financial accounting structure | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
47 | Establish financial accounting structure | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
47 | Establish financial accounting structure | MP | Implementation COT | Ohne Angabe |  |  |  | 1
48 | Evaluate success of IT service rollout | CP | Elaboration | In Arbeit | 2026-05-04 | 2026-07-31 | 0 | 1
48 | Evaluate success of IT service rollout | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
48 | Evaluate success of IT service rollout | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
48 | Evaluate success of IT service rollout | CP | Implementation COT | Ohne Angabe |  |  |  | 1
49 | Gather relevant cost and consumption data | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
49 | Gather relevant cost and consumption data | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
49 | Gather relevant cost and consumption data | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
49 | Gather relevant cost and consumption data | MP | Implementation COT | Ohne Angabe |  |  |  | 1
50 | Handle IT Incident | CP | Elaboration | In Arbeit | 2026-01-13 | 2026-03-19 | 48 | 1
50 | Handle IT Incident | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
50 | Handle IT Incident | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
50 | Handle IT Incident | CP | Implementation COT | Ohne Angabe |  |  |  | 1
51 | Handle IT problem | CP | Elaboration | In Arbeit | 2026-01-13 | 2026-03-19 | 48 | 1
51 | Handle IT problem | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
51 | Handle IT problem | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
51 | Handle IT problem | CP | Implementation COT | Ohne Angabe |  |  |  | 1
52 | Identify process and determine goals | MP | Elaboration | In Arbeit | 2026-01-12 | 2026-05-31 | 100 | 1
52 | Identify process and determine goals | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
52 | Identify process and determine goals | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
52 | Identify process and determine goals | MP | Implementation COT | Ohne Angabe |  |  |  | 1
53 | Implement cost allocation to stakeholders or companies | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
53 | Implement cost allocation to stakeholders or companies | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
53 | Implement cost allocation to stakeholders or companies | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
53 | Implement cost allocation to stakeholders or companies | MP | Implementation COT | Ohne Angabe |  |  |  | 1
54 | Implement process | MP | Elaboration | In Arbeit | 2026-01-12 | 2026-05-31 | 100 | 1
54 | Implement process | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
54 | Implement process | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
54 | Implement process | MP | Implementation COT | Ohne Angabe |  |  |  | 1
55 | Implement to improve | MP | Elaboration | In Arbeit | 2025-10-01 | 2026-09-30 | 261 | 1
55 | Implement to improve | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
55 | Implement to improve | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
55 | Implement to improve | MP | Implementation COT | Ohne Angabe |  |  |  | 1
56 | Initiate corrective or preventive actions | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
56 | Initiate corrective or preventive actions | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
56 | Initiate corrective or preventive actions | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
56 | Initiate corrective or preventive actions | MP | Implementation COT | Ohne Angabe |  |  |  | 1
57 | Leverage IT innovation | SP | Elaboration | Ohne Angabe | 2026-05-01 | 2026-10-31 | 0 | 1
57 | Leverage IT innovation | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
57 | Leverage IT innovation | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
57 | Leverage IT innovation | SP | Implementation COT | Ohne Angabe |  |  |  | 1
58 | Maintain CMDB | CP | Elaboration | In Arbeit | 2026-01-14 | 2026-06-16 | 91 | 1
58 | Maintain CMDB | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
58 | Maintain CMDB | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
58 | Maintain CMDB | CP | Implementation COT | Ohne Angabe |  |  |  | 1
59 | Maintan and adjust budget | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
59 | Maintan and adjust budget | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
59 | Maintan and adjust budget | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
59 | Maintan and adjust budget | MP | Implementation COT | Ohne Angabe |  |  |  | 1
60 | Manage IT compliance | MP | Elaboration | In Arbeit | 2025-10-01 | 2026-09-30 | 261 | 1
60 | Manage IT compliance | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
60 | Manage IT compliance | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
60 | Manage IT compliance | MP | Implementation COT | Ohne Angabe |  |  |  | 1
61 | Manage IT costs | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
61 | Manage IT costs | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
61 | Manage IT costs | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
61 | Manage IT costs | MP | Implementation COT | Ohne Angabe |  |  |  | 1
62 | Manage IT governance framework | MP | Elaboration | In Arbeit | 2026-03-16 | 2026-05-21 | 49 | 1
62 | Manage IT governance framework | MP | Implementation LIS | Terminiert | 2026-05-25 | 2026-08-31 | 71 | 1
62 | Manage IT governance framework | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
62 | Manage IT governance framework | MP | Implementation COT | Ohne Angabe |  |  |  | 1
63 | Manage IT portfolio | MP | Elaboration | Abgeschlossen | 2025-11-11 | 2026-01-29 | 58 | 1
63 | Manage IT portfolio | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
63 | Manage IT portfolio | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
63 | Manage IT portfolio | MP | Implementation COT | Ohne Angabe |  |  |  | 1
64 | Manage IT processes and continuous improvement | MP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-10-01 | 1 | 1
64 | Manage IT processes and continuous improvement | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
64 | Manage IT processes and continuous improvement | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
64 | Manage IT processes and continuous improvement | MP | Implementation COT | Ohne Angabe |  |  |  | 1
65 | Manage IT risks and compliance | MP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-10-01 | 1 | 1
65 | Manage IT risks and compliance | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
65 | Manage IT risks and compliance | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
65 | Manage IT risks and compliance | MP | Implementation COT | Ohne Angabe |  |  |  | 1
66 | Manage IT service portfolio | MP | Elaboration | In Arbeit | 2026-04-01 | 2026-07-15 | 54 | 1
66 | Manage IT service portfolio | MP | Implementation LIS | Nicht geplant |  |  |  | 1
66 | Manage IT service portfolio | MP | Implementation LUS | Nicht geplant |  |  |  | 1
66 | Manage IT service portfolio | MP | Implementation COT | Nicht geplant |  |  |  | 1
67 | Manage IT service release | CP | Elaboration | In Arbeit | 2026-02-20 | 2026-05-08 | 56 | 1
67 | Manage IT service release | CP | Implementation LIS | Nicht geplant |  |  |  | 1
67 | Manage IT service release | CP | Implementation LUS | Nicht geplant |  |  |  | 1
67 | Manage IT service release | CP | Implementation COT | Nicht geplant |  |  |  | 1
68 | Manage IT sourcing and procurement | SP | Elaboration | In Arbeit | 2026-04-20 | 2026-04-22 | 52 | 1
68 | Manage IT sourcing and procurement | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
68 | Manage IT sourcing and procurement | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
68 | Manage IT sourcing and procurement | SP | Implementation COT | Ohne Angabe |  |  |  | 1
69 | Manage IT strategy | MP | Elaboration | In Arbeit | 2026-02-02 | 2026-04-30 | 64 | 1
69 | Manage IT strategy | MP | Implementation LIS | Terminiert | 2026-05-14 | 2026-07-29 | 55 | 1
69 | Manage IT strategy | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
69 | Manage IT strategy | MP | Implementation COT | Ohne Angabe |  |  |  | 1
70 | Manage IT-C framework | MP | Elaboration | In Arbeit | 2025-10-01 | 2026-09-30 | 261 | 1
70 | Manage IT-C framework | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
70 | Manage IT-C framework | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
70 | Manage IT-C framework | MP | Implementation COT | Ohne Angabe |  |  |  | 1
71 | Manage IT-C strategy | MP | Elaboration | In Arbeit | 2025-10-01 | 2026-09-30 | 261 | 1
71 | Manage IT-C strategy | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
71 | Manage IT-C strategy | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
71 | Manage IT-C strategy | MP | Implementation COT | Ohne Angabe |  |  |  | 1
72 | Manage and control IT financials | MP | Elaboration | In Arbeit | 2025-10-15 | 2026-04-30 | 142 | 1
72 | Manage and control IT financials | MP | Implementation LIS | Terminiert | 2026-05-01 | 2026-07-31 | 66 | 1
72 | Manage and control IT financials | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
72 | Manage and control IT financials | MP | Implementation COT | Ohne Angabe |  |  |  | 1
73 | Manage finance and accounting | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
73 | Manage finance and accounting | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
73 | Manage finance and accounting | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
73 | Manage finance and accounting | MP | Implementation COT | Ohne Angabe |  |  |  | 1
74 | Model and allocate IT costs | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
74 | Model and allocate IT costs | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
74 | Model and allocate IT costs | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
74 | Model and allocate IT costs | MP | Implementation COT | Ohne Angabe |  |  |  | 1
75 | Monitor to delegate | MP | Elaboration | In Arbeit | 2025-10-01 | 2026-09-30 | 261 | 1
75 | Monitor to delegate | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
75 | Monitor to delegate | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
75 | Monitor to delegate | MP | Implementation COT | Ohne Angabe |  |  |  | 1
76 | Onboard new IT employee and manager | SP | Elaboration | In Arbeit | 2025-10-16 | 2026-04-30 | 141 | 1
76 | Onboard new IT employee and manager | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
76 | Onboard new IT employee and manager | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
76 | Onboard new IT employee and manager | SP | Implementation COT | Ohne Angabe |  |  |  | 1
77 | Perform SaaS Security Assessment | SP | Elaboration | In Arbeit | 2025-10-19 | 2025-11-30 | 139 | 1
77 | Perform SaaS Security Assessment | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
77 | Perform SaaS Security Assessment | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
77 | Perform SaaS Security Assessment | SP | Implementation COT | Ohne Angabe |  |  |  | 1
78 | Perform onboarding | SP | Elaboration | In Arbeit | 2025-10-16 | 2026-04-30 | 141 | 1
78 | Perform onboarding | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
78 | Perform onboarding | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
78 | Perform onboarding | SP | Implementation COT | Ohne Angabe |  |  |  | 1
79 | Perform operational process management | MP | Elaboration | In Arbeit | 2026-01-12 | 2026-05-31 | 100 | 1
79 | Perform operational process management | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
79 | Perform operational process management | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
79 | Perform operational process management | MP | Implementation COT | Ohne Angabe |  |  |  | 1
80 | Perform, learn and grow | SP | Elaboration | Ohne Angabe | 2025-10-01 |  |  | 1
80 | Perform, learn and grow | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
80 | Perform, learn and grow | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
80 | Perform, learn and grow | SP | Implementation COT | Ohne Angabe |  |  |  | 1
81 | Plan process execution | MP | Elaboration | In Arbeit | 2026-01-12 | 2026-05-31 | 100 | 1
81 | Plan process execution | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
81 | Plan process execution | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
81 | Plan process execution | MP | Implementation COT | Ohne Angabe |  |  |  | 1
82 | Pre-board new IT employee and manager | SP | Elaboration | In Arbeit | 2025-10-16 | 2026-04-30 | 141 | 1
82 | Pre-board new IT employee and manager | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
82 | Pre-board new IT employee and manager | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
82 | Pre-board new IT employee and manager | SP | Implementation COT | Ohne Angabe |  |  |  | 1
83 | Provide and develop IT workforce | SP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-10-01 | 1 | 1
83 | Provide and develop IT workforce | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
83 | Provide and develop IT workforce | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
83 | Provide and develop IT workforce | SP | Implementation COT | Ohne Angabe |  |  |  | 1
84 | Report actual IT costs | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
84 | Report actual IT costs | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
84 | Report actual IT costs | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
84 | Report actual IT costs | MP | Implementation COT | Ohne Angabe |  |  |  | 1
85 | Requirements to measures | MP | Elaboration | In Arbeit | 2025-10-01 | 2026-09-30 | 261 | 1
85 | Requirements to measures | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
85 | Requirements to measures | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
85 | Requirements to measures | MP | Implementation COT | Ohne Angabe |  |  |  | 1
86 | Review budget plan | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
86 | Review budget plan | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
86 | Review budget plan | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
86 | Review budget plan | MP | Implementation COT | Ohne Angabe |  |  |  | 1
87 | Revise and optimize budget plan | MP | Elaboration | Ohne Angabe | 2025-10-15 |  |  | 1
87 | Revise and optimize budget plan | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
87 | Revise and optimize budget plan | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
87 | Revise and optimize budget plan | MP | Implementation COT | Ohne Angabe |  |  |  | 1
88 | Test and validate IT service | CP | Elaboration | In Arbeit | 2026-05-04 | 2026-07-31 | 44 | 1
88 | Test and validate IT service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
88 | Test and validate IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
88 | Test and validate IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
89 | Deliver IT service | CP | Elaboration | Ohne Angabe |  |  |  | 1
89 | Deliver IT service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
89 | Deliver IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
89 | Deliver IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
90 | Manage HR4IT strategy, governane and framework | SP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-10-01 | 1 | 1
90 | Manage HR4IT strategy, governane and framework | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
90 | Manage HR4IT strategy, governane and framework | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
90 | Manage HR4IT strategy, governane and framework | SP | Implementation COT | Ohne Angabe |  |  |  | 1
91 | Manage IT development programme | SP | Elaboration | Ohne Angabe |  |  |  | 1
91 | Manage IT development programme | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
91 | Manage IT development programme | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
91 | Manage IT development programme | SP | Implementation COT | Ohne Angabe |  |  |  | 1
92 | Manage IT risks | MP | Elaboration | Ohne Angabe |  |  |  | 1
92 | Manage IT risks | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
92 | Manage IT risks | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
92 | Manage IT risks | MP | Implementation COT | Ohne Angabe |  |  |  | 1
93 | Manage IT talent pool and identify potential | SP | Elaboration | Ohne Angabe |  |  |  | 1
93 | Manage IT talent pool and identify potential | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
93 | Manage IT talent pool and identify potential | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
93 | Manage IT talent pool and identify potential | SP | Implementation COT | Ohne Angabe |  |  |  | 1
94 | Monitor and report IT service level | CP | Elaboration | Ohne Angabe |  |  |  | 1
94 | Monitor and report IT service level | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
94 | Monitor and report IT service level | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
94 | Monitor and report IT service level | CP | Implementation COT | Ohne Angabe |  |  |  | 1
95 | Monitor and report IT service performance | CP | Elaboration | Ohne Angabe |  |  |  | 1
95 | Monitor and report IT service performance | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
95 | Monitor and report IT service performance | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
95 | Monitor and report IT service performance | CP | Implementation COT | Ohne Angabe |  |  |  | 1
96 | Ensure IT service continuity | CP | Elaboration | Ohne Angabe |  |  |  | 1
96 | Ensure IT service continuity | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
96 | Ensure IT service continuity | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
96 | Ensure IT service continuity | CP | Implementation COT | Ohne Angabe |  |  |  | 1
97 | Maintain IT asset database | CP | Elaboration | Ohne Angabe |  |  |  | 1
97 | Maintain IT asset database | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
97 | Maintain IT asset database | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
97 | Maintain IT asset database | CP | Implementation COT | Ohne Angabe |  |  |  | 1
98 | Maintain standard change catalogue for IT service | CP | Elaboration | Ohne Angabe |  |  |  | 1
98 | Maintain standard change catalogue for IT service | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
98 | Maintain standard change catalogue for IT service | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
98 | Maintain standard change catalogue for IT service | CP | Implementation COT | Ohne Angabe |  |  |  | 1
99 | Manage IT service capacity | CP | Elaboration | Ohne Angabe |  |  |  | 1
99 | Manage IT service capacity | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
99 | Manage IT service capacity | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
99 | Manage IT service capacity | CP | Implementation COT | Ohne Angabe |  |  |  | 1
100 | Manage IT service desk | CP | Elaboration | Ohne Angabe |  |  |  | 1
100 | Manage IT service desk | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
100 | Manage IT service desk | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
100 | Manage IT service desk | CP | Implementation COT | Ohne Angabe |  |  |  | 1
101 | Manage a common approach to contiual improvement | MP | Elaboration | Ohne Angabe |  |  |  | 1
101 | Manage a common approach to contiual improvement | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
101 | Manage a common approach to contiual improvement | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
101 | Manage a common approach to contiual improvement | MP | Implementation COT | Ohne Angabe |  |  |  | 1
102 | Manage continual improvement initiative | MP | Elaboration | Ohne Angabe |  |  |  | 1
102 | Manage continual improvement initiative | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
102 | Manage continual improvement initiative | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
102 | Manage continual improvement initiative | MP | Implementation COT | Ohne Angabe |  |  |  | 1
103 | Monitor IT service risk and compliance | CP | Elaboration | Ohne Angabe |  |  |  | 1
103 | Monitor IT service risk and compliance | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
103 | Monitor IT service risk and compliance | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
103 | Monitor IT service risk and compliance | CP | Implementation COT | Ohne Angabe |  |  |  | 1
104 | Monitor and analyse events | CP | Elaboration | Ohne Angabe |  |  |  | 1
104 | Monitor and analyse events | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
104 | Monitor and analyse events | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
104 | Monitor and analyse events | CP | Implementation COT | Ohne Angabe |  |  |  | 1
105 | Monitor and report IT service financials | CP | Elaboration | Ohne Angabe |  |  |  | 1
105 | Monitor and report IT service financials | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
105 | Monitor and report IT service financials | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
105 | Monitor and report IT service financials | CP | Implementation COT | Ohne Angabe |  |  |  | 1
106 | Monitor user experience | CP | Elaboration | Ohne Angabe |  |  |  | 1
106 | Monitor user experience | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
106 | Monitor user experience | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
106 | Monitor user experience | CP | Implementation COT | Ohne Angabe |  |  |  | 1
107 | Review and maintain IT service continuity plan | CP | Elaboration | Ohne Angabe |  |  |  | 1
107 | Review and maintain IT service continuity plan | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
107 | Review and maintain IT service continuity plan | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
107 | Review and maintain IT service continuity plan | CP | Implementation COT | Ohne Angabe |  |  |  | 1
108 | Analyse process | MP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-10-01 | 1 | 1
108 | Analyse process | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
108 | Analyse process | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
108 | Analyse process | MP | Implementation COT | Ohne Angabe |  |  |  | 1
109 | Assign personnel resources to IT project | SP | Elaboration | Abgeschlossen | 2025-11-11 | 2025-12-10 | 22 | 1
109 | Assign personnel resources to IT project | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
109 | Assign personnel resources to IT project | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
109 | Assign personnel resources to IT project | SP | Implementation COT | Ohne Angabe |  |  |  | 1
110 | Close IT project | SP | Elaboration | Abgeschlossen | 2025-11-11 | 2025-12-10 | 22 | 1
110 | Close IT project | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
110 | Close IT project | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
110 | Close IT project | SP | Implementation COT | Ohne Angabe |  |  |  | 1
111 | Conduct market analysis and compile long or short list | CP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-12-23 | 1 | 1
111 | Conduct market analysis and compile long or short list | CP | Implementation LIS | Ohne Angabe | 2026-02-16 | 2026-04-30 | 0 | 1
111 | Conduct market analysis and compile long or short list | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
111 | Conduct market analysis and compile long or short list | CP | Implementation COT | Ohne Angabe |  |  |  | 1
112 | Develop and maintain IT BPM framework | MP | Elaboration | Abgeschlossen | 2025-08-04 | 2025-08-30 | 20 | 1
112 | Develop and maintain IT BPM framework | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
112 | Develop and maintain IT BPM framework | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
112 | Develop and maintain IT BPM framework | MP | Implementation COT | Ohne Angabe |  |  |  | 1
113 | Handle IT service request | CP | Elaboration | Abgeschlossen | 2026-02-02 | 2026-03-19 | 34 | 1
113 | Handle IT service request | CP | Implementation LIS | Ohne Angabe |  |  |  | 1
113 | Handle IT service request | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
113 | Handle IT service request | CP | Implementation COT | Ohne Angabe |  |  |  | 1
114 | Initiate IT project | SP | Elaboration | Abgeschlossen | 2025-11-11 | 2025-12-10 | 22 | 1
114 | Initiate IT project | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
114 | Initiate IT project | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
114 | Initiate IT project | SP | Implementation COT | Ohne Angabe |  |  |  | 1
115 | Manage IT project | SP | Elaboration | Abgeschlossen | 2025-11-11 | 2025-12-10 | 22 | 1
115 | Manage IT project | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
115 | Manage IT project | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
115 | Manage IT project | SP | Implementation COT | Ohne Angabe |  |  |  | 1
116 | Manage IT project change request | SP | Elaboration | Abgeschlossen | 2025-11-11 | 2025-12-10 | 22 | 1
116 | Manage IT project change request | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
116 | Manage IT project change request | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
116 | Manage IT project change request | SP | Implementation COT | Ohne Angabe |  |  |  | 1
117 | Manage IT service change | CP | Elaboration | Abgeschlossen | 2026-01-12 | 2026-03-18 | 48 | 1
117 | Manage IT service change | CP | Implementation LIS | Nicht geplant |  |  |  | 1
117 | Manage IT service change | CP | Implementation LUS | Nicht geplant |  |  |  | 1
117 | Manage IT service change | CP | Implementation COT | Nicht geplant |  |  |  | 1
118 | Perform and measure process | MP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-10-01 | 1 | 1
118 | Perform and measure process | MP | Implementation LIS | Ohne Angabe |  |  |  | 1
118 | Perform and measure process | MP | Implementation LUS | Ohne Angabe |  |  |  | 1
118 | Perform and measure process | MP | Implementation COT | Ohne Angabe |  |  |  | 1
119 | Perform vendor use case pitch and usability test | CP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-12-23 | 1 | 1
119 | Perform vendor use case pitch and usability test | CP | Implementation LIS | Ohne Angabe | 2026-02-16 | 2026-04-30 | 0 | 1
119 | Perform vendor use case pitch and usability test | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
119 | Perform vendor use case pitch and usability test | CP | Implementation COT | Ohne Angabe |  |  |  | 1
120 | Plan IT project | SP | Elaboration | Abgeschlossen | 2025-11-11 | 2025-12-10 | 22 | 1
120 | Plan IT project | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
120 | Plan IT project | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
120 | Plan IT project | SP | Implementation COT | Ohne Angabe |  |  |  | 1
121 | Recommendation and EA approval | CP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-12-23 | 1 | 1
121 | Recommendation and EA approval | CP | Implementation LIS | Ohne Angabe | 2026-02-16 | 2026-04-30 | 0 | 1
121 | Recommendation and EA approval | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
121 | Recommendation and EA approval | CP | Implementation COT | Ohne Angabe |  |  |  | 1
122 | Record and plan functional requirements | CP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-12-23 | 1 | 1
122 | Record and plan functional requirements | CP | Implementation LIS | Ohne Angabe | 2026-02-16 | 2026-04-30 | 0 | 1
122 | Record and plan functional requirements | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
122 | Record and plan functional requirements | CP | Implementation COT | Ohne Angabe |  |  |  | 1
123 | Steer and execute IT project | SP | Elaboration | Abgeschlossen | 2025-11-11 | 2025-12-10 | 22 | 1
123 | Steer and execute IT project | SP | Implementation LIS | Ohne Angabe |  |  |  | 1
123 | Steer and execute IT project | SP | Implementation LUS | Ohne Angabe |  |  |  | 1
123 | Steer and execute IT project | SP | Implementation COT | Ohne Angabe |  |  |  | 1
124 | Validate strategic fit | CP | Elaboration | Abgeschlossen | 2025-10-01 | 2025-12-23 | 1 | 1
124 | Validate strategic fit | CP | Implementation LIS | Ohne Angabe | 2026-02-16 | 2026-04-30 | 0 | 1
124 | Validate strategic fit | CP | Implementation LUS | Ohne Angabe |  |  |  | 1
124 | Validate strategic fit | CP | Implementation COT | Ohne Angabe |  |  |  | 1

## Listen (hidden)
Auswahllisten für die Felder im Cockpit
Prozessgruppe | Initiative | L1-Prozess | Ebene | Status | Process Manager
(Alle) | (Alle) | (Alle) | (Alle) | (Alle) | (Alle)
CP | Architecture management | Build IT Service | L1 | Verzögert | Mielenz Thomas (LMT)
MP | Central area (Jan Müskens) | Deliver IT service | L2 | In Arbeit | Monnier Murielle (LEC)
SP | Corporate IT body | Ensure Information security | L3 | Terminiert | Moser Mario (LIS-LAH)
| HR initiatives for IT | Ensure performance and conformance of IT services | L4 | Abgeschlossen | Nussbaumer Florian (LBC)
| IT planning and steering | Leverage IT innovation |  | Nicht geplant | Reiner Heiko (HAU-ITSA)
| IT project management | Manage IT governance framework |  |  | Rollinger Alexander (LIS)
| ITSM | Manage IT knowledge |  |  | Schnurrenberger Christoph (LIS-LIN)
| Information security | Manage IT portfolio |  |  | Sint Rachel (LBH)
| n/a | Manage IT processes and continuous improvement |  |  | Wiehe Alexander (COB)
|  | Manage IT project |  |  | –
Manage IT risks and compliance
Manage IT sourcing and procurement
Manage IT stakeholder relationships
Manage IT strategy
Manage and control IT financials
Manage enterprise architecture
Plan IT service
Provide and develop IT workforce
Run IT service

## Auswertung (hidden)
Auswertung – speist die Diagramme im Cockpit. Alle Werte sind Formeln über die Trefferspalte.
Status | Anzahl |  | Prozessgruppe | Verzögert | In Arbeit | Terminiert | Abgeschlossen | Nicht geplant
Verzögert | 29 | MP | MP · Management | 6 | 39 | 1 | 3 | 2
In Arbeit | 59 | CP | CP · Core | 12 | 10 | 3 | 7 | 10
Terminiert | 7 | SP | SP · Support | 11 | 10 | 3 | 7 | 0
Abgeschlossen | 17
Nicht geplant | 12
Initiative | Ø Fortschritt | Prozesse |  | L1-Prozessbereich | davon verzögert
Architecture management | 92.86% | 7 |  | Provide and develop IT workforce | 9
Central area (Jan Müskens) | 21.88% | 8 |  | Plan IT service | 5
Corporate IT body | 56.82% | 11 |  | Run IT service | 3
HR initiatives for IT | 12.61% | 18 |  | Deliver IT service | 2
IT planning and steering | 50% | 21 |  | Build IT Service | 2
IT project management | 100% | 8 |  | Manage enterprise architecture | 2
ITSM | 28.33% | 48 |  | Ensure performance and conformance of IT services | 1
Information security | 50% | 2 |  | Manage IT processes and continuous improvement | 1
n/a | 22% | 1 |  | Manage IT knowledge | 1
|  |  |  | Manage IT portfolio | 1
Phase | terminiert | abgeschlossen
Elaboration | 104 | 30
Implementation LIS | 30 | 0
Implementation LUS | 4 | 0
Implementation COT | 12 | 0

## Hinweise
IT Process Portfolio – Cockpit
Bedienung
Im Blatt Cockpit die gelb hinterlegten Auswahlfelder ändern. Kennzahlen, Diagramme und
die Trefferliste rechnen sofort neu. Alle übrigen Zellen sind gesperrt, damit nichts
versehentlich überschrieben wird; ein Kennwort wird dafür nicht benötigt.
Die Blätter Prozesse und Phasen tragen echte Excel-Tabellen: dort lässt sich zusätzlich
über die Spaltenköpfe filtern und sortieren.
Gemeinsames Arbeiten
Die Auswahlfelder sind Zellen der Mappe. Ändert sie jemand, sehen alle anderen dieselbe
Auswahl. Wer für sich allein filtern möchte, nutzt in Excel für das Web auf den Blättern
Prozesse oder Phasen die Blattansicht (Ansicht > Blattansicht > Neu).
Wie der Status entsteht
Verzögert – mindestens eine Phase trägt in der Projektplanung die Ist-Phase "Delayed".
Verzögerung hat Vorrang vor allen anderen Zuständen.
Abgeschlossen – 100 % Arbeitsfortschritt oder alle vier Phasen fertig.
In Arbeit – Fortschritt über 0 % oder eine Phase in Bearbeitung.
Terminiert – Termine vorhanden, aber noch keine Bearbeitung.
Nicht geplant – weder Termine noch Status.
Überfällig – der späteste Phasentermin liegt vor dem Stichtag und der Prozess ist nicht
abgeschlossen. Der Stichtag ist das siebte Auswahlfeld und frei setzbar.
Herkunft der Daten
Quelle: Process_Portfolio_Timeline.xlsx, Blatt "data Draft-april26" (Draft April 2026).
Die Hierarchie steckt dort in der Einrückung der Spalte Process; je Prozess gibt es eine
Summenzeile und vier Phasenzeilen. Daraus entstehen 124 Prozesse über vier Ebenen.
19 Prozesse tragen keine Termine, in den Phasen LUS und COT ist bislang kein Fortschritt
erfasst – beides ist so aus der Planung übernommen und nicht geglättet.
Neu erzeugen nach einer aktualisierten Planung: python3 build/excel.py